## Read Me
Output Artefact Index
Purpose | Every file produced for Steps 1-20, mapped to the atomic step that required it.
Scope | Steps 1-35. 35 atomic steps, 241 gates.
Project | Habot UDF mobile client (Flutter) - habot-mobile/udf_setup
Owner | Fredrick
Date | 12 August 2026
Requirements source | My stepsFN06082026.xlsx -> Fredrick sheet
Tabs | Code Artefacts - every file in the Flutter project, its owning step and its category
By Step - one row per atomic step: artefacts produced, gate file, gate count, status
Documents - the deliverables in Others/Fredrick and what each one is for
OWNING STEP | The step whose requirements caused the file to exist. Shared infrastructure files
(main.dart, the reporter, the guard, verify_aiss.sh) serve all 35 and are marked "All".
STATUS | Complete / Partial is DERIVED from gate outcomes, never asserted. A step is Partial
when a requirement is knowingly open with a recorded reason - Step 6 (zoom lock, CLS)
and Step 31 (physical-device confirmation of the overscroll stretch).
Step 14 was Partial after batch 2 and is now Complete: Steps 34-35 built the telemetry
its deferred gate was waiting on.
NOT YET COMPILED | The code has been statically verified but not compiled. Run:
cd habot-mobile/udf_setup && ./tool/verify_aiss.sh

## By Step
Impl. Order | Global Ref ID | Atomic Step Ref ID | Original S. No | Setup Step (Action) | Artefacts Produced | Artefact Paths | Gate File | Gates | Deferred | Derived Status | Per-step Summary Doc
1 | TTMCS-001 | TTMCS-001-A01 | 1797 | Install and configure the verified Material 3 layout component framework within frontend client packages. | 5 | lib/design_system/theme/habot_theme.dart lib/design_system/theme/habot_theme_extension.dart lib/design_system/layout/fluid_container.dart lib/design_system/layout/page_frame.dart lib/app.dart | test/aiss/ttmcs_001_test.dart | 7 | 0 | Complete | step_summaries/Step_01_TTMCS-001.md
2 | RCGLA-001 | RCGLA-001-A01 | 3227 | Build global corporate style token variables inside the mobile client framework. | 7 | lib/design_system/tokens/tokens.json lib/design_system/tokens/color_tokens.dart lib/design_system/tokens/spacing_tokens.dart lib/design_system/tokens/typography_tokens.dart lib/design_system/tokens/elevation_tokens.dart lib/design_system/tokens/grid_tokens.dart lib/design_system/tokens/shape_tokens.dart | test/aiss/rcgla_001_test.dart | 6 | 0 | Complete | step_summaries/Step_02_RCGLA-001.md
3 | TTMCS-004 | TTMCS-004-A01 | 1654 | TTMCS-004 — Configure Atomic Light/Dark Adaptation Tokens | 4 | lib/design_system/theme/theme_controller.dart lib/design_system/theme/habot_theme_scope.dart lib/design_system/a11y/contrast.dart lib/design_system/a11y/contrast_audit.dart | test/aiss/ttmcs_004_test.dart | 9 | 0 | Complete | step_summaries/Step_03_TTMCS-004.md
4 | TTMCS-005 | TTMCS-005-A01 | 3139 | TTMCS-005 — Mobile Dark Mode Contrast Enforcement | 4 | lib/design_system/tokens/elevation_tokens.dart lib/design_system/theme/habot_theme_extension.dart lib/design_system/a11y/contrast_audit.dart build/aiss/contrast_audit.txt | test/aiss/ttmcs_005_test.dart | 8 | 0 | Complete | step_summaries/Step_04_TTMCS-005.md
5 | SSTLA-004 | SSTLA-004-A01 | 169 | Define the exact base breakpoint, column count, fluid margin, and gutter widths for the core mobile experience before scaling upward to tablet or desktop views. | 3 | lib/design_system/tokens/device_matrix.json lib/design_system/layout/device_profiles.dart lib/design_system/layout/grid_wireframe.dart | test/aiss/sstla_004_test.dart | 8 | 0 | Complete | step_summaries/Step_05_SSTLA-004.md
6 | RCGLA-012 | RCGLA-012-A01 | 345 | RCGLA-012 - Initialize Atomic Grid System & Mobile Viewport Constraints | 3 | lib/design_system/layout/mobile_grid_container.dart lib/design_system/tokens/grid_tokens.dart web/index.html | test/aiss/rcgla_012_test.dart | 7 | 2 | Partial | step_summaries/Step_06_RCGLA-012.md
7 | RCGLA-032 | RCGLA-032-A01 | 3051 | RCGLA-032 - Configure the Material Design 3 (MD3) adaptive 4-column fluid layout token engine for mobile screens. | 3 | lib/design_system/layout/layout_boundary.dart lib/design_system/layout/fluid_container.dart lib/design_system/tokens/grid_tokens.dart | test/aiss/rcgla_032_test.dart | 7 | 0 | Complete | step_summaries/Step_07_RCGLA-032.md
8 | RCGLA-018 | RCGLA-018-A01 | 356 | RCGLA-018 - Universal Master Layout Architecture for React Components | 2 | lib/design_system/layout/master_scaffold.dart lib/app.dart | test/aiss/rcgla_018_test.dart | 6 | 0 | Complete | step_summaries/Step_08_RCGLA-018.md
9 | ANSA-012 | ANSA-012-A01 | 4 | Establish Contextual Navigation Header Framework. | 2 | lib/design_system/navigation/contextual_header.dart lib/design_system/navigation/back_navigation.dart | test/aiss/ansa_012_test.dart | 7 | 0 | Complete | step_summaries/Step_09_ANSA-012.md
10 | TTMAC-011 | TTMAC-011-A01 | 3095 | Touch-Target Optimization Framework Setup (48×48 dp Minimum Interaction Nodes). | 1 | lib/design_system/interaction/touch_target.dart | test/aiss/ttmac_011_test.dart | 7 | 0 | Complete | step_summaries/Step_10_TTMAC-011.md
11 | BPTR-0422 | BPTR-0422-A01 | 257 | Define Passive Failure Motion Curves. | 2 | lib/design_system/tokens/motion_tokens.dart lib/design_system/tokens/tokens.json | test/aiss/bptr_0422_test.dart | 8 | 0 | Complete | step_summaries/Step_11_BPTR-0422.md
12 | REF-377 | REF-377-A01 | 400 | Set Progressive Stepper Transitions. | 2 | lib/design_system/tokens/motion_tokens.dart lib/design_system/wizard/carousel_stepper.dart | test/aiss/ref_377_test.dart | 6 | 0 | Complete | step_summaries/Step_12_REF-377.md
13 | BPTR-0128 | BPTR-0128-A01 | 1566 | Establish Global Atomic Byt Micro-Interaction Boundaries | 2 | lib/design_system/interaction/atomic_button.dart lib/design_system/interaction/interaction_states.dart | test/aiss/bptr_0128_test.dart | 7 | 0 | Complete | step_summaries/Step_13_BPTR-0128.md
14 | TTMAC-014 | TTMAC-014-A01 | 2028 | TTMAC-014 - Interactive Touch Target Standardization Engine Setup | 2 | lib/design_system/interaction/touch_standards.dart lib/design_system/interaction/touch_target.dart | test/aiss/ttmac_014_test.dart | 7 | 0 | Complete | step_summaries/Step_14_TTMAC-014.md
15 | CSIVW-001 | CSIVW-001-A01 | 3062 | Implement strict client-side Input Masking on all template text area entry portals. | 2 | lib/design_system/forms/input_mask.dart lib/design_system/forms/field_validation.dart | test/aiss/csivw_001_test.dart | 7 | 0 | Complete | step_summaries/Step_15_CSIVW-001.md
16 | IS12-CSIVW-011-AS01 | IS12-CSIVW-011-AS01-A01 | 3205 | Setup character formatting filters across text entry boxes. | 3 | lib/design_system/forms/validated_input_field.dart lib/design_system/forms/field_validation.dart lib/design_system/forms/form_gate.dart | test/aiss/is12_csivw_011_test.dart | 7 | 0 | Complete | step_summaries/Step_16_IS12-CSIVW-011-AS01.md
17 | IS02-CSIVW-005-AS01 | IS02-CSIVW-005-AS01-A01 | 2490 | Program dynamic inline error layouts to activate when input fields fail validation checks. | 2 | lib/design_system/forms/inline_error.dart lib/design_system/forms/form_gate.dart | test/aiss/is02_csivw_005_test.dart | 6 | 0 | Complete | step_summaries/Step_17_IS02-CSIVW-005-AS01.md
18 | BPTR-0160 | BPTR-0160-A01 | 3073 | Code and isolate mobile compound fields into distinct, standalone UI components featuring strict 48x48dp touch targets. | 2 | lib/design_system/forms/compound_field.dart lib/design_system/forms/field_validation.dart | test/aiss/bptr_0160_test.dart | 7 | 0 | Complete | step_summaries/Step_18_BPTR-0160.md
19 | REF-197 | REF-197-A01 | 3238 | Developing the Safe Error-Handling UI Rollback Handler | 3 | lib/design_system/resilience/error_templates.dart lib/design_system/resilience/log_scrubber.dart lib/design_system/resilience/error_rollback_boundary.dart | test/aiss/ref_197_test.dart | 7 | 0 | Complete | step_summaries/Step_19_REF-197.md
20 | FIEVR-033 | FIEVR-033-A01 | 3128 | FIEVR-033 - Build Multi-Step Guided Carousel Layout Stepper | 2 | lib/design_system/wizard/step_machine.dart lib/design_system/wizard/carousel_stepper.dart | test/aiss/fievr_033_test.dart | 8 | 0 | Complete | step_summaries/Step_20_FIEVR-033.md
21 | GEN-00055 | GEN-00055-A01 | 8298 | Build the BottomSheet atomic component using MD3 design tokens. | 2 | lib/design_system/surfaces/bottom_sheet.dart lib/design_system/tokens/surface_tokens.dart | test/aiss/gen_00055_test.dart | 7 | 0 | Complete | step_summaries/Step_21_GEN-00055.md
22 | GEN-00954 | GEN-00954-A01 | 9189 | Standardize Material Design 3 (MD3) Bottom-Sheet UI for Mobile Complex Action Flows | 3 | lib/design_system/surfaces/bottom_sheet.dart lib/design_system/tokens/color_tokens.dart lib/design_system/tokens/surface_tokens.dart | test/aiss/gen_00954_test.dart | 6 | 0 | Complete | step_summaries/Step_22_GEN-00954.md
23 | GEN-00235 | GEN-00235-A01 | 8474 | Set the default snapping point to 60% viewport height for optimal thumb interaction. | 3 | lib/design_system/surfaces/bottom_sheet.dart lib/design_system/tokens/surface_tokens.dart lib/design_system/tokens/tokens.json | test/aiss/gen_00235_test.dart | 6 | 0 | Complete | step_summaries/Step_23_GEN-00235.md
24 | MUFCE-028 | MUFCE-028-A01 | 1786 | Mandatory removal of all mouse hover tooltips and replacement with touch long-press modal sheets. | 4 | lib/design_system/surfaces/metadata_disclosure.dart lib/design_system/interaction/touch_target.dart lib/design_system/navigation/contextual_header.dart test/guards/poka_yoke_no_hardcoded_values_test.dart | test/aiss/mufce_028_test.dart | 7 | 0 | Complete | step_summaries/Step_24_MUFCE-028.md
25 | GEN-01363 | GEN-01363-A01 | 9596 | Bind the client UI error boundaries to trigger M3 error Snackbars upon caught exceptions. | 2 | lib/design_system/feedback/error_snackbar.dart lib/design_system/resilience/error_rollback_boundary.dart | test/aiss/gen_01363_test.dart | 7 | 0 | Complete | step_summaries/Step_25_GEN-01363.md
26 | GEN-01848 | GEN-01848-A01 | 10080 | Implement visual progress indicators to show user advancement. | 1 | lib/design_system/feedback/progress_indicators.dart | test/aiss/gen_01848_test.dart | 7 | 0 | Complete | step_summaries/Step_26_GEN-01848.md
27 | GEN-01297 | GEN-01297-A01 | 9530 | Implement an empty state container with custom illustrations to display when search queries return zero logs. | 1 | lib/design_system/feedback/empty_state.dart | test/aiss/gen_01297_test.dart | 6 | 0 | Complete | step_summaries/Step_27_GEN-01297.md
28 | GEN-01275 | GEN-01275-A01 | 9508 | Embed M3 status Badges to mark completed and active milestone nodes. | 1 | lib/design_system/feedback/status_badge.dart | test/aiss/gen_01275_test.dart | 6 | 0 | Complete | step_summaries/Step_28_GEN-01275.md
29 | GEN-01452 | GEN-01452-A01 | 9684 | Construct the card UI chassis using M3 Outlined or Elevated Card specifications. | 1 | lib/design_system/surfaces/card_chassis.dart | test/aiss/gen_01452_test.dart | 7 | 0 | Complete | step_summaries/Step_29_GEN-01452.md
30 | GEN-00201 | GEN-00201-A01 | 8441 | Use Material Design 3 shared axis transitions for mobile view state changes. | 2 | lib/design_system/motion/shared_axis.dart lib/design_system/tokens/motion_tokens.dart | test/aiss/gen_00201_test.dart | 6 | 0 | Complete | step_summaries/Step_30_GEN-00201.md
31 | IS38-SGTIM-018-AS01 | IS38-SGTIM-018-AS01-A01 | 1555 | Apply M3 Overscroll Stretch on MTOI Lists | 2 | lib/design_system/layout/habot_scroll_behavior.dart lib/app.dart | test/aiss/is38_sgtim_018_test.dart | 8 | 1 | Partial | step_summaries/Step_31_IS38-SGTIM-018-AS01.md
32 | CPNCA-006 | CPNCA-006-A01 | 2468 | Build a standardized list virtualization and dynamic data chunking component for data tables Operationalizing System Architecture Design]. | 2 | lib/design_system/layout/virtualized_list.dart lib/design_system/tokens/surface_tokens.dart | test/aiss/cpnca_006_test.dart | 7 | 0 | Complete | step_summaries/Step_32_CPNCA-006.md
33 | ANSA-006 | ANSA-006-A01 | 3194 | Implementation Step 15: Build an expandable search text line inside primary system headers. (ANSA-006) | 2 | lib/design_system/navigation/header_search.dart lib/design_system/tokens/surface_tokens.dart | test/aiss/ansa_006_test.dart | 7 | 0 | Complete | step_summaries/Step_33_ANSA-006.md
34 | UFHT-032 | UFHT-032-A01 | 4723 | UI Hesitation Tracker Engine Setup | 2 | lib/design_system/telemetry/hesitation_tracker.dart lib/design_system/forms/validated_input_field.dart | test/aiss/ufht_032_test.dart | 7 | 0 | Complete | step_summaries/Step_34_UFHT-032.md
35 | GEN-00632 | GEN-00632-A01 | 8870 | Deploy Mobile UX Friction Logs (Hesitation Tracking) | 2 | lib/design_system/telemetry/friction_tracker.dart lib/design_system/telemetry/hesitation_tracker.dart | test/aiss/gen_00632_test.dart | 5 | 0 | Complete | step_summaries/Step_35_GEN-00632.md

## Code Artefacts
# | Path (relative to udf_setup/) | Category | Kind | Owning Step(s) | Owning Ref ID(s) | Gates Asserting Against It | Step Status | What It Is
1 | analysis_options.yaml | Project config | Config | All (1-35) | shared infrastructure | 241 | n/a | Analyzer configuration (deliberately conservative - see the comment block).
2 | lib/app.dart | Application shell | Dart source | 1, 8, 31 | TTMCS-001, RCGLA-018, IS38-SGTIM-018-AS01 | 21 | Partial | Root widget, single theme controller owner, and the design-system probe screen.
3 | lib/data_entry_probe_page.dart | Application shell | Dart source | 11-20 (shared probe) | forms & feedback batch | 70 | Complete | Probe screen for the Steps 11-20 forms/feedback layer.
4 | lib/design_system/a11y/contrast.dart | Accessibility | Dart source | 3 | TTMCS-004 | 9 | Complete | WCAG 2.1 relative luminance and contrast-ratio implementation.
5 | lib/design_system/a11y/contrast_audit.dart | Accessibility | Dart source | 3, 4 | TTMCS-004, TTMCS-005 | 17 | Complete | Audits every scheme colour pair against the 4.5:1 / 7:1 policy.
6 | lib/design_system/aiss/aiss_evidence.dart | Evidence model | Dart source | All (1-35) | shared infrastructure | 241 | n/a | Gate and step evidence model. Derives completion status from gate outcomes.
7 | lib/design_system/feedback/empty_state.dart | Feedback | Dart source | 27 | GEN-01297 | 6 | Complete | Four empty reasons, each with its own illustration, copy and action decision.
8 | lib/design_system/feedback/error_snackbar.dart | Feedback | Dart source | 25 | GEN-01363 | 7 | Complete | M3 error snackbar bound to the error boundary. Cannot show an unscrubbed message.
9 | lib/design_system/feedback/progress_indicators.dart | Feedback | Dart source | 26 | GEN-01848 | 7 | Complete | Determinate bar, spinner and step progress. Reduced motion makes them static.
10 | lib/design_system/feedback/status_badge.dart | Feedback | Dart source | 28 | GEN-01275 | 6 | Complete | One status vocabulary. Icon and label always, so colour is never the only carrier.
11 | lib/design_system/forms/compound_field.dart | Forms | Dart source | 18 | BPTR-0160 | 7 | Complete | Compound fields (date, name, address) as isolated 48dp parts.
12 | lib/design_system/forms/field_validation.dart | Forms | Dart source | 15, 16, 18 | CSIVW-001, IS12-CSIVW-011-AS01, BPTR-0160 | 21 | Complete | The 13 Critical Data Element rules: regex, keyboard, placeholder, message.
13 | lib/design_system/forms/form_gate.dart | Forms | Dart source | 16, 17 | IS12-CSIVW-011-AS01, IS02-CSIVW-005-AS01 | 13 | Complete | Single authority on whether a form may be submitted.
14 | lib/design_system/forms/inline_error.dart | Forms | Dart source | 17 | IS02-CSIVW-005-AS01 | 6 | Complete | Blur-bound inline error layout, bodySmall in the audited error colour.
15 | lib/design_system/forms/input_mask.dart | Forms | Dart source | 15 | CSIVW-001 | 7 | Complete | Keystroke-level input masking, ASCII hygiene, paste caps.
16 | lib/design_system/forms/validated_input_field.dart | Forms | Dart source | 16, 34 | IS12-CSIVW-011-AS01, UFHT-032 | 14 | Complete | The only text input in the app. Cannot exist without a CDE.
17 | lib/design_system/interaction/atomic_button.dart | Interaction | Dart source | 13 | BPTR-0128 | 7 | Complete | The atomic button primitive (13-line build).
18 | lib/design_system/interaction/interaction_states.dart | Interaction | Dart source | 13 | BPTR-0128 | 7 | Complete | Material 3 state-layer opacities for hover/focus/press/drag.
19 | lib/design_system/interaction/touch_standards.dart | Interaction | Dart source | 14 | TTMAC-014 | 7 | Complete | Touch standards engine: protective padding, icon sizes, clearance.
20 | lib/design_system/interaction/touch_target.dart | Interaction | Dart source | 10, 14, 24 | TTMAC-011, TTMAC-014, MUFCE-028 | 21 | Complete | 48dp minimum tap area with transparent expansion and safety margin.
21 | lib/design_system/layout/device_profiles.dart | Layout | Dart source | 5 | SSTLA-004 | 8 | Complete | The 9-device test matrix, mirrored from device_matrix.json.
22 | lib/design_system/layout/fluid_container.dart | Layout | Dart source | 1, 7 | TTMCS-001, RCGLA-032 | 14 | Complete | Fluid container that reflows on window class.
23 | lib/design_system/layout/grid_wireframe.dart | Layout | Dart source | 5 | SSTLA-004 | 8 | Complete | Debug overlay drawing the live column / gutter / rhythm grid.
24 | lib/design_system/layout/habot_scroll_behavior.dart | Layout | Dart source | 31 | IS38-SGTIM-018-AS01 | 8 | Partial | App-wide scroll behaviour: stretch on Android family, bounce on iOS, never a glow.
25 | lib/design_system/layout/layout_boundary.dart | Layout | Dart source | 7 | RCGLA-032 | 7 | Complete | Global layout boundary and vertical segment listener.
26 | lib/design_system/layout/master_scaffold.dart | Layout | Dart source | 8 | RCGLA-018 | 6 | Complete | The wrapper every screen must use. No padding escape hatch.
27 | lib/design_system/layout/mobile_grid_container.dart | Layout | Dart source | 6 | RCGLA-012 | 7 | Partial | Compact-class grid container (17-line build).
28 | lib/design_system/layout/page_frame.dart | Layout | Dart source | 1 | TTMCS-001 | 7 | Complete | Page frame binding scaffold, header and safe area.
29 | lib/design_system/layout/virtualized_list.dart | Layout | Dart source | 32 | CPNCA-006 | 7 | Complete | List virtualisation and chunked fetching. Flat element count at 10,000 rows.
30 | lib/design_system/motion/shared_axis.dart | Motion | Dart source | 30 | GEN-00201 | 6 | Complete | MD3 shared-axis transitions with a disjoint fade-through.
31 | lib/design_system/navigation/back_navigation.dart | Navigation | Dart source | 9 | ANSA-012 | 7 | Complete | Double-tap-safe back navigation with a token-driven debounce.
32 | lib/design_system/navigation/contextual_header.dart | Navigation | Dart source | 9, 24 | ANSA-012, MUFCE-028 | 14 | Complete | 64dp contextual header: title cap, action priority, scroll elevation.
33 | lib/design_system/navigation/header_search.dart | Navigation | Dart source | 33 | ANSA-006 | 7 | Complete | Header search: debounce, punctuation filter, grouped results, local history.
34 | lib/design_system/resilience/error_rollback_boundary.dart | Resilience | Dart source | 19, 25 | REF-197, GEN-01363 | 14 | Complete | Transaction rollback boundary around failable submissions.
35 | lib/design_system/resilience/error_templates.dart | Resilience | Dart source | 19 | REF-197 | 7 | Complete | The 9 error categories and their plain-language templates.
36 | lib/design_system/resilience/log_scrubber.dart | Resilience | Dart source | 19 | REF-197 | 7 | Complete | Removes URLs, paths, IPs, emails, tokens and SQL from anything logged.
37 | lib/design_system/surfaces/bottom_sheet.dart | Surfaces | Dart source | 21, 22, 23 | GEN-00055, GEN-00954, GEN-00235 | 19 | Complete | The bottom sheet: chassis, 32% scrim, 60% snap point. The only modal surface.
38 | lib/design_system/surfaces/card_chassis.dart | Surfaces | Dart source | 29 | GEN-01452 | 7 | Complete | Card chassis: filled, outlined, elevated. Never a border and a shadow together.
39 | lib/design_system/surfaces/metadata_disclosure.dart | Surfaces | Dart source | 24 | MUFCE-028 | 7 | Complete | The only route by which metadata reaches the screen. Replaced every tooltip.
40 | lib/design_system/telemetry/friction_tracker.dart | Telemetry | Dart source | 35 | GEN-00632 | 5 | Complete | Screen wrapper turning interactions into a friction report. Closes the Step 14 deferral.
41 | lib/design_system/telemetry/hesitation_tracker.dart | Telemetry | Dart source | 34, 35 | UFHT-032, GEN-00632 | 12 | Complete | Focus listeners on every field. Records that something happened, never what.
42 | lib/design_system/theme/habot_theme.dart | Theme | Dart source | 1 | TTMCS-001 | 7 | Complete | The ONLY file permitted to construct a ThemeData.
43 | lib/design_system/theme/habot_theme_extension.dart | Theme | Dart source | 1, 4 | TTMCS-001, TTMCS-005 | 15 | Complete | HabotTokens ThemeExtension carrying tokens through the tree.
44 | lib/design_system/theme/habot_theme_scope.dart | Theme | Dart source | 3 | TTMCS-004 | 9 | Complete | InheritedNotifier exposing the theme controller without a full reflow.
45 | lib/design_system/theme/theme_controller.dart | Theme | Dart source | 3 | TTMCS-004 | 9 | Complete | OS brightness listener and light/dark mode state.
46 | lib/design_system/tokens/color_tokens.dart | Token constants | Dart source | 2, 22 | RCGLA-001, GEN-00954 | 12 | Complete | 28 colour roles x light/dark, mirrored from tokens.json.
47 | lib/design_system/tokens/device_matrix.json | Token data (source of truth) | JSON data | 5 | SSTLA-004 | 8 | Complete | 9-device matrix plus the decision record for the gutter contradiction.
48 | lib/design_system/tokens/elevation_tokens.dart | Token constants | Dart source | 2, 4 | RCGLA-001, TTMCS-005 | 14 | Complete | Elevation ladder and the dark-surface composite derivation.
49 | lib/design_system/tokens/grid_tokens.dart | Token constants | Dart source | 2, 6, 7 | RCGLA-001, RCGLA-012, RCGLA-032 | 20 | Partial | Breakpoints, columns, margin, gutter, vertical rhythm.
50 | lib/design_system/tokens/motion_tokens.dart | Token constants | Dart source | 11, 12, 30 | BPTR-0422, REF-377, GEN-00201 | 20 | Complete | Durations, curves and the reduced-motion policy.
51 | lib/design_system/tokens/shape_tokens.dart | Token constants | Dart source | 2 | RCGLA-001 | 6 | Complete | Corner radius scale.
52 | lib/design_system/tokens/spacing_tokens.dart | Token constants | Dart source | 2 | RCGLA-001 | 6 | Complete | Spacing scale and density constants.
53 | lib/design_system/tokens/surface_tokens.dart | Token constants | Dart source | 21, 22, 23, 32, 33 | GEN-00055, GEN-00954, GEN-00235, CPNCA-006, ANSA-006 | 33 | Complete | Every dimension the surface, feedback and discovery layers use.
54 | lib/design_system/tokens/tokens.json | Token data (source of truth) | JSON data | 2, 11, 23 | RCGLA-001, BPTR-0422, GEN-00235 | 20 | Complete | SOURCE OF TRUTH for every design token. Marked PROVISIONAL pending Brand.
55 | lib/design_system/tokens/typography_tokens.dart | Token constants | Dart source | 2 | RCGLA-001 | 6 | Complete | The 15-entry type scale, mirrored from tokens.json.
56 | lib/design_system/wizard/carousel_stepper.dart | Wizard | Dart source | 12, 20 | REF-377, FIEVR-033 | 14 | Complete | The guided multi-step form shell (17-line build).
57 | lib/design_system/wizard/step_machine.dart | Wizard | Dart source | 20 | FIEVR-033 | 8 | Complete | Wizard state machine: step order, validity, progress.
58 | lib/main.dart | Application shell | Dart source | All (1-35) | shared infrastructure | 241 | n/a | Entry point. Runs HabotApp and nothing else.
59 | lib/surfaces_probe_page.dart | Application shell | Dart source | 11-20 (shared probe) | forms & feedback batch | 99 | Complete | Probe screen for the Steps 21-35 surface, feedback and telemetry layers.
60 | test/aiss/aiss_reporter.dart | Test support | Dart source | All (1-35) | shared infrastructure | 241 | n/a | Collects gate outcomes and writes build/aiss/evidence.json.
61 | test/aiss/ansa_006_test.dart | Gate suite | Dart source | 33 | ANSA-006 | 7 | Complete | The 7 gates for Step 33 (ANSA-006) - one assertion per requirement column.
62 | test/aiss/ansa_012_test.dart | Gate suite | Dart source | 9 | ANSA-012 | 7 | Complete | The 7 gates for Step 9 (ANSA-012) - one assertion per requirement column.
63 | test/aiss/bptr_0128_test.dart | Gate suite | Dart source | 13 | BPTR-0128 | 7 | Complete | The 7 gates for Step 13 (BPTR-0128) - one assertion per requirement column.
64 | test/aiss/bptr_0160_test.dart | Gate suite | Dart source | 18 | BPTR-0160 | 7 | Complete | The 7 gates for Step 18 (BPTR-0160) - one assertion per requirement column.
65 | test/aiss/bptr_0422_test.dart | Gate suite | Dart source | 11 | BPTR-0422 | 8 | Complete | The 8 gates for Step 11 (BPTR-0422) - one assertion per requirement column.
66 | test/aiss/cpnca_006_test.dart | Gate suite | Dart source | 32 | CPNCA-006 | 7 | Complete | The 7 gates for Step 32 (CPNCA-006) - one assertion per requirement column.
67 | test/aiss/csivw_001_test.dart | Gate suite | Dart source | 15 | CSIVW-001 | 7 | Complete | The 7 gates for Step 15 (CSIVW-001) - one assertion per requirement column.
68 | test/aiss/fievr_033_test.dart | Gate suite | Dart source | 20 | FIEVR-033 | 8 | Complete | The 8 gates for Step 20 (FIEVR-033) - one assertion per requirement column.
69 | test/aiss/gen_00055_test.dart | Gate suite | Dart source | 21 | GEN-00055 | 7 | Complete | The 7 gates for Step 21 (GEN-00055) - one assertion per requirement column.
70 | test/aiss/gen_00201_test.dart | Gate suite | Dart source | 30 | GEN-00201 | 6 | Complete | The 6 gates for Step 30 (GEN-00201) - one assertion per requirement column.
71 | test/aiss/gen_00235_test.dart | Gate suite | Dart source | 23 | GEN-00235 | 6 | Complete | The 6 gates for Step 23 (GEN-00235) - one assertion per requirement column.
72 | test/aiss/gen_00632_test.dart | Gate suite | Dart source | 35 | GEN-00632 | 5 | Complete | The 5 gates for Step 35 (GEN-00632) - one assertion per requirement column.
73 | test/aiss/gen_00954_test.dart | Gate suite | Dart source | 22 | GEN-00954 | 6 | Complete | The 6 gates for Step 22 (GEN-00954) - one assertion per requirement column.
74 | test/aiss/gen_01275_test.dart | Gate suite | Dart source | 28 | GEN-01275 | 6 | Complete | The 6 gates for Step 28 (GEN-01275) - one assertion per requirement column.
75 | test/aiss/gen_01297_test.dart | Gate suite | Dart source | 27 | GEN-01297 | 6 | Complete | The 6 gates for Step 27 (GEN-01297) - one assertion per requirement column.
76 | test/aiss/gen_01363_test.dart | Gate suite | Dart source | 25 | GEN-01363 | 7 | Complete | The 7 gates for Step 25 (GEN-01363) - one assertion per requirement column.
77 | test/aiss/gen_01452_test.dart | Gate suite | Dart source | 29 | GEN-01452 | 7 | Complete | The 7 gates for Step 29 (GEN-01452) - one assertion per requirement column.
78 | test/aiss/gen_01848_test.dart | Gate suite | Dart source | 26 | GEN-01848 | 7 | Complete | The 7 gates for Step 26 (GEN-01848) - one assertion per requirement column.
79 | test/aiss/is02_csivw_005_test.dart | Gate suite | Dart source | 17 | IS02-CSIVW-005-AS01 | 6 | Complete | The 6 gates for Step 17 (IS02-CSIVW-005-AS01) - one assertion per requirement column.
80 | test/aiss/is12_csivw_011_test.dart | Gate suite | Dart source | 16 | IS12-CSIVW-011-AS01 | 7 | Complete | The 7 gates for Step 16 (IS12-CSIVW-011-AS01) - one assertion per requirement column.
81 | test/aiss/is38_sgtim_018_test.dart | Gate suite | Dart source | 31 | IS38-SGTIM-018-AS01 | 8 | Partial | The 8 gates for Step 31 (IS38-SGTIM-018-AS01) - one assertion per requirement column.
82 | test/aiss/mufce_028_test.dart | Gate suite | Dart source | 24 | MUFCE-028 | 7 | Complete | The 7 gates for Step 24 (MUFCE-028) - one assertion per requirement column.
83 | test/aiss/rcgla_001_test.dart | Gate suite | Dart source | 2 | RCGLA-001 | 6 | Complete | The 6 gates for Step 2 (RCGLA-001) - one assertion per requirement column.
84 | test/aiss/rcgla_012_test.dart | Gate suite | Dart source | 6 | RCGLA-012 | 7 | Partial | The 7 gates for Step 6 (RCGLA-012) - one assertion per requirement column.
85 | test/aiss/rcgla_018_test.dart | Gate suite | Dart source | 8 | RCGLA-018 | 6 | Complete | The 6 gates for Step 8 (RCGLA-018) - one assertion per requirement column.
86 | test/aiss/rcgla_032_test.dart | Gate suite | Dart source | 7 | RCGLA-032 | 7 | Complete | The 7 gates for Step 7 (RCGLA-032) - one assertion per requirement column.
87 | test/aiss/ref_197_test.dart | Gate suite | Dart source | 19 | REF-197 | 7 | Complete | The 7 gates for Step 19 (REF-197) - one assertion per requirement column.
88 | test/aiss/ref_377_test.dart | Gate suite | Dart source | 12 | REF-377 | 6 | Complete | The 6 gates for Step 12 (REF-377) - one assertion per requirement column.
89 | test/aiss/sstla_004_test.dart | Gate suite | Dart source | 5 | SSTLA-004 | 8 | Complete | The 8 gates for Step 5 (SSTLA-004) - one assertion per requirement column.
90 | test/aiss/ttmac_011_test.dart | Gate suite | Dart source | 10 | TTMAC-011 | 7 | Complete | The 7 gates for Step 10 (TTMAC-011) - one assertion per requirement column.
91 | test/aiss/ttmac_014_test.dart | Gate suite | Dart source | 14 | TTMAC-014 | 7 | Complete | The 7 gates for Step 14 (TTMAC-014) - one assertion per requirement column.
92 | test/aiss/ttmcs_001_test.dart | Gate suite | Dart source | 1 | TTMCS-001 | 7 | Complete | The 7 gates for Step 1 (TTMCS-001) - one assertion per requirement column.
93 | test/aiss/ttmcs_004_test.dart | Gate suite | Dart source | 3 | TTMCS-004 | 9 | Complete | The 9 gates for Step 3 (TTMCS-004) - one assertion per requirement column.
94 | test/aiss/ttmcs_005_test.dart | Gate suite | Dart source | 4 | TTMCS-005 | 8 | Complete | The 8 gates for Step 4 (TTMCS-005) - one assertion per requirement column.
95 | test/aiss/ufht_032_test.dart | Gate suite | Dart source | 34 | UFHT-032 | 7 | Complete | The 7 gates for Step 34 (UFHT-032) - one assertion per requirement column.
96 | test/guards/poka_yoke_no_hardcoded_values_test.dart | Mistake-proofing guard | Dart source | All (1-35) | shared infrastructure | 241 | n/a | Static scan over lib/: 6 mistake-proofing rules, 0 violations permitted.
97 | test/widget_test.dart | Test support | Dart source | All (1-35) | shared infrastructure | 241 | n/a | Smoke test that the app boots and the probe screen renders.
98 | tool/verify_aiss.sh | Verification tooling | Shell script | All (1-35) | shared infrastructure | 241 | n/a | The one command. 5 gate groups: format, analyze, poka-yoke, AISS gates, roll-up.
99 | web/index.html | Web host | HTML | 6 | RCGLA-012 | 7 | Partial | Web host page. Carries the viewport meta and the documented zoom-lock override.

## Documents
# | Document | Location | Format | What It Is | Audience
1 | AISS_Verification_Methodology.md | Others/Fredrick | Markdown | How every step is verified, why each gate exists, and Appendix A: the full 142-gate register. | Engineering + audit
2 | AISS_Verification_Evidence_Log.xlsx | Others/Fredrick | Excel | The gate register as a filterable sheet, plus per-step metric bands and the contrast audit. | Engineering + audit
3 | UDF_Implementation_Summary_Steps_1_to_20.md | Others/Fredrick | Markdown | Executive roll-up: what was built, metric results against the sheet bands, the decisions needed. | Leadership
4 | Output_Artefact_Index.xlsx | Others/Fredrick | Excel | This file. Every artefact mapped to the step that produced it. | Everyone
5 | step_summaries/Step_01..Step_35.md | Others/Fredrick | Markdown x35 | One engineering summary per atomic step: requirement-to-gate mapping and metric result. | Engineering
6 | Steps_21_to_35_Implementation_Order.xlsx | Others/Fredrick | Excel | The dependency-free build order for Steps 21-35, all 49 original columns retained. | Planning
7 | First_10_Steps_Implementation_Order.xlsx | Others/Fredrick | Excel | Dependency-free build order for Steps 1-10, all 49 original columns retained. | Planning
8 | Steps_11_to_20_Implementation_Order.xlsx | Others/Fredrick | Excel | The same for Steps 11-20, plus a reference tab for the completed 1-10. | Planning
9 | README.md | habot-mobile | Markdown | Codebase README: the five machine-enforced design-system rules and how to run everything. | Engineering
10 | tokens.json | udf_setup/lib/design_system/tokens | JSON | Source of truth for every design token. PROVISIONAL pending Brand sign-off. | Design + engineering
11 | device_matrix.json | udf_setup/lib/design_system/tokens | JSON | The 9-device matrix and the decision record resolving the gutter contradiction. | Design + engineering
12 | build/aiss/evidence.json | udf_setup (generated) | JSON | Written by ./tool/verify_aiss.sh on every run. Machine-readable gate outcomes. | CI