## Read Me
Steps 21-35 - Dependency-Free Build Order
Source | My stepsFN06082026.xlsx -> "Fredrick" tab (1,314 steps assigned to you)
Selection rule | Only steps where Dependency Count = 0 and Dependency (Atomic Step Serial No) = "No Dependency",
AND not already implemented in Steps 1-20. Verified row by row - all 15 confirmed zero-dependency.
Pool | 682 of your 1,314 steps have zero dependencies. 20 are done, leaving 662. Of those, 411 are
front-end steps whose output columns are not contaminated by backend content. These 15 come from there.
Track chosen | Surfaces & feedback - the "response" half of the UI. Steps 1-10 gave you the frame
(tokens, grid, scaffold, header, touch targets); Steps 11-20 gave you input (masking, validation,
errors, wizard). This batch gives you what the app shows BACK: sheets, snackbars, badges,
progress, empty states, cards, transitions, lists and search.
Ordering rule | Foundation-first. surface primitives -> surface consumer -> feedback surfaces -> status ->
content surfaces -> motion -> list behaviour -> list engine -> discovery -> telemetry.
No step here depends on any other, so you can start any of them today. The order means no rework:
each one consumes the artefact the previous one produced.
Closes open work | Steps 34 (UFHT-032) and 35 (GEN-00632) supply the hesitation and correction telemetry that
TTMAC-014 (Step 14) is currently Partial for. TTMAC-014 names UFHT-032 explicitly.
Step 25 (GEN-01363) is the snackbar step that could NOT be included in Steps 11-20, because every
snackbar candidate then had contaminated columns. This one is clean.
DATA QUALITY FLAGS | Two selected rows carry a contaminated Expected Output. They are still the right steps - the
Setup Step, Description, Substeps and Metric are all coherent - but do not gate against these two
Expected Output cells:
S.No 1786 MUFCE-028 long-press modal sheets -> Expected Output = "Asset Loading Optimization Plan"
S.No 4723 UFHT-032 hesitation tracker -> Expected Output = "Historical Audit Report SQL";
Completion = "Row_Level_Audit_Coverage == 100%"; the pre-step Decision asks
about primary keys in caching tables. The Description ("attach focus event
listeners to every input field") and the Metric are the usable requirement.
Three more have a Metric Name that does not match their action. Gate the action, not the metric:
S.No 9530 empty state container -> Metric = "Activity Log Data Completeness"
S.No 10080 progress indicators -> Metric = "Automated PR Rejection Rate for Non-Compliance"
S.No 9684 card UI chassis -> Metric = "Real-Time Availability Badge Accuracy"
All five are worth correcting at source in the master sheet.
ROW QUALITY | Four of the 15 are richly specified in the way Steps 1-20 were - full substeps, a pre-step
decision, a poka-yoke rule and distinct completion measures: Steps 24 (MUFCE-028), 31
(IS38-SGTIM-018), 32 (CPNCA-006) and 33 (ANSA-006). The eleven GEN-* rows share a boilerplate
Expected Output ("Fully configured and validated implementation of...") and Completion Measure
("100% CI/CD pass rate"). For those, the gates will be derived from the Setup Step, the
Description and the Metric Name, which are specific. This is stated up front so the evidence log
does not overclaim.
Next candidates | Rich rows that fit a later batch rather than this track: S.No 389 (swipeable ENUM chip arrays),
3172 (expiry timeline tracker), 3084 (binary checklist steppers), 2039 (responsive preference
panel), 3161 / 13776 (split-screen layout blueprints), 10839 (WCAG 2.2 AA + screen reader audit).
Columns | All 49 original columns preserved, in original order, with original values (verified cell-for-cell).
Four columns ADDED (shaded pale yellow): Implementation Order, Build Layer,
Why This Position In The Sequence, and Blocks (Steps That Need This).
Total effort | Approximately 8 working days of engineering time across the 15 steps.

## Build Sequence Summary
# | Build Layer | Global Ref ID | Atomic Step Ref ID | Setup Step (Action) | Est. Time | Dependency Count | Original S. No | Why This Position In The Sequence
21 | 21 - Surface Primitive | GEN-00055 | GEN-00055 | Build the BottomSheet atomic component using MD3 design tokens. | 4 Hours | 0 | 8298 | The container every other surface in this batch sits inside. Builds the BottomSheet as an atomic component from the MD3 tokens you already shipped in Step 2, so the sheet inherits shape, elevation and colour rather than declaring its own. Nothing here has a software prerequisite - it is the first thing to build.
22 | 22 - Surface Primitive | GEN-00954 | GEN-00954 | Standardize Material Design 3 (MD3) Bottom-Sheet UI for Mobile Complex Action Flows | 4 Hours | 0 | 9189 | Standardises the sheet built in Step 21: 32% opacity black backdrop scrim, and one set of rules for every complex action flow. Separated from Step 21 because the scrim is a contrast-sensitive value that has to be audited against the light and dark schemes from Steps 3-4, not just declared.
23 | 23 - Surface Primitive | GEN-00235 | GEN-00235 | Set the default snapping point to 60% viewport height for optimal thumb interaction. | 4 Hours | 0 | 8474 | Fixes the default snapping point at 60% viewport height. Comes third because a snap point is meaningless until the sheet and its scrim exist, and because it must be validated across the 9-device matrix you recorded in Step 5 rather than on one screen size.
24 | 24 - Surface Consumer | MUFCE-028 | MUFCE-028-A01 | Mandatory removal of all mouse hover tooltips and replacement with touch long-press modal sheets. | 2 Days | 0 | 1786 | The first real consumer of the sheet: strips every .onHover tooltip from the codebase and routes rich metadata to a long-press bottom drawer instead. Depends on Steps 21-23 existing, and on the long-press behaviour already built into HabotTouchTarget in Step 10. Doing it before the sheet is complete means building the drawer twice.
25 | 25 - Feedback Surface | GEN-01363 | GEN-01363 | Bind the client UI error boundaries to trigger M3 error Snackbars upon caught exceptions. | 4 Hours | 0 | 9596 | Binds the error boundary you shipped in Step 19 to M3 error Snackbars, so a caught exception surfaces as a scrubbed, plain-language message instead of a stack trace. This is the snackbar step that could not be included in Steps 11-20 because every snackbar candidate then had contaminated columns - this row is clean.
26 | 26 - Feedback Surface | GEN-01848 | GEN-01848 | Implement visual progress indicators to show user advancement. | 4 Hours | 0 | 10080 | Visual progress indicators, consuming the motion tokens from Steps 11-12 and the reduced-motion policy with them. Placed after the snackbar so the indeterminate and error paths of the same operation are designed together rather than in separate sittings.
27 | 27 - Feedback Surface | GEN-01297 | GEN-01297 | Implement an empty state container with custom illustrations to display when search queries return zero logs. | 4 Hours | 0 | 9530 | The empty state container. Needs the card chassis, the sheet and the progress indicator to already exist, because an empty state is defined by what is absent from a populated surface - build it earlier and you are guessing at the layout it has to replace.
28 | 28 - Status Surface | GEN-01275 | GEN-01275 | Embed M3 status Badges to mark completed and active milestone nodes. | 4 Hours | 0 | 9508 | M3 status Badges for completed and active nodes. Follows the feedback surfaces because a badge is the persistent form of the same status a snackbar announces transiently, and both must draw from one status vocabulary rather than two.
29 | 29 - Content Surface | GEN-01452 | GEN-01452 | Construct the card UI chassis using M3 Outlined or Elevated Card specifications. | 4 Hours | 0 | 9684 | The card chassis - M3 Outlined and Elevated variants built on the elevation ladder from Step 4 and the shape tokens from Step 2. Every list, empty state and badge host in the rest of this batch renders inside a card, so the chassis has to be settled before they are.
30 | 30 - Motion | GEN-00201 | GEN-00201 | Use Material Design 3 shared axis transitions for mobile view state changes. | 4 Hours | 0 | 8441 | MD3 shared-axis transitions for view state changes. Extends the motion token layer from Steps 11-12 with the transition patterns the new surfaces need, and lands before the list work so list navigation animates through the shared axis instead of a bespoke curve.
31 | 31 - List Behaviour | IS38-SGTIM-018-AS01 | IS38-SGTIM-018-AS01-A01 | Apply M3 Overscroll Stretch on MTOI Lists | 1h | 0 | 1555 | M3 overscroll stretch on lists. A one-hour step that establishes the physical feel of a list boundary before the virtualisation engine changes how those boundaries are computed. Cheap to do now, awkward to retrofit once chunking is in place.
32 | 32 - List Engine | CPNCA-006 | CPNCA-006-A01 | Build a standardized list virtualization and dynamic data chunking component for data tables Operationalizing System Architecture Design]. | 12 Hours | 0 | 2468 | List virtualisation with dynamic data chunking - viewport boundary calculation, batched fetches, low element count at 10,000 rows. The largest step in the batch at 12 hours. It comes after the card chassis and overscroll because it renders those cards and must preserve that scroll feel under recycling.
33 | 33 - Discovery | ANSA-006 | ANSA-006-A01 | Implementation Step 15: Build an expandable search text line inside primary system headers. (ANSA-006) | 5 Hours | 0 | 3194 | The expandable search line inside the contextual header from Step 9, with keypress debounce, a results dropdown and local keyword history. Deliberately last of the UI steps: it consumes the header, the card chassis, the virtualised list, the empty state for zero results, and the progress indicator for the in-flight query.
34 | 34 - Telemetry | UFHT-032 | UFHT-032 | UI Hesitation Tracker Engine Setup | 2H | 0 | 4723 | The UI Hesitation Tracker engine - focus event listeners on every input field. Named directly in TTMAC-014 (Step 14) as the source of the double-tap correction rate, which is one of the three gates currently deferred. Placed here because it instruments the forms from Steps 15-18 and the surfaces from Steps 21-33 in one pass.
35 | 35 - Telemetry | GEN-00632 | GEN-00632 | Deploy Mobile UX Friction Logs (Hesitation Tracking) | 4 Hours | 0 | 8870 | The FrictionTracker widget wrapper that consumes the listeners from Step 34 and turns them into friction logs. Together these two close the telemetry half of the TTMAC-014 deferral and turn Step 14 from Partial to Complete. Last, because it can only wrap components that already exist.

## Steps 1-20 (already done)
# | Global Ref ID | Atomic Step Ref ID | Setup Step (Action) | Original S. No | Status
1 | TTMCS-001 | TTMCS-001-A01 | Install and configure the verified Material 3 layout component framework within frontend client packages. | 1797 | Implemented - Complete (all gates active and passing)
2 | RCGLA-001 | RCGLA-001-A01 | Build global corporate style token variables inside the mobile client framework. | 3227 | Implemented - Complete (all gates active and passing)
3 | TTMCS-004 | TTMCS-004-A01 | TTMCS-004 — Configure Atomic Light/Dark Adaptation Tokens | 1654 | Implemented - Complete (all gates active and passing)
4 | TTMCS-005 | TTMCS-005-A01 | TTMCS-005 — Mobile Dark Mode Contrast Enforcement | 3139 | Implemented - Complete (all gates active and passing)
5 | SSTLA-004 | SSTLA-004-A01 | Define the exact base breakpoint, column count, fluid margin, and gutter widths for the core mobile experience before scaling upward to tablet or desktop views. | 169 | Implemented - Complete, awaiting a human reviewer quality score
6 | RCGLA-012 | RCGLA-012-A01 | RCGLA-012 - Initialize Atomic Grid System & Mobile Viewport Constraints | 345 | Implemented - PARTIAL (2 gates deferred: zoom lock, CLS)
7 | RCGLA-032 | RCGLA-032-A01 | RCGLA-032 - Configure the Material Design 3 (MD3) adaptive 4-column fluid layout token engine for mobile screens. | 3051 | Implemented - Complete (all gates active and passing)
8 | RCGLA-018 | RCGLA-018-A01 | RCGLA-018 - Universal Master Layout Architecture for React Components | 356 | Implemented - Complete (all gates active and passing)
9 | ANSA-012 | ANSA-012-A01 | Establish Contextual Navigation Header Framework. | 4 | Implemented - Complete (all gates active and passing)
10 | TTMAC-011 | TTMAC-011-A01 | Touch-Target Optimization Framework Setup (48×48 dp Minimum Interaction Nodes). | 3095 | Implemented - Complete (all gates active and passing)
11 | BPTR-0422 | BPTR-0422-A01 | Define Passive Failure Motion Curves. | 257 | Implemented - Complete (all gates active and passing)
12 | REF-377 | REF-377-A01 | Set Progressive Stepper Transitions. | 400 | Implemented - Complete (all gates active and passing)
13 | BPTR-0128 | BPTR-0128-A01 | Establish Global Atomic Byt Micro-Interaction Boundaries | 1566 | Implemented - Complete (all gates active and passing)
14 | TTMAC-014 | TTMAC-014-A01 | TTMAC-014 - Interactive Touch Target Standardization Engine Setup | 2028 | Implemented - PARTIAL (1 gate deferred: double-tap rate - closed by Steps 34-35)
15 | CSIVW-001 | CSIVW-001-A01 | Implement strict client-side Input Masking on all template text area entry portals. | 3062 | Implemented - Complete (all gates active and passing)
16 | IS12-CSIVW-011-AS01 | IS12-CSIVW-011-AS01-A01 | Setup character formatting filters across text entry boxes. | 3205 | Implemented - Complete (all gates active and passing)
17 | IS02-CSIVW-005-AS01 | IS02-CSIVW-005-AS01-A01 | Program dynamic inline error layouts to activate when input fields fail validation checks. | 2490 | Implemented - Complete (all gates active and passing)
18 | BPTR-0160 | BPTR-0160-A01 | Code and isolate mobile compound fields into distinct, standalone UI components featuring strict 48x48dp touch targets. | 3073 | Implemented - Complete (all gates active and passing)
19 | REF-197 | REF-197-A01 | Developing the Safe Error-Handling UI Rollback Handler | 3238 | Implemented - Complete (all gates active and passing)
20 | FIEVR-033 | FIEVR-033-A01 | FIEVR-033 - Build Multi-Step Guided Carousel Layout Stepper | 3128 | Implemented - Complete (all gates active and passing)

## Steps 21-35 - Build Order
Implementation Order | Build Layer | S. No | Global Reference ID | Atomic Steps Reference ID | Setup Step (Action) | Setup Step Description | 4 Substeps | Decision Group | Decision to be Made Before Setup Step | Decision Category | Why This Matters | Mobile App First Implication | UX Translation | Data Requirement | User Interaction / Flow Impact | Dashboard / Interface Implication | What Standardized Must Be Done | Atomic Reusability | Common Library to Store | GCP / BigQuery Alignment | Sequence Order | Estimated Time Required | Expected Output | Completion Measures | Dependencies | Mobile-First & Responsive UX Google Material Design Decision | Mobile-First & Responsive UI Google Material Design Decision | Mobile-First & Responsive UX Google Material Design Implementation | Mobile-First & Responsive UI Google Material Design Implementation | Domain Expertise Needed | Mistake-Proofing (Poka-Yoke) | Self-Chasing | What Creates Vitality & Prosperity For Us | What Creates Vitality & Prosperity For the Customer | Responsive UX/UI Design | Vitality & Prosperity (VAP) | Setup Step (Action).1 | Atomic Step | Metric Name | Floor Boundary | Optimal Target | Ceiling Boundary | Best Qualitative Output | Best Qualitative/Quantitative Output Type | Assigned Team Member | Data Collected by System | Required Data / Configuration / Implementation Fields (from AL-AQ Analysis) | Dependency Count | Dependency (Atomic Step Serial No) | Output format | Why This Position In The Sequence | Blocks (Steps That Need This)
21 | 21 - Surface Primitive | 8298 | GEN-00055 | GEN-00055 | Build the BottomSheet atomic component using MD3 design tokens. | Build the BottomSheet atomic component using MD3 design tokens. | 1. Plan and scope this step. 2. Implement the core configuration. 3. Test and validate in staging. 4. Document and commit to runbook. | Architecture & Implementation Governance | What exact configuration and validation approach should be applied for: Build the BottomSheet atomic component using MD3 design tokens.? | UX Flow / BigQuery | Build the BottomSheet atomic component using MD3 design tokens. is a critical implementation step. Without it, downstream steps lack the required baseline configuration. | Ensures sub-100ms API response latencies on mobile clients via optimized backend configuration. | Single-column mobile layout with M3 status cards displaying step completion state. | Data/artifacts to prepare: Build the BottomSheet atomic component using MD3 design tokens.. Metric config: 'Component Delivery Completeness' (floor threshold: Component functionally complete, minor polish outstanding). Reference standard/spec to configure against: ISO/IEC 25010 Functional Suitability. Output field to capture: Complete/Partial/Not Complete. | Users interact with this step exclusively through the mobile engineering console. Read-only M3 KPI cards with deep-link drill-down. | Engineering console dashboard displays step health via M3 Elevated Card with inline status chip. | English Code (EC) blueprint required before any code is written. All functions must have single-verb EC headers. | Core pattern for this step stored as a reusable module in the shared library. | @habot/shared-library | All step execution events stream to BigQuery partitioned by event_date, clustered by trace_id. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: N/A ¦ Row: 8298.0 | 4 Hours | Fully configured and validated implementation of: Build the BottomSheet atomic component using MD3 design tokens.. | 100% CI/CD pass rate. All validation checks passing. Documentation committed to runbook. | Dependent on prior foundational steps. | M3 responsive layout: single-column on mobile (<600dp), multi-column on desktop (≥840dp). | M3 Elevated Cards Level 2 (3dp). M3 Status Chips for health indicators. 48x48dp touch targets. | Background polling refreshes data every 30 seconds. Pull-to-refresh triggers manual sync. | M3 Bottom Sheet for configuration inputs. M3 Snackbar for confirmations. Material You dynamic color. | Mobile Engineering, GCP Architecture, UX/UI Design (MD3), DCDF Engine Architecture. | CI/CD pipeline physically blocks deployment if any gate for this step fails. | Automated Liveness Handshake monitors this step every 30 seconds and triggers rollback on failure. | Eliminates manual overhead, reduces operational cost, and protects revenue pipelines. | Engineers and end-users experience reliable, uninterrupted platform performance. | M3 responsive single-column on mobile, multi-panel on tablet/desktop. 48x48dp touch targets. | Us: Eliminates manual overhead and reduces operational cost. ¦ Customer: Reliable, uninterrupted platform performance. | Build the BottomSheet atomic component using MD3 design tokens. | Build the BottomSheet atomic component using MD3 design tokens. | Component Delivery Completeness | Component functionally complete, minor polish outstanding | 100% functional + documented (Storybook/README) delivery | 1.0 | Complete/Partial/Not Complete | ISO/IEC 25010 Functional Suitability | Fredrick | Build the BottomSheet atomic component using MD3 design tokens.; Completion Status ('Complete/Partial/Not Complete'); Action/Event Timestamp; User/Session ID | Data Required: Component Delivery Completeness ¦¦ Configuration Data: Floor=Component functionally complete, minor polish outstanding ¦ Optimal=100% functional + documented (Storybook/README) delivery ¦ Ceiling=1 ¦¦ Implementation Data: Output field='Complete/Partial/Not Complete'; Standard/Reference='ISO/IEC 25010 Functional Suitability' | 0 | No Dependency |  | The container every other surface in this batch sits inside. Builds the BottomSheet as an atomic component from the MD3 tokens you already shipped in Step 2, so the sheet inherits shape, elevation and colour rather than declaring its own. Nothing here has a software prerequisite - it is the first thing to build. | 22,23,24,27,33
22 | 22 - Surface Primitive | 9189 | GEN-00954 | GEN-00954 | Standardize Material Design 3 (MD3) Bottom-Sheet UI for Mobile Complex Action Flows | Configure backdrop scrim color to 32% opacity black. | 1. Plan and scope this step. 2. Implement the core configuration. 3. Test and validate in staging. 4. Document and commit to runbook. | Architecture & Implementation Governance | What exact configuration and validation approach should be applied for: Configure backdrop scrim color to 32% opacity black.? | UX Flow / BigQuery | Configure backdrop scrim color to 32% opacity black. is a critical implementation step. Without it, downstream steps lack the required baseline configuration. | Ensures sub-100ms API response latencies on mobile clients via optimized backend configuration. | Single-column mobile layout with M3 status cards displaying step completion state. | Data/artifacts to prepare: Configure backdrop scrim color to 32% opacity black.. Metric config: 'Scrim Opacity Compliance' (floor threshold: $32\%$). Reference standard/spec to configure against: Google Material Design 3 Color Tokens. Output field to capture: Pass / Fail. | Users interact with this step exclusively through the mobile engineering console. Read-only M3 KPI cards with deep-link drill-down. | Engineering console dashboard displays step health via M3 Elevated Card with inline status chip. | English Code (EC) blueprint required before any code is written. All functions must have single-verb EC headers. | Core pattern for this step stored as a reusable module in the shared library. | @habot/shared-library | All step execution events stream to BigQuery partitioned by event_date, clustered by trace_id. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: N/A ¦ Row: 9189.0 | 4 Hours | Fully configured and validated implementation of: Configure backdrop scrim color to 32% opacity black.. | 100% CI/CD pass rate. All validation checks passing. Documentation committed to runbook. | Dependent on prior foundational steps. | M3 responsive layout: single-column on mobile (<600dp), multi-column on desktop (≥840dp). | M3 Elevated Cards Level 2 (3dp). M3 Status Chips for health indicators. 48x48dp touch targets. | Background polling refreshes data every 30 seconds. Pull-to-refresh triggers manual sync. | M3 Bottom Sheet for configuration inputs. M3 Snackbar for confirmations. Material You dynamic color. | Mobile Engineering, GCP Architecture, UX/UI Design (MD3), DCDF Engine Architecture. | CI/CD pipeline physically blocks deployment if any gate for this step fails. | Automated Liveness Handshake monitors this step every 30 seconds and triggers rollback on failure. | Eliminates manual overhead, reduces operational cost, and protects revenue pipelines. | Engineers and end-users experience reliable, uninterrupted platform performance. | M3 responsive single-column on mobile, multi-panel on tablet/desktop. 48x48dp touch targets. | Us: Eliminates manual overhead and reduces operational cost. ¦ Customer: Reliable, uninterrupted platform performance. | Standardize Material Design 3 (MD3) Bottom-Sheet UI for Mobile Complex Action Flows | Configure backdrop scrim color to 32% opacity black. | Scrim Opacity Compliance | $32\%$ | $32\%$ | $32\%$ | Pass / Fail | Google Material Design 3 Color Tokens | Fredrick | Configure backdrop scrim color to 32% opacity black.; Completion Status ('Pass / Fail'); Action/Event Timestamp; User/Session ID | Data Required: Scrim Opacity Compliance ¦¦ Configuration Data: Floor=$32\%$ ¦ Optimal=$32\%$ ¦ Ceiling=$32\%$ ¦¦ Implementation Data: Output field='Pass / Fail'; Standard/Reference='Google Material Design 3 Color Tokens' | 0 | No Dependency |  | Standardises the sheet built in Step 21: 32% opacity black backdrop scrim, and one set of rules for every complex action flow. Separated from Step 21 because the scrim is a contrast-sensitive value that has to be audited against the light and dark schemes from Steps 3-4, not just declared. | 23,24,27
23 | 23 - Surface Primitive | 8474 | GEN-00235 | GEN-00235 | Set the default snapping point to 60% viewport height for optimal thumb interaction. | Set the default snapping point to 60% viewport height for optimal thumb interaction. | 1. Plan and scope this step. 2. Implement the core configuration. 3. Test and validate in staging. 4. Document and commit to runbook. | Architecture & Implementation Governance | What exact configuration and validation approach should be applied for: Set the default snapping point to 60% viewport height for optimal thumb interact? | UX Flow / BigQuery | Set the default snapping point to 60% viewport height for optimal thumb interaction. is a critical implementation step. Without it, downstream steps lack the required baseline configuration. | Ensures sub-100ms API response latencies on mobile clients via optimized backend configuration. | Single-column mobile layout with M3 status cards displaying step completion state. | Data/artifacts to prepare: Set the default snapping point to 60% viewport height for…. Metric config: 'Cross-Viewport Rendering Consistency' (floor threshold: Zero regressions on primary breakpoints (360/390/412px)). Reference standard/spec to configure against: W3C Responsive Images/Web Design guidelines; BrowserStack device-matrix best practice. Output field to capture: Pass/Fail. | Users interact with this step exclusively through the mobile engineering console. Read-only M3 KPI cards with deep-link drill-down. | Engineering console dashboard displays step health via M3 Elevated Card with inline status chip. | English Code (EC) blueprint required before any code is written. All functions must have single-verb EC headers. | Core pattern for this step stored as a reusable module in the shared library. | @habot/shared-library | All step execution events stream to BigQuery partitioned by event_date, clustered by trace_id. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: N/A ¦ Row: 8474.0 | 4 Hours | Fully configured and validated implementation of: Set the default snapping point to 60% viewport height for optimal thumb interact. | 100% CI/CD pass rate. All validation checks passing. Documentation committed to runbook. | Dependent on prior foundational steps. | M3 responsive layout: single-column on mobile (<600dp), multi-column on desktop (≥840dp). | M3 Elevated Cards Level 2 (3dp). M3 Status Chips for health indicators. 48x48dp touch targets. | Background polling refreshes data every 30 seconds. Pull-to-refresh triggers manual sync. | M3 Bottom Sheet for configuration inputs. M3 Snackbar for confirmations. Material You dynamic color. | Mobile Engineering, GCP Architecture, UX/UI Design (MD3), DCDF Engine Architecture. | CI/CD pipeline physically blocks deployment if any gate for this step fails. | Automated Liveness Handshake monitors this step every 30 seconds and triggers rollback on failure. | Eliminates manual overhead, reduces operational cost, and protects revenue pipelines. | Engineers and end-users experience reliable, uninterrupted platform performance. | M3 responsive single-column on mobile, multi-panel on tablet/desktop. 48x48dp touch targets. | Us: Eliminates manual overhead and reduces operational cost. ¦ Customer: Reliable, uninterrupted platform performance. | Set the default snapping point to 60% viewport height for optimal thumb interaction. | Set the default snapping point to 60% viewport height for optimal thumb interaction. | Cross-Viewport Rendering Consistency | Zero regressions on primary breakpoints (360/390/412px) | Zero regressions across full tested device matrix | N/A (zero-tolerance metric, no upper bound) | Pass/Fail | W3C Responsive Images/Web Design guidelines; BrowserStack device-matrix best practice | Fredrick | Set the default snapping point to 60% viewport height for…; Completion Status ('Pass/Fail'); Action/Event Timestamp; User/Session ID | Data Required: Cross-Viewport Rendering Consistency ¦¦ Configuration Data: Floor=Zero regressions on primary breakpoints (360/390/412px) ¦ Optimal=Zero regressions across full tested device matrix ¦ Ceiling=N/A (zero-tolerance metric, no upper bound) ¦¦ Implementation Data: Output field='Pass/Fail'; Standard/Reference='W3C Responsive Images/Web Design guidelines; BrowserStack device-matrix best practice' | 0 | No Dependency |  | Fixes the default snapping point at 60% viewport height. Comes third because a snap point is meaningless until the sheet and its scrim exist, and because it must be validated across the 9-device matrix you recorded in Step 5 rather than on one screen size. | 24,27
24 | 24 - Surface Consumer | 1786 | MUFCE-028 | MUFCE-028-A01 | Mandatory removal of all mouse hover tooltips and replacement with touch long-press modal sheets. | Open the UI component library templates containing interactive metadata elements. | Strip all .onHover logic actions from mobile codebase templates. Bind formula lookup scripts to explicit touch-and-hold gestures. Route rich metadata descriptions to smooth bottom drawer overlays. Set up an alternative quick-tap option icon next to dynamic labels. | Layout Engine |  |  | Keeps background download latency minimal, avoiding form rendering stalls on unstable mobile links. | Restricts heavy image loading configurations, optimizing file transit based on connection health. | Placeholders load fast, rendering sharper asset details as network signals improve. | Atomic-level data fields: Library Name; Library Version; Component Count; Installation Status; Dependency List; Library Location Path ¦¦ Mobile UX/UI design config required: Manage data delivery expectations elegantly across network drops. ¦ Use muted background surfaces for loading placeholders. ¦ Apply soft pulse animations to loading shapes to show app responsiveness. ¦ Lock placeholders tightly to forthcoming asset dimensions. ¦¦ Domain expertise/sign-off required: Network Telemetry / Media Stream Compression. | Operators experience continuous app performance without waiting for heavy file drops. | Adaptive data containers that load contents fluidly based on system telemetry. | Interface performance budget rules configuration. | NetworkAdaptiveImageLoader wrapper component. | UI Component Library. | Adjusts network loading volume based on live hardware environment changes. | Level 3 ¦ Phase: SETUP-03 ¦ Atomic Step: 1.0 ¦ Row: 1786.0 | 2 Days | Asset Loading Optimization Plan. | Interface payloads scale down properly during limited-bandwidth test cycles. | HC-DE-0304. Mobile-First & Responsive UX Google material design decision: Manage data delivery expectations elegantly across network drops. Mobile-First & Responsive UI Google material design decision: Use muted background surfaces for loading placeholders. Mobile-First & Responsive UX Google material design implementation: Apply soft pulse animations to loading shapes to show app responsiveness. Mobile-First & Responsive UI Google material design implementation: Lock placeholders tightly to forthcoming asset dimensions. Domain expertise needed to implement this step: Network Telemetry / Media Stream Compression. 1. Mistake-Proofing (Poka-Yoke): Pre-processing rules compress large files automatically, shielding mobile network budgets. 2. Self-Chasing: Failed image transactions trigger clean retry icons, guiding recovery steps cleanly. 3. Vitality & Prosperity (VAP): What creates vitality and prosperity for us: Maintains interface agility across remote-first tracking paths. What creates vitality and prosperity for the customer: Provides a reliable, consistent, and uninterrupted app experience. | Manage data delivery expectations elegantly across network drops. | Use muted background surfaces for loading placeholders. | Apply soft pulse animations to loading shapes to show app responsiveness. | Lock placeholders tightly to forthcoming asset dimensions. | Network Telemetry / Media Stream Compression. |  |  | Maintains interface agility across remote-first tracking paths. | Provides a reliable, consistent, and uninterrupted app experience. |  |  | Mandatory removal of all mouse hover tooltips and replacement with touch long-press modal sheets. | Open the UI component library templates containing interactive metadata elements. | Environment / Asset Access Readiness | Located on first attempt | Path version-controlled & documented | N/A (one-time setup) | Complete / Partial / Not Complete | Source files and directories referenced should be under version control and discoverable without tribal knowledge. | Fredrick | Library Name; Library Version; Component Count; Installation Status; Dependency List; Library Location Path; Completion Status ('Complete / Partial / Not Complete'); Action/Event Timestamp; User/Session ID | Data Required: Environment / Asset Access Readiness ¦¦ Configuration Data: Floor=Located on first attempt ¦ Optimal=Path version-controlled & documented ¦ Ceiling=N/A (one-time setup) ¦¦ Implementation Data: Output field='Complete / Partial / Not Complete'; Standard/Reference='Source files and directories referenced should be under version control and discoverable without tribal knowledge.' | 0 | No Dependency |  | The first real consumer of the sheet: strips every .onHover tooltip from the codebase and routes rich metadata to a long-press bottom drawer instead. Depends on Steps 21-23 existing, and on the long-press behaviour already built into HabotTouchTarget in Step 10. Doing it before the sheet is complete means building the drawer twice. | -
25 | 25 - Feedback Surface | 9596 | GEN-01363 | GEN-01363 | Bind the client UI error boundaries to trigger M3 error Snackbars upon caught exceptions. | Bind the client UI error boundaries to trigger M3 error Snackbars upon caught exceptions. | 1. Plan and scope this step. 2. Implement the core configuration. 3. Test and validate in staging. 4. Document and commit to runbook. | Architecture & Implementation Governance | What exact configuration and validation approach should be applied for: Bind the client UI error boundaries to trigger M3 error Snackbars upon caught ex? | UX Flow / BigQuery | Bind the client UI error boundaries to trigger M3 error Snackbars upon caught exceptions. is a critical implementation step. Without it, downstream steps lack the required baseline configuration. | Ensures sub-100ms API response latencies on mobile clients via optimized backend configuration. | Single-column mobile layout with M3 status cards displaying step completion state. | Data/artifacts to prepare: Bind the client UI error boundaries to trigger M3 error…. Metric config: 'Crash-Free Session Rate' (floor threshold: 0.99). Reference standard/spec to configure against: Google Play / Firebase Crashlytics Vitals Benchmark. Output field to capture: Good/Average/Poor. | Users interact with this step exclusively through the mobile engineering console. Read-only M3 KPI cards with deep-link drill-down. | Engineering console dashboard displays step health via M3 Elevated Card with inline status chip. | English Code (EC) blueprint required before any code is written. All functions must have single-verb EC headers. | Core pattern for this step stored as a reusable module in the shared library. | @habot/shared-library | All step execution events stream to BigQuery partitioned by event_date, clustered by trace_id. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: N/A ¦ Row: 9596.0 | 4 Hours | Fully configured and validated implementation of: Bind the client UI error boundaries to trigger M3 error Snackbars upon caught ex. | 100% CI/CD pass rate. All validation checks passing. Documentation committed to runbook. | Dependent on prior foundational steps. | M3 responsive layout: single-column on mobile (<600dp), multi-column on desktop (≥840dp). | M3 Elevated Cards Level 2 (3dp). M3 Status Chips for health indicators. 48x48dp touch targets. | Background polling refreshes data every 30 seconds. Pull-to-refresh triggers manual sync. | M3 Bottom Sheet for configuration inputs. M3 Snackbar for confirmations. Material You dynamic color. | Mobile Engineering, GCP Architecture, UX/UI Design (MD3), DCDF Engine Architecture. | CI/CD pipeline physically blocks deployment if any gate for this step fails. | Automated Liveness Handshake monitors this step every 30 seconds and triggers rollback on failure. | Eliminates manual overhead, reduces operational cost, and protects revenue pipelines. | Engineers and end-users experience reliable, uninterrupted platform performance. | M3 responsive single-column on mobile, multi-panel on tablet/desktop. 48x48dp touch targets. | Us: Eliminates manual overhead and reduces operational cost. ¦ Customer: Reliable, uninterrupted platform performance. | Bind the client UI error boundaries to trigger M3 error Snackbars upon caught exceptions. | Bind the client UI error boundaries to trigger M3 error Snackbars upon caught exceptions. | Crash-Free Session Rate | 0.99 | 0.999 | 1.0 | Good/Average/Poor | Google Play / Firebase Crashlytics Vitals Benchmark | Fredrick | Bind the client UI error boundaries to trigger M3 error…; Completion Status ('Good/Average/Poor'); Action/Event Timestamp; User/Session ID | Data Required: Crash-Free Session Rate ¦¦ Configuration Data: Floor=0.99 ¦ Optimal=0.999 ¦ Ceiling=1 ¦¦ Implementation Data: Output field='Good/Average/Poor'; Standard/Reference='Google Play / Firebase Crashlytics Vitals Benchmark' | 0 | No Dependency |  | Binds the error boundary you shipped in Step 19 to M3 error Snackbars, so a caught exception surfaces as a scrubbed, plain-language message instead of a stack trace. This is the snackbar step that could not be included in Steps 11-20 because every snackbar candidate then had contaminated columns - this row is clean. | 26,27,35
26 | 26 - Feedback Surface | 10080 | GEN-01848 | GEN-01848 | Implement visual progress indicators to show user advancement. | Implement visual progress indicators to show user advancement. | 1. Plan and scope this step. 2. Implement the core configuration. 3. Test and validate in staging. 4. Document and commit to runbook. | Architecture & Implementation Governance | What exact configuration and validation approach should be applied for: Implement visual progress indicators to show user advancement.? | UX Flow / BigQuery | Implement visual progress indicators to show user advancement. is a critical implementation step. Without it, downstream steps lack the required baseline configuration. | Ensures sub-100ms API response latencies on mobile clients via optimized backend configuration. | Single-column mobile layout with M3 status cards displaying step completion state. | Data/artifacts to prepare: Implement visual progress indicators to show user advancement.. Metric config: 'Automated PR Rejection Rate for Non-Compliance (%)' (floor threshold: 95). Reference standard/spec to configure against: CI/CD Best Practices & GitHub Standards. Output field to capture: High/Medium/Low. | Users interact with this step exclusively through the mobile engineering console. Read-only M3 KPI cards with deep-link drill-down. | Engineering console dashboard displays step health via M3 Elevated Card with inline status chip. | English Code (EC) blueprint required before any code is written. All functions must have single-verb EC headers. | Core pattern for this step stored as a reusable module in the shared library. | @habot/shared-library | All step execution events stream to BigQuery partitioned by event_date, clustered by trace_id. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: N/A ¦ Row: 10080.0 | 4 Hours | Fully configured and validated implementation of: Implement visual progress indicators to show user advancement.. | 100% CI/CD pass rate. All validation checks passing. Documentation committed to runbook. | Dependent on prior foundational steps. | M3 responsive layout: single-column on mobile (<600dp), multi-column on desktop (≥840dp). | M3 Elevated Cards Level 2 (3dp). M3 Status Chips for health indicators. 48x48dp touch targets. | Background polling refreshes data every 30 seconds. Pull-to-refresh triggers manual sync. | M3 Bottom Sheet for configuration inputs. M3 Snackbar for confirmations. Material You dynamic color. | Mobile Engineering, GCP Architecture, UX/UI Design (MD3), DCDF Engine Architecture. | CI/CD pipeline physically blocks deployment if any gate for this step fails. | Automated Liveness Handshake monitors this step every 30 seconds and triggers rollback on failure. | Eliminates manual overhead, reduces operational cost, and protects revenue pipelines. | Engineers and end-users experience reliable, uninterrupted platform performance. | M3 responsive single-column on mobile, multi-panel on tablet/desktop. 48x48dp touch targets. | Us: Eliminates manual overhead and reduces operational cost. ¦ Customer: Reliable, uninterrupted platform performance. | Implement visual progress indicators to show user advancement. | Implement visual progress indicators to show user advancement. | Automated PR Rejection Rate for Non-Compliance (%) | 95.0 | 99.5 | 100.0 | High/Medium/Low | CI/CD Best Practices & GitHub Standards | Fredrick | Implement visual progress indicators to show user advancement.; Completion Status ('High/Medium/Low'); Action/Event Timestamp; User/Session ID | Data Required: Automated PR Rejection Rate for Non-Compliance (%) ¦¦ Configuration Data: Floor=95 ¦ Optimal=99.5 ¦ Ceiling=100 ¦¦ Implementation Data: Output field='High/Medium/Low'; Standard/Reference='CI/CD Best Practices & GitHub Standards' | 0 | No Dependency |  | Visual progress indicators, consuming the motion tokens from Steps 11-12 and the reduced-motion policy with them. Placed after the snackbar so the indeterminate and error paths of the same operation are designed together rather than in separate sittings. | 27,29,33
27 | 27 - Feedback Surface | 9530 | GEN-01297 | GEN-01297 | Implement an empty state container with custom illustrations to display when search queries return zero logs. | Implement an empty state container with custom illustrations to display when search queries return zero logs. | 1. Plan and scope this step. 2. Implement the core configuration. 3. Test and validate in staging. 4. Document and commit to runbook. | Architecture & Implementation Governance | What exact configuration and validation approach should be applied for: Implement an empty state container with custom illustrations to display when sea? | UX Flow / BigQuery | Implement an empty state container with custom illustrations to display when search queries return z is a critical implementation step. Without it, downstream steps lack the required baseline configuration. | Ensures sub-100ms API response latencies on mobile clients via optimized backend configuration. | Single-column mobile layout with M3 status cards displaying step completion state. | Data/artifacts to prepare: Implement an empty state container with custom illustrations to display…. Metric config: 'Activity Log Data Completeness' (floor threshold: 0.95). Reference standard/spec to configure against: ISO/IEC 25012 Data Quality Model. Output field to capture: Complete/Partial/Not Complete. | Users interact with this step exclusively through the mobile engineering console. Read-only M3 KPI cards with deep-link drill-down. | Engineering console dashboard displays step health via M3 Elevated Card with inline status chip. | English Code (EC) blueprint required before any code is written. All functions must have single-verb EC headers. | Core pattern for this step stored as a reusable module in the shared library. | @habot/shared-library | All step execution events stream to BigQuery partitioned by event_date, clustered by trace_id. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: N/A ¦ Row: 9530.0 | 4 Hours | Fully configured and validated implementation of: Implement an empty state container with custom illustrations to display when sea. | 100% CI/CD pass rate. All validation checks passing. Documentation committed to runbook. | Dependent on prior foundational steps. | M3 responsive layout: single-column on mobile (<600dp), multi-column on desktop (≥840dp). | M3 Elevated Cards Level 2 (3dp). M3 Status Chips for health indicators. 48x48dp touch targets. | Background polling refreshes data every 30 seconds. Pull-to-refresh triggers manual sync. | M3 Bottom Sheet for configuration inputs. M3 Snackbar for confirmations. Material You dynamic color. | Mobile Engineering, GCP Architecture, UX/UI Design (MD3), DCDF Engine Architecture. | CI/CD pipeline physically blocks deployment if any gate for this step fails. | Automated Liveness Handshake monitors this step every 30 seconds and triggers rollback on failure. | Eliminates manual overhead, reduces operational cost, and protects revenue pipelines. | Engineers and end-users experience reliable, uninterrupted platform performance. | M3 responsive single-column on mobile, multi-panel on tablet/desktop. 48x48dp touch targets. | Us: Eliminates manual overhead and reduces operational cost. ¦ Customer: Reliable, uninterrupted platform performance. | Implement an empty state container with custom illustrations to display when search queries return z | Implement an empty state container with custom illustrations to display when search queries return zero logs. | Activity Log Data Completeness | 0.95 | 0.999 | 1.0 | Complete/Partial/Not Complete | ISO/IEC 25012 Data Quality Model | Fredrick | Implement an empty state container with custom illustrations to display…; Completion Status ('Complete/Partial/Not Complete'); Action/Event Timestamp; User/Session ID | Data Required: Activity Log Data Completeness ¦¦ Configuration Data: Floor=0.95 ¦ Optimal=0.999 ¦ Ceiling=1 ¦¦ Implementation Data: Output field='Complete/Partial/Not Complete'; Standard/Reference='ISO/IEC 25012 Data Quality Model' | 0 | No Dependency |  | The empty state container. Needs the card chassis, the sheet and the progress indicator to already exist, because an empty state is defined by what is absent from a populated surface - build it earlier and you are guessing at the layout it has to replace. | 31,32,33
28 | 28 - Status Surface | 9508 | GEN-01275 | GEN-01275 | Embed M3 status Badges to mark completed and active milestone nodes. | Embed M3 status Badges to mark completed and active milestone nodes. | 1. Plan and scope this step. 2. Implement the core configuration. 3. Test and validate in staging. 4. Document and commit to runbook. | Architecture & Implementation Governance | What exact configuration and validation approach should be applied for: Embed M3 status Badges to mark completed and active milestone nodes.? | UX Flow / BigQuery | Embed M3 status Badges to mark completed and active milestone nodes. is a critical implementation step. Without it, downstream steps lack the required baseline configuration. | Ensures sub-100ms API response latencies on mobile clients via optimized backend configuration. | Single-column mobile layout with M3 status cards displaying step completion state. | Data/artifacts to prepare: Embed M3 status Badges to mark completed and active milestone…. Metric config: 'Real-Time Status Update Latency' (floor threshold: <30s). Reference standard/spec to configure against: GPS/Telematics Real-Time Tracking SLA. Output field to capture: Good/Average/Poor. | Users interact with this step exclusively through the mobile engineering console. Read-only M3 KPI cards with deep-link drill-down. | Engineering console dashboard displays step health via M3 Elevated Card with inline status chip. | English Code (EC) blueprint required before any code is written. All functions must have single-verb EC headers. | Core pattern for this step stored as a reusable module in the shared library. | @habot/shared-library | All step execution events stream to BigQuery partitioned by event_date, clustered by trace_id. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: N/A ¦ Row: 9508.0 | 4 Hours | Fully configured and validated implementation of: Embed M3 status Badges to mark completed and active milestone nodes.. | 100% CI/CD pass rate. All validation checks passing. Documentation committed to runbook. | Dependent on prior foundational steps. | M3 responsive layout: single-column on mobile (<600dp), multi-column on desktop (≥840dp). | M3 Elevated Cards Level 2 (3dp). M3 Status Chips for health indicators. 48x48dp touch targets. | Background polling refreshes data every 30 seconds. Pull-to-refresh triggers manual sync. | M3 Bottom Sheet for configuration inputs. M3 Snackbar for confirmations. Material You dynamic color. | Mobile Engineering, GCP Architecture, UX/UI Design (MD3), DCDF Engine Architecture. | CI/CD pipeline physically blocks deployment if any gate for this step fails. | Automated Liveness Handshake monitors this step every 30 seconds and triggers rollback on failure. | Eliminates manual overhead, reduces operational cost, and protects revenue pipelines. | Engineers and end-users experience reliable, uninterrupted platform performance. | M3 responsive single-column on mobile, multi-panel on tablet/desktop. 48x48dp touch targets. | Us: Eliminates manual overhead and reduces operational cost. ¦ Customer: Reliable, uninterrupted platform performance. | Embed M3 status Badges to mark completed and active milestone nodes. | Embed M3 status Badges to mark completed and active milestone nodes. | Real-Time Status Update Latency | <30s | <5s | <60s | Good/Average/Poor | GPS/Telematics Real-Time Tracking SLA | Fredrick | Embed M3 status Badges to mark completed and active milestone…; Completion Status ('Good/Average/Poor'); Action/Event Timestamp; User/Session ID | Data Required: Real-Time Status Update Latency ¦¦ Configuration Data: Floor=<30s ¦ Optimal=<5s ¦ Ceiling=<60s ¦¦ Implementation Data: Output field='Good/Average/Poor'; Standard/Reference='GPS/Telematics Real-Time Tracking SLA' | 0 | No Dependency |  | M3 status Badges for completed and active nodes. Follows the feedback surfaces because a badge is the persistent form of the same status a snackbar announces transiently, and both must draw from one status vocabulary rather than two. | 29,31,32
29 | 29 - Content Surface | 9684 | GEN-01452 | GEN-01452 | Construct the card UI chassis using M3 Outlined or Elevated Card specifications. | Construct the card UI chassis using M3 Outlined or Elevated Card specifications. | 1. Plan and scope this step. 2. Implement the core configuration. 3. Test and validate in staging. 4. Document and commit to runbook. | Architecture & Implementation Governance | What exact configuration and validation approach should be applied for: Construct the card UI chassis using M3 Outlined or Elevated Card specifications.? | UX Flow / BigQuery | Construct the card UI chassis using M3 Outlined or Elevated Card specifications. is a critical implementation step. Without it, downstream steps lack the required baseline configuration. | Ensures sub-100ms API response latencies on mobile clients via optimized backend configuration. | Single-column mobile layout with M3 status cards displaying step completion state. | Data/artifacts to prepare: Construct the card UI chassis using M3 Outlined or Elevated…. Metric config: 'Real-Time Availability Badge Accuracy' (floor threshold: 0.95). Reference standard/spec to configure against: ISO/IEC 25010 (Data Currency/Accuracy). Output field to capture: Pass/Fail. | Users interact with this step exclusively through the mobile engineering console. Read-only M3 KPI cards with deep-link drill-down. | Engineering console dashboard displays step health via M3 Elevated Card with inline status chip. | English Code (EC) blueprint required before any code is written. All functions must have single-verb EC headers. | Core pattern for this step stored as a reusable module in the shared library. | @habot/shared-library | All step execution events stream to BigQuery partitioned by event_date, clustered by trace_id. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: N/A ¦ Row: 9684.0 | 4 Hours | Fully configured and validated implementation of: Construct the card UI chassis using M3 Outlined or Elevated Card specifications.. | 100% CI/CD pass rate. All validation checks passing. Documentation committed to runbook. | Dependent on prior foundational steps. | M3 responsive layout: single-column on mobile (<600dp), multi-column on desktop (≥840dp). | M3 Elevated Cards Level 2 (3dp). M3 Status Chips for health indicators. 48x48dp touch targets. | Background polling refreshes data every 30 seconds. Pull-to-refresh triggers manual sync. | M3 Bottom Sheet for configuration inputs. M3 Snackbar for confirmations. Material You dynamic color. | Mobile Engineering, GCP Architecture, UX/UI Design (MD3), DCDF Engine Architecture. | CI/CD pipeline physically blocks deployment if any gate for this step fails. | Automated Liveness Handshake monitors this step every 30 seconds and triggers rollback on failure. | Eliminates manual overhead, reduces operational cost, and protects revenue pipelines. | Engineers and end-users experience reliable, uninterrupted platform performance. | M3 responsive single-column on mobile, multi-panel on tablet/desktop. 48x48dp touch targets. | Us: Eliminates manual overhead and reduces operational cost. ¦ Customer: Reliable, uninterrupted platform performance. | Construct the card UI chassis using M3 Outlined or Elevated Card specifications. | Construct the card UI chassis using M3 Outlined or Elevated Card specifications. | Real-Time Availability Badge Accuracy | 0.95 | 0.999 | 1.0 | Pass/Fail | ISO/IEC 25010 (Data Currency/Accuracy) | Fredrick | Construct the card UI chassis using M3 Outlined or Elevated…; Completion Status ('Pass/Fail'); Action/Event Timestamp; User/Session ID | Data Required: Real-Time Availability Badge Accuracy ¦¦ Configuration Data: Floor=0.95 ¦ Optimal=0.999 ¦ Ceiling=1 ¦¦ Implementation Data: Output field='Pass/Fail'; Standard/Reference='ISO/IEC 25010 (Data Currency/Accuracy)' | 0 | No Dependency |  | The card chassis - M3 Outlined and Elevated variants built on the elevation ladder from Step 4 and the shape tokens from Step 2. Every list, empty state and badge host in the rest of this batch renders inside a card, so the chassis has to be settled before they are. | 31,32,33
30 | 30 - Motion | 8441 | GEN-00201 | GEN-00201 | Use Material Design 3 shared axis transitions for mobile view state changes. | Use Material Design 3 shared axis transitions for mobile view state changes. | 1. Plan and scope this step. 2. Implement the core configuration. 3. Test and validate in staging. 4. Document and commit to runbook. | Architecture & Implementation Governance | What exact configuration and validation approach should be applied for: Use Material Design 3 shared axis transitions for mobile view state changes.? | UX Flow / BigQuery | Use Material Design 3 shared axis transitions for mobile view state changes. is a critical implementation step. Without it, downstream steps lack the required baseline configuration. | Ensures sub-100ms API response latencies on mobile clients via optimized backend configuration. | Single-column mobile layout with M3 status cards displaying step completion state. | Data/artifacts to prepare: Use Material Design 3 shared axis transitions for mobile view…. Metric config: 'General Task Completion Quality' (floor threshold: Task completed with documented exceptions). Reference standard/spec to configure against: Internal Process Gate — no external quantitative standard applies (Agile Definition of Done, Scrum Guide 2020). Output field to capture: Complete/Partial/Not Complete. | Users interact with this step exclusively through the mobile engineering console. Read-only M3 KPI cards with deep-link drill-down. | Engineering console dashboard displays step health via M3 Elevated Card with inline status chip. | English Code (EC) blueprint required before any code is written. All functions must have single-verb EC headers. | Core pattern for this step stored as a reusable module in the shared library. | @habot/shared-library | All step execution events stream to BigQuery partitioned by event_date, clustered by trace_id. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: N/A ¦ Row: 8441.0 | 4 Hours | Fully configured and validated implementation of: Use Material Design 3 shared axis transitions for mobile view state changes.. | 100% CI/CD pass rate. All validation checks passing. Documentation committed to runbook. | Dependent on prior foundational steps. | M3 responsive layout: single-column on mobile (<600dp), multi-column on desktop (≥840dp). | M3 Elevated Cards Level 2 (3dp). M3 Status Chips for health indicators. 48x48dp touch targets. | Background polling refreshes data every 30 seconds. Pull-to-refresh triggers manual sync. | M3 Bottom Sheet for configuration inputs. M3 Snackbar for confirmations. Material You dynamic color. | Mobile Engineering, GCP Architecture, UX/UI Design (MD3), DCDF Engine Architecture. | CI/CD pipeline physically blocks deployment if any gate for this step fails. | Automated Liveness Handshake monitors this step every 30 seconds and triggers rollback on failure. | Eliminates manual overhead, reduces operational cost, and protects revenue pipelines. | Engineers and end-users experience reliable, uninterrupted platform performance. | M3 responsive single-column on mobile, multi-panel on tablet/desktop. 48x48dp touch targets. | Us: Eliminates manual overhead and reduces operational cost. ¦ Customer: Reliable, uninterrupted platform performance. | Use Material Design 3 shared axis transitions for mobile view state changes. | Use Material Design 3 shared axis transitions for mobile view state changes. | General Task Completion Quality | Task completed with documented exceptions | 100% completion matching stated implementation-step intent | 1.0 | Complete/Partial/Not Complete | Internal Process Gate — no external quantitative standard applies (Agile Definition of Done, Scrum Guide 2020) | Fredrick | Use Material Design 3 shared axis transitions for mobile view…; Completion Status ('Complete/Partial/Not Complete'); Action/Event Timestamp; User/Session ID | Data Required: General Task Completion Quality ¦¦ Configuration Data: Floor=Task completed with documented exceptions ¦ Optimal=100% completion matching stated implementation-step intent ¦ Ceiling=1 ¦¦ Implementation Data: Output field='Complete/Partial/Not Complete'; Standard/Reference='Internal Process Gate — no external quantitative standard applies (Agile Definition of Done, Scrum Guide 2020)' | 0 | No Dependency |  | MD3 shared-axis transitions for view state changes. Extends the motion token layer from Steps 11-12 with the transition patterns the new surfaces need, and lands before the list work so list navigation animates through the shared axis instead of a bespoke curve. | 31,32,33
31 | 31 - List Behaviour | 1555 | IS38-SGTIM-018-AS01 | IS38-SGTIM-018-AS01-A01 | Apply M3 Overscroll Stretch on MTOI Lists | Open Material Design 3 (M3) UI components configuration workspace. | 1) Update to Compose Foundation 1.1.0+. 2) Apply to LazyColumn task lists. 3) Test scrolling bounds. 4) Verify physical elasticity feel on devices. | UI Experience | How does the list feel when the user reaches the end of their task queue? | Interaction | Delivers a native, high-quality mobile feel. Visual feedback like overscroll prevents users from thinking the app is frozen when they hit the bottom of a list. |  | The list physically "stretches" and bounces back, confirming the boundary organically. | Atomic-level data fields: Component Name; Component Type; Component Properties; State Definitions; Component Hierarchy ¦¦ No matched reference row in Setup Implementation master list — required data fields limited to atomic-level Data Collection Requirements only; standardized Mobile UX/UI & domain-expertise fields unavailable, verify manually. | Delightful, kinetic scrolling experience. | N/A. | Stretch overscroll is on by default in M3 scrolling containers and must not be overridden. | Applies globally to all lists and grids. | Compose Foundation. | N/A. | Level 1 ¦ Phase: SETUP-01 ¦ Atomic Step: 1.0 ¦ Row: 1555.0 | 1h | A polished, native-feeling list interaction. | Physical device testing confirms the stretch effect upon reaching the end of the MTOI task list. | HC-BIO-0003. | Overscroll uses a stretch effect at the edge of scrolling containers to signify boundaries. | Maintain fluid, 60fps animations during the stretch physics. | Rely on default behavior in LazyColumn (Compose Foundation 1.1.0 and above). | Do not implement custom overlapping scroll bounds that break the native physics. |  | Built-in Material 3 physics prevent unnatural scrolling breaks or rigid UI halts. | Designers who attempt to overwrite this native behavior will fail UI review, forcing them to adhere to M3 defaults. |  |  |  | For Us: Reduces development time by leveraging built-in, highly optimized library behaviors rather than coding custom physics. For Customer: (The Worker): A delightful, modern app experience that feels premium and responsive to their touch. | Apply M3 Overscroll Stretch on MTOI Lists | Open Material Design 3 (M3) UI components configuration workspace. | Asset & Component Discovery Completeness - Material design 3 m3 ui components | 90% of target assets confirmed present | 100% of target assets confirmed present | 100% (full inventory - no further discovery value beyond complete coverage) | Complete/Partial/Not Complete | Confirm the full inventory of the referenced files, components, or directories is located before any downstream configuration begins; partial discovery is the leading cause of rework later in the build. | Fredrick | Component Name; Component Type; Component Properties; State Definitions; Component Hierarchy; Completion Status ('Complete/Partial/Not Complete'); Action/Event Timestamp; User/Session ID | Data Required: Asset & Component Discovery Completeness - Material design 3 m3 ui components ¦¦ Configuration Data: Floor=90% of target assets confirmed present ¦ Optimal=100% of target assets confirmed present ¦ Ceiling=100% (full inventory - no further discovery value beyond complete coverage) ¦¦ Implementation Data: Output field='Complete/Partial/Not Complete'; Standard/Reference='Confirm the full inventory of the referenced files, components, or directories is located before any downstream configuration begins; partial…' | 0 | No Dependency |  | M3 overscroll stretch on lists. A one-hour step that establishes the physical feel of a list boundary before the virtualisation engine changes how those boundaries are computed. Cheap to do now, awkward to retrofit once chunking is in place. | 32,33
32 | 32 - List Engine | 2468 | CPNCA-006 | CPNCA-006-A01 | Build a standardized list virtualization and dynamic data chunking component for data tables Operationalizing System Architecture Design]. | Review the mobile user interface architecture documentation concerning system virtualization patterns. | Author a container component that calculates visible viewport boundaries using real-time scroll tracking Operationalizing System Architecture Design]. Implement data partitioning hooks that fetch record batches (e.g., 20 items per request) rather than loading entire datasets at once. Create structural item wrappers that position elements cleanly within a virtual scrolling track. Add automated cleanup listeners that unmount off-screen data rows to free up mobile device memory. | Frontend System Baseline. | Choose between using infinite scrolling mechanics or clear "Load More" action flags based on data accessibility needs. | Interaction / BigQuery. | Attempting to render thousands of complex interactive rows on a mobile browser quickly drains system memory, causing sluggish scrolling or app crashes. | Ensures complex data lists remain responsive and smooth even on entry-level mobile hardware with limited memory. | Long data collections transform into smooth, scrollable feeds that render rows cleanly as the user navigates. | Atomic-level data fields: Document Title; Document URL; Last Updated Date; Accessibility Status; Document Access Log ¦¦ Mobile UX/UI design config required: Use standard MD3 pull-to-refresh mechanics to trigger fresh data reloads. ¦ Style loading indicator paths using core brand identity primary color tokens. ¦ Configure scroll containers with smooth scrolling properties (-webkit-overflow-scrolling: touch). ¦ Map row actions to fit within standard mobile interaction boundaries. ¦¦ Domain expertise/sign-off required: High-Performance Frontend Architect / DOM Optimization Engineer. | Users browse heavy historical records without interface lag, stuttering, or device freezing. | Heavy data grids adapt into mobile-friendly scrollable lists that load content on demand Operationalizing System Architecture Design]. | All interfaces handling open-ended data collections must use the standardized virtual scrolling wrapper structure. | High; a single list virtualization wrapper manages all data feed views across different modules. | Private core template package (@habot-connect/layout-shell). | Optimize pagination query strings to hit clustered BigQuery indexes, ensuring rapid data delivery to mobile clients. | Level 11 ¦ Phase: SETUP-11 ¦ Atomic Step: 1.0 ¦ Row: 2468.0 | 12 Hours | Virtualized scrolling component suite live and running across core list views. | Loading a test collection of 10,000 items preserves a consistent, low DOM element count during continuous scrolling. | HC-DE-0274 Universal Mobile Component Registry Initialization, HC-CMP-0231 Skeleton Loader Primitives Implementation. Mobile-First & Responsive UX Google Material Design Decision: Use standard MD3 pull-to-refresh mechanics to trigger fresh data reloads. Mobile-First & Responsive UI Google Material Design Decision: Style loading indicator paths using core brand identity primary color tokens. Mobile-First & Responsive UX Google Material Design Implementation: Configure scroll containers with smooth scrolling properties (-webkit-overflow-scrolling: touch). Mobile-First & Responsive UI Google Material Design Implementation: Map row actions to fit within standard mobile interaction boundaries. Domain expertise needed to implement this step: High-Performance Frontend Architect / DOM Optimization Engineer. Mistake-Proofing (Poka-Yoke): The pagination component enforces an upper request boundary limit; it blocks queries requesting more than 50 rows at once, protecting mobile client resources. Self-Chasing: Application tracking scripts audit client performance; if rendering loops drop below 45fps during a scroll interaction, performance flags alert the optimization queue. Vitality & Prosperity (VAP): What creates VAP for us: Minimizes API gateway payload sizes, optimizing server processing efficiency across the board. What creates VAP for the customer: Provides a lag-free data browsing experience, turning complex corporate reporting into an intuitive mobile feed. | Use standard MD3 pull-to-refresh mechanics to trigger fresh data reloads. | Style loading indicator paths using core brand identity primary color tokens. | Configure scroll containers with smooth scrolling properties (-webkit-overflow-scrolling: touch). | Map row actions to fit within standard mobile interaction boundaries. | High-Performance Frontend Architect / DOM Optimization Engineer. |  |  | Minimizes API gateway payload sizes, optimizing server processing efficiency across the board. | Provides a lag-free data browsing experience, turning complex corporate reporting into an intuitive mobile feed. |  |  | Build a standardized list virtualization and dynamic data chunking component for data tables Operationalizing System Architecture Design]. | Review the mobile user interface architecture documentation concerning system virtualization patterns. | Requirements / Discovery Coverage (%) | 90% of relevant items identified | 98% of relevant items identified | 100% of relevant items identified | Complete/Partial/Not Complete | Discovery and audit activities in world-class delivery practice are expected to reach near-complete coverage of the target scope before downstream build work starts. | Fredrick | Document Title; Document URL; Last Updated Date; Accessibility Status; Document Access Log; Completion Status ('Complete/Partial/Not Complete'); Action/Event Timestamp; User/Session ID | Data Required: Requirements / Discovery Coverage (%) ¦¦ Configuration Data: Floor=90% of relevant items identified ¦ Optimal=98% of relevant items identified ¦ Ceiling=100% of relevant items identified ¦¦ Implementation Data: Output field='Complete/Partial/Not Complete'; Standard/Reference='Discovery and audit activities in world-class delivery practice are expected to reach near-complete coverage of the target scope before downstream…' | 0 | No Dependency |  | List virtualisation with dynamic data chunking - viewport boundary calculation, batched fetches, low element count at 10,000 rows. The largest step in the batch at 12 hours. It comes after the card chassis and overscroll because it renders those cards and must preserve that scroll feel under recycling. | 33
33 | 33 - Discovery | 3194 | ANSA-006 | ANSA-006-A01 | Implementation Step 15: Build an expandable search text line inside primary system headers. (ANSA-006) | Open the primary master application workspace navigation header component file. | Position a clean, clear text input field inside primary workspace headers. ¦ Setup brief keypress delay timers to wait for typing pauses before running queries. ¦ Render clear category match dropdown grids directly below the header search bar. ¦ Save successful lookup keyword values locally to provide rapid history shortcuts. | TZNG | Step 12. | Interaction | Provides an instant shortcut to find any project asset or configuration from anywhere in the application. | Expands to a clean full-screen view when tapped, giving fingers plenty of space and closing out busy charts. | Clicking search dims background layout elements and opens an organized quick-match panel. | Atomic-level data fields: Workspace Name; Workspace ID; Workspace Configuration; Member List; Workspace Status ¦¦ Mobile UX/UI design config required: Collapse search rows into a single icon on mobile, expanding to full-screen inputs when tapped. ¦ Include a prominent close button in the full-screen mobile search view to return to main pages. ¦ Position search as a wide, permanent text bar centered within desktop navigation lines. ¦ Group search results by type (like Projects, Tools, Teams) clearly inside desktop lists. ¦¦ Domain expertise/sign-off required: Search Integration Developer & Mobile Layout Designer. | Cuts out hours spent digging through menus by making assets searchable in two clicks. | Clear screen overlay masks focus attention on search result boxes when typing. | Provide a clear, one-tap "Clear Search" icon button inside the text input box. | Unified system header search widget (<GlobalSearchHub>). | mobile-gesture-nav-pack | Links directly with backend database search indexes to return matches while keeping query overhead low. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: 1.0 ¦ Row: 3194.0 | 5 Hours | Full-screen expanding search handlers and quick filtered result lists. | Entering valid search terms returns matching assets inside dropdown lists under 350ms. | HC-IAM-0045. ¦ "Mobile-First & Responsive UX Google Material Design Decision: Collapse search rows into a single icon on mobile, expanding to full-screen inputs when tapped. | Collapse search rows into a single icon on mobile, expanding to full-screen inputs when tapped. | Include a prominent close button in the full-screen mobile search view to return to main pages. | Position search as a wide, permanent text bar centered within desktop navigation lines. | Group search results by type (like Projects, Tools, Teams) clearly inside desktop lists. | Search Integration Developer & Mobile Layout Designer. | Filter out invalid code punctuation marks from search inputs automatically to prevent database query errors. | Search modules fall back to parsing locally cached workspace data if server connection drops interrupt active queries. | Improves application engagement numbers and lowers user drop-off rates across main hubs. | Delivers a powerful shortcut tool that saves teams hours of searching through deep menus. ¦ Step 23: Deploy Context-Aware Floating Action Buttons (FAB) | Include a prominent close button in the full-screen mobile search view to return to main pages. ¦ Position search as a wide, permanent text bar centered within desktop navigation lines. ¦ Group search results by type (like Projects, Tools, Teams) clearly inside desktop lists. |  | Implementation Step 15: Build an expandable search text line inside primary system headers. (ANSA-006) | Open the primary master application workspace navigation header component file. | Environment & Configuration Setup Readiness | Config file located & version-controlled | Config file opened in correct branch with schema validated pre-edit | N/A (gate, not a range) | Pass/Fail | Confirm the correct source-of-truth file/module is opened before any edits begin, to avoid config drift across environments. | Fredrick | Workspace Name; Workspace ID; Workspace Configuration; Member List; Workspace Status; Completion Status ('Pass/Fail'); Action/Event Timestamp; User/Session ID | Data Required: Environment & Configuration Setup Readiness ¦¦ Configuration Data: Floor=Config file located & version-controlled ¦ Optimal=Config file opened in correct branch with schema validated pre-edit ¦ Ceiling=N/A (gate, not a range) ¦¦ Implementation Data: Output field='Pass/Fail'; Standard/Reference='Confirm the correct source-of-truth file/module is opened before any edits begin, to avoid config drift across environments.' | 0 | No Dependency |  | The expandable search line inside the contextual header from Step 9, with keypress debounce, a results dropdown and local keyword history. Deliberately last of the UI steps: it consumes the header, the card chassis, the virtualised list, the empty state for zero results, and the progress indicator for the in-flight query. | -
34 | 34 - Telemetry | 4723 | UFHT-032 | UFHT-032 | UI Hesitation Tracker Engine Setup | Attach focus event listeners to every individual input field within the target form. |  | Mobile Data Caching | Are primary keys strictly enforced across all mobile caching tables? | BigQuery | Time travel only gives snapshots; the CHANGES function exposes the exact sequence of modifications for strict compliance and debugging. | Traces offline-to-online sync behaviors perfectly, ensuring no edge-case modification is lost during poor connectivity. | Admin-level history logs UI (Internal). | Atomic-level data fields: Step Execution ID; Execution Status; Execution Timestamp; Step Outcome; User ID ¦¦ Mobile UX/UI design config required: Ensure background tracking logic drops resource priorities during intensive rendering tasks. ¦ Maintain default component dimensions to avoid changing input balances during tracking. ¦ Record scrolling reversals to catch instances where users look back for instructions. ¦ Keep tracking hooks decoupled from main interface styling paths. ¦¦ Domain expertise/sign-off required: User Behavior Clickstream Engineering & Main-Thread Performance Optimization. | N/A (Backend Admin tracing). | Detailed Audit trails for each mobile End Document. | Change history tracking enablement. | Audit Query Module. | Query Repository. | Native BQ TVF utilization. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: 7.0 ¦ Row: 4723.0 | 2H | Historical Audit Report SQL. | Row_Level_Audit_Coverage == 100%. | Step 18 | Use adaptive card layout shifting from single-column (compact) to grid (expanded) view. | Apply Material M3 Card with tonal elevation and 16dp internal padding. | Implement LazyColumn with DiffUtil for performant list rendering on mobile. | Set card maximum width to 640dp on expanded viewports; full-width on compact. | Data Engineering. | CHANGES TVF query strictly fails if the end_timestamp falls within the last 10 minutes, mechanically preventing querying volatile active buffers. | Failed query forces the auditor to respect the 10-minute buffer window constraint, ensuring data read stability. | Absolute transparency into the evolution of every single row of data, enabling perfect RCA. | Complete auditability of their actions and historical changes for trust and compliance. |  |  | UI Hesitation Tracker Engine Setup | Attach focus event listeners to every individual input field within the target form. | Event Listener Coverage Rate (%) | 95.0 | 99.0 | 100.0 | Complete/Partial/Not Complete | ISO 20252:2012 Market Research Standards | Fredrick | Step Execution ID; Execution Status; Execution Timestamp; Step Outcome; User ID; Completion Status ('Complete/Partial/Not Complete'); Action/Event Timestamp; User/Session ID | Data Required: Event Listener Coverage Rate (%) ¦¦ Configuration Data: Floor=95 ¦ Optimal=99 ¦ Ceiling=100 ¦¦ Implementation Data: Output field='Complete/Partial/Not Complete'; Standard/Reference='ISO 20252:2012 Market Research Standards' | 0 | No Dependency |  | The UI Hesitation Tracker engine - focus event listeners on every input field. Named directly in TTMAC-014 (Step 14) as the source of the double-tap correction rate, which is one of the three gates currently deferred. Placed here because it instruments the forms from Steps 15-18 and the surfaces from Steps 21-33 in one pass. | 35
35 | 35 - Telemetry | 8870 | GEN-00632 | GEN-00632 | Deploy Mobile UX Friction Logs (Hesitation Tracking) | Define the FrictionTracker widget wrapper class. | 1. Plan and scope this step. 2. Implement the core configuration. 3. Test and validate in staging. 4. Document and commit to runbook. | Architecture & Implementation Governance | What exact configuration and validation approach should be applied for: Define the FrictionTracker widget wrapper class.? | UX Flow / BigQuery | Define the FrictionTracker widget wrapper class. is a critical implementation step. Without it, downstream steps lack the required baseline configuration. | Ensures sub-100ms API response latencies on mobile clients via optimized backend configuration. | Single-column mobile layout with M3 status cards displaying step completion state. | Data/artifacts to prepare: Define the FrictionTracker widget wrapper class.. Metric config: 'Class Wrapper Integrity' (floor threshold: $100\%$). Reference standard/spec to configure against: Flutter/React Widget Wrapper. Output field to capture: Complete / Not Complete. | Users interact with this step exclusively through the mobile engineering console. Read-only M3 KPI cards with deep-link drill-down. | Engineering console dashboard displays step health via M3 Elevated Card with inline status chip. | English Code (EC) blueprint required before any code is written. All functions must have single-verb EC headers. | Core pattern for this step stored as a reusable module in the shared library. | @habot/shared-library | All step execution events stream to BigQuery partitioned by event_date, clustered by trace_id. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: N/A ¦ Row: 8870.0 | 4 Hours | Fully configured and validated implementation of: Define the FrictionTracker widget wrapper class.. | 100% CI/CD pass rate. All validation checks passing. Documentation committed to runbook. | Dependent on prior foundational steps. | M3 responsive layout: single-column on mobile (<600dp), multi-column on desktop (≥840dp). | M3 Elevated Cards Level 2 (3dp). M3 Status Chips for health indicators. 48x48dp touch targets. | Background polling refreshes data every 30 seconds. Pull-to-refresh triggers manual sync. | M3 Bottom Sheet for configuration inputs. M3 Snackbar for confirmations. Material You dynamic color. | Mobile Engineering, GCP Architecture, UX/UI Design (MD3), DCDF Engine Architecture. | CI/CD pipeline physically blocks deployment if any gate for this step fails. | Automated Liveness Handshake monitors this step every 30 seconds and triggers rollback on failure. | Eliminates manual overhead, reduces operational cost, and protects revenue pipelines. | Engineers and end-users experience reliable, uninterrupted platform performance. | M3 responsive single-column on mobile, multi-panel on tablet/desktop. 48x48dp touch targets. | Us: Eliminates manual overhead and reduces operational cost. ¦ Customer: Reliable, uninterrupted platform performance. | Deploy Mobile UX Friction Logs (Hesitation Tracking) | Define the FrictionTracker widget wrapper class. | Class Wrapper Integrity | $100\%$ | $100\%$ | N/A (100% target) | Complete / Not Complete | Flutter/React Widget Wrapper | Fredrick | Define the FrictionTracker widget wrapper class.; Completion Status ('Complete / Not Complete'); Action/Event Timestamp; User/Session ID | Data Required: Class Wrapper Integrity ¦¦ Configuration Data: Floor=$100\%$ ¦ Optimal=$100\%$ ¦ Ceiling=N/A (100% target) ¦¦ Implementation Data: Output field='Complete / Not Complete'; Standard/Reference='Flutter/React Widget Wrapper' | 0 | No Dependency |  | The FrictionTracker widget wrapper that consumes the listeners from Step 34 and turns them into friction logs. Together these two close the telemetry half of the TTMAC-014 deferral and turn Step 14 from Partial to Complete. Last, because it can only wrap components that already exist. | -