## Read Me
Steps 11-20 - Dependency-Free Build Order
Source | My stepsFN06082026.xlsx -> "Fredrick" tab (1,314 steps assigned to you)
Selection rule | Only steps where Dependency Count = 0 and Dependency (Atomic Step Serial No) = "No Dependency",
AND not already implemented in Steps 1-10.
Pool | 682 of your 1,314 steps have zero dependencies. 10 are done, so 672 remained. These 10 come from that pool.
Track chosen | Forms & feedback layer - the natural next layer on top of the tokens, grid, layout shell,
navigation header and touch targets delivered in Steps 1-10.
Ordering rule | Foundation-first: motion tokens -> interaction core -> touch standards -> input primitives ->
validation UX -> composition -> resilience -> multi-step composition.
No step here depends on any other, so you can start any of them today. The order means no rework:
each one consumes the artefact the previous one produced.
Two steps extend | Step 14 (TTMAC-014) extends the 48dp touch framework you shipped as Step 10 (TTMAC-011).
existing work | Step 13 (BPTR-0128) is the interaction-state counterpart to the token layer from Step 2 (RCGLA-001).
Both reuse existing code rather than re-solving it.
DATA QUALITY FLAG | Three snackbar/toast candidates were EXCLUDED because their columns are contaminated - the
Setup Step (Action) is a UI task but Expected Output / Completion Measures belong to a different
domain entirely. Worth fixing at source in the master sheet:
S.No 3865 HSFVS-012 "Implement M3 Snackbar for DCYN Failures"
-> Expected Output = "Terraform CORS policy rules"; Completion = "Request from unauthorized domain is rejected"
S.No 7253 PNSAD-026 "Build Floating Bottom Snackbar Feedback Banner"
-> Expected Output = "Enforced RLS Policies"; Completion = tenant row isolation in BigQuery
S.No 1368 EDBAA-001 "Design the Liveness Handshake Failure Toast"
-> Metric = "TLS Protocol Compliance Rate"; Expected Output = sign-up wireframe
That is why no snackbar/toast made this batch despite the track covering feedback. Once those rows
are corrected, a toast/snackbar step is the obvious first pick for Steps 21-30.
Columns | All 49 original columns preserved, in original order, with original values (verified cell-for-cell).
Four columns ADDED (shaded pale yellow): Implementation Order, Build Layer,
Why This Position In The Sequence, and Blocks (Steps That Need This).
Total effort | Approximately 5 working days of engineering time across the 10 steps.

## Build Sequence Summary
# | Build Layer | Global Ref ID | Atomic Step Ref ID | Setup Step (Action) | Est. Time | Dependency Count | Original S. No | Why This Position In The Sequence
11 | 11 - Motion Tokens | BPTR-0422 | BPTR-0422-A01 | Define Passive Failure Motion Curves. | 3 hours | 0 | 257 | The motion token layer must exist before anything animates. Fixes duration (300ms), easing curve, dimming intensity and auto-scroll behaviour once, so every later transition references a token instead of inventing a number. Nothing in this batch has a software prerequisite before it.
12 | 12 - Motion Tokens | REF-377 | REF-377-A01 | Set Progressive Stepper Transitions. | 2 hours | 0 | 400 | Completes the motion layer started in Step 11 with the stepper-specific values (200ms slide-in/out, easing, reduced-motion preference). Shipped alongside Step 11 because both live in the same Motion & Animation System file - splitting them means opening it twice.
13 | 13 - Interaction Core | BPTR-0128 | BPTR-0128-A01 | Establish Global Atomic Byt Micro-Interaction Boundaries | 6 Hours. | 0 | 1566 | The first component that consumes the motion tokens: an AtomicButton under 20 lines with active/focus/hover state feedback and passive touch listeners. Every interactive element built after this inherits from it, so it has to land before the input primitives.
14 | 14 - Touch Standards | TTMAC-014 | TTMAC-014-A01 | TTMAC-014 - Interactive Touch Target Standardization Engine Setup | 90 Minutes. | 0 | 2028 | Wraps the AtomicButton from Step 13 in protective padding zones and clearance spacing. Extends the 48dp framework you already shipped as Step 10 (TTMAC-011) rather than duplicating it, so it must follow the component it is protecting.
15 | 15 - Input Primitive | CSIVW-001 | CSIVW-001-A01 | Implement strict client-side Input Masking on all template text area entry portals. | 5 Minutes. | 0 | 3062 | First form primitive: client-side input masking - alphanumeric keystroke filter, regex block on unauthorised character sets, clipboard paste rejection past the field cap. Sits inside the core text area component that Steps 16-19 all decorate.
16 | 16 - Input Primitive | IS12-CSIVW-011-AS01 | IS12-CSIVW-011-AS01-A01 | Setup character formatting filters across text entry boxes. | 5 Hours | 0 | 3205 | Character formatting filters build directly on the mask from Step 15: real-time formatting, non-numeric keystroke restriction on cost and dimension fields, helper text under the input, and submit-key gating driven by field validation status.
17 | 17 - Validation UX | IS02-CSIVW-005-AS01 | IS02-CSIVW-005-AS01-A01 | Program dynamic inline error layouts to activate when input fields fail validation checks. | 3 Hours | 0 | 2490 | Inline error layouts consume the validation status produced in Step 16. Binds error components to blur events, locks message text to high-contrast red under the affected input, and freezes form submission while errors are active.
18 | 18 - Composition | BPTR-0160 | BPTR-0160-A01 | Code and isolate mobile compound fields into distinct, standalone UI components featuring strict 48x48dp touch targets. | 2H | 0 | 3073 | Compound fields (split address blocks, combined date-time) become standalone components. Needs all four preceding pieces at once: masking (15), filters (16), inline errors (17) and the 48x48dp touch bounds (14). Building it earlier means retrofitting each one.
19 | 19 - Resilience | REF-197 | REF-197-A01 | Developing the Safe Error-Handling UI Rollback Handler | 130 Minutes | 0 | 3238 | The error boundary wraps the transactional forms built in Steps 15-18, scrubs sensitive backend paths from user-facing logs, and falls back to friendly copy when processing fails. Placed before the stepper so the stepper is wrapped as it is built, not retrofitted.
20 | 20 - Composition | FIEVR-033 | FIEVR-033-A01 | FIEVR-033 - Build Multi-Step Guided Carousel Layout Stepper | 10 Hours. | 0 | 3128 | The highest-level composition in this batch: a multi-step guided carousel stepper. Consumes the motion tokens (11-12), the validated inputs (15-18) and the error boundary (19). Deliberately last - it is the only step that needs everything else to exist first.

## Steps 1-10 (already done)
# | Global Ref ID | Atomic Step Ref ID | Setup Step (Action) | Original S. No | Status
1 | TTMCS-001 | TTMCS-001-A01 | Install and configure the verified Material 3 layout component framework within frontend client packages. | 1797 | Implemented - see Others/Fredrick/AISS_Verification_Methodology.md
2 | RCGLA-001 | RCGLA-001-A01 | Build global corporate style token variables inside the mobile client framework. | 3227 | Implemented - see Others/Fredrick/AISS_Verification_Methodology.md
3 | TTMCS-004 | TTMCS-004-A01 | TTMCS-004 — Configure Atomic Light/Dark Adaptation Tokens | 1654 | Implemented - see Others/Fredrick/AISS_Verification_Methodology.md
4 | TTMCS-005 | TTMCS-005-A01 | TTMCS-005 — Mobile Dark Mode Contrast Enforcement | 3139 | Implemented - see Others/Fredrick/AISS_Verification_Methodology.md
5 | SSTLA-004 | SSTLA-004-A01 | Define the exact base breakpoint, column count, fluid margin, and gutter widths for the core mobile experience before scaling upward to tablet or desktop views. | 169 | Implemented - see Others/Fredrick/AISS_Verification_Methodology.md
6 | RCGLA-012 | RCGLA-012-A01 | RCGLA-012 - Initialize Atomic Grid System & Mobile Viewport Constraints | 345 | Implemented - see Others/Fredrick/AISS_Verification_Methodology.md
7 | RCGLA-032 | RCGLA-032-A01 | RCGLA-032 - Configure the Material Design 3 (MD3) adaptive 4-column fluid layout token engine for mobile screens. | 3051 | Implemented - see Others/Fredrick/AISS_Verification_Methodology.md
8 | RCGLA-018 | RCGLA-018-A01 | RCGLA-018 - Universal Master Layout Architecture for React Components | 356 | Implemented - see Others/Fredrick/AISS_Verification_Methodology.md
9 | ANSA-012 | ANSA-012-A01 | Establish Contextual Navigation Header Framework. | 4 | Implemented - see Others/Fredrick/AISS_Verification_Methodology.md
10 | TTMAC-011 | TTMAC-011-A01 | Touch-Target Optimization Framework Setup (48×48 dp Minimum Interaction Nodes). | 3095 | Implemented - see Others/Fredrick/AISS_Verification_Methodology.md

## Steps 11-20 - Build Order
Implementation Order | Build Layer | S. No | Global Reference ID | Atomic Steps Reference ID | Setup Step (Action) | Setup Step Description | 4 Substeps | Decision Group | Decision to be Made Before Setup Step | Decision Category | Why This Matters | Mobile App First Implication | UX Translation | Data Requirement | User Interaction / Flow Impact | Dashboard / Interface Implication | What Standardized Must Be Done | Atomic Reusability | Common Library to Store | GCP / BigQuery Alignment | Sequence Order | Estimated Time Required | Expected Output | Completion Measures | Dependencies | Mobile-First & Responsive UX Google Material Design Decision | Mobile-First & Responsive UI Google Material Design Decision | Mobile-First & Responsive UX Google Material Design Implementation | Mobile-First & Responsive UI Google Material Design Implementation | Domain Expertise Needed | Mistake-Proofing (Poka-Yoke) | Self-Chasing | What Creates Vitality & Prosperity For Us | What Creates Vitality & Prosperity For the Customer | Responsive UX/UI Design | Vitality & Prosperity (VAP) | Setup Step (Action).1 | Atomic Step | Metric Name | Floor Boundary | Optimal Target | Ceiling Boundary | Best Qualitative Output | Best Qualitative/Quantitative Output Type | Assigned Team Member | Data Collected by System | Required Data / Configuration / Implementation Fields (from AL-AQ Analysis) | Dependency Count | Dependency (Atomic Step Serial No) | Output format | Why This Position In The Sequence | Blocks (Steps That Need This)
11 | 11 - Motion Tokens | 257 | BPTR-0422 | BPTR-0422-A01 | Define Passive Failure Motion Curves. | Open the core motion design framework settings file for the application environment. | 1. Set animation duration (300ms). 2. Define easing curve. 3. Decide dimming intensity. 4. Set auto-scroll. | UI/UX | Set the baseline motion timings. | Interaction | Passive failures must physically halt the user journey to address quarantined data. | Optimized CSS transitions ensure 60fps rendering without draining mobile battery. | Standardized motion profile for system-generated stops. | Atomic-level data fields: Object Type; Object Location/Path; Open Status; Timestamp; File Handle ID ¦¦ No matched reference row in Setup Implementation master list — required data fields limited to atomic-level Data Collection Requirements only; standardized Mobile UX/UI & domain-expertise fields unavailable, verify manually. | User forced to address quarantined data immediately. | Dictates error presentation in active queues. | Motion and animation design tokens. | Wraps all compliance/validation failures. | Motion & Animation System. | Triggered instantly by Cloud Run rejections. | Level 12 ¦ Phase: SETUP-12 ¦ Atomic Step: 1.0 ¦ Row: 257.0 | 3 hours | CSS motion token library. | Standardized CSS transitions defined. |  | Motion draws eye to failure point on any screen. | Material Design motion principles. | Clear communication of state. | CSS transition properties. | UI/UX | Animation physically locks surrounding UI until acknowledged. | Failed element pulses continuously until resolved. For Vitality and Prosperity give: | Reduces support tickets. | Friendly guidance keeps momentum high. |  |  | Define Passive Failure Motion Curves. | Open the core motion design framework settings file for the application environment. | Requirements Traceability Coverage | 90.0 | 98.0 | 100.0 | Complete (Scale: Complete/Partial/Not Complete) | Confirm the source-of-truth document is the latest approved version and every referenced field/rule is traceable back to it before proceeding. | Fredrick | Object Type; Object Location/Path; Open Status; Timestamp; File Handle ID; Completion Status ('Complete (Scale: Complete/Partial/Not Complete)'); Action/Event Timestamp; User/Session ID | Data Required: Requirements Traceability Coverage ¦¦ Configuration Data: Floor=90 ¦ Optimal=98 ¦ Ceiling=100 ¦¦ Implementation Data: Output field='Complete (Scale: Complete/Partial/Not Complete)'; Standard/Reference='Confirm the source-of-truth document is the latest approved version and every referenced field/rule is traceable back to it before proceeding.' | 0 | No Dependency |  | The motion token layer must exist before anything animates. Fixes duration (300ms), easing curve, dimming intensity and auto-scroll behaviour once, so every later transition references a token instead of inventing a number. Nothing in this batch has a software prerequisite before it. | 12,13,14,20
12 | 12 - Motion Tokens | 400 | REF-377 | REF-377-A01 | Set Progressive Stepper Transitions. | Locate the progressive stepper component in the UI architecture. | 1. Define slide-in duration (200ms). 2. Define slide-out duration. 3. Decide easing function. 4. Respect reduced motion preferences. | OPS | Set the global transition variable. | UX Flow | Splitting tasks into single Byt screens requires fast transitions to avoid UI fatigue. | Single-field per screen ensures the mobile keyboard never obscures the CTA button. | Smooth, rapid lateral sliding motion. | Atomic-level data fields: Architecture Pattern; Component Hierarchy; Data Flow Diagram; Integration Points ¦¦ No matched reference row in Setup Implementation master list — required data fields limited to atomic-level Data Collection Requirements only; standardized Mobile UX/UI & domain-expertise fields unavailable, verify manually. | Users maintain flow state through multi-part processes. | Gamifies data entry through swift progression. | Motion tokens for view switching. | Applied to all Progressive Disclosure wizards. | Motion & Animation System. |  | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: 1.0 ¦ Row: 400.0 | 2 hours | Motion prototypes. | Transitions feel instantaneous and fluid. |  | Motion provides spatial context. | CSS transform animations. | Sense of rapid accomplishment. | prefers-reduced-motion media queries. | OPS | Unmounts previous steps from DOM to prevent accidental back-edits. | Stalling triggers subtle pulse on "Next" button, chasing user to continue. For Vitality and Prosperity give: | Categorical data feeds directly into RCA queries. | Structured reporting prevents users feeling ignored. |  |  | Set Progressive Stepper Transitions. | Locate the progressive stepper component in the UI architecture. | Location Accuracy | 100.0 | 100.0 | 100.0 | Complete/Not Complete | Target correct component. | Fredrick | Architecture Pattern; Component Hierarchy; Data Flow Diagram; Integration Points; Completion Status ('Complete/Not Complete'); Action/Event Timestamp; User/Session ID | Data Required: Location Accuracy ¦¦ Configuration Data: Floor=100 ¦ Optimal=100 ¦ Ceiling=100 ¦¦ Implementation Data: Output field='Complete/Not Complete'; Standard/Reference='Target correct component.' | 0 | No Dependency |  | Completes the motion layer started in Step 11 with the stepper-specific values (200ms slide-in/out, easing, reduced-motion preference). Shipped alongside Step 11 because both live in the same Motion & Animation System file - splitting them means opening it twice. | 13,20
13 | 13 - Interaction Core | 1566 | BPTR-0128 | BPTR-0128-A01 | Establish Global Atomic Byt Micro-Interaction Boundaries | Fetch the Material Design specifications documentation for micro-interaction states. | Define global Material Design CSS tokens forcing minimal tap-target area distributions ¦ Build an abstract, pure AtomicButton component under 20 lines of total functional code ¦ Code dynamic visual feedback systems simulating rapid interactive state states (active, focus, hover) ¦ Implement performance-tuned passive touch listeners directly to eradicate 300ms mobile touch-click delays completely. | Interaction Design Core. | Finalize global interactive color states and token variables mapping directly to Material Design specs. | Interaction. | Eliminates fat-finger mistakes where customers hit multiple interactive buttons simultaneously, which dramatically drops mobile onboarding completion metrics. | Ensures interface components remain deeply optimized around tactile thumb range spaces, explicitly prioritizing mobile touch constraints over mouse-hover mechanics. | Buttons display spacious padding states internally, maximizing tap reliability while retaining a visually lean presentation. | Atomic-level data fields: Document Title; Document URL; Last Updated Date; Accessibility Status; Document Access Log ¦¦ No matched reference row in Setup Implementation master list — required data fields limited to atomic-level Data Collection Requirements only; standardized Mobile UX/UI & domain-expertise fields unavailable, verify manually. | Users receive crisp, instant visual micro-confirmations, elevating perceived application speed metrics. | Prevents tight configurations of interactive buttons inside dashboard layout structures. | Enforce 100% compliance with standard Google Material Design touch element dimensions. | Fully universal across every single interactive call-to-action component. | @habot-core/atomic-interactive-byts. | Real-time logging of interactive click streams fed directly into analytics pipelines via event-driven pub-sub systems. | Level 1 ¦ Phase: SETUP-01 ¦ Atomic Step: 1.0 ¦ Row: 1566.0 | 6 Hours. | Complete collection of basic functional interactive button systems accompanied by robust English Code validation maps. | Lighthouse accessibility checks scoring an absolute 100 on interactive target criteria. | HC-FE-0002 (Mobile Grid Foundation). | Mandate a minimum interactive tap target sizing constraint of 48 x 48px. | Maintain an absolute minimum safety padding boundary of 8px separating distinct interactive units. | Utilize programmatic dynamic padding extensions to expand small icons into full touch-compliant zones. | Leverage absolute hardware-accelerated CSS transforms to handle touch ripple feedback workflows efficiently. | Interaction Designer / Frontend Engineer. | TypeScript compiler constraints instantly flag compile errors if a developer creates a clickable component without specifying explicit touch padding parameters. | Runtime assertions write explicit warning flags to console environments if computed DOM node bounding client rectangles fall beneath target 48px parameters. | Reduced support overhead for touch-related UI bugs. | Frustration-free navigation with zero "fat-finger" selection errors. |  |  | Establish Global Atomic Byt Micro-Interaction Boundaries | Fetch the Material Design specifications documentation for micro-interaction states. | Requirements Traceability Coverage | 90.0 | 98.0 | 100.0 | Complete (Scale: Complete/Partial/Not Complete) | Confirm the source-of-truth document is the latest approved version and every referenced field/rule is traceable back to it before proceeding. | Fredrick | Document Title; Document URL; Last Updated Date; Accessibility Status; Document Access Log; Completion Status ('Complete (Scale: Complete/Partial/Not Complete)'); Action/Event Timestamp; User/Session ID | Data Required: Requirements Traceability Coverage ¦¦ Configuration Data: Floor=90 ¦ Optimal=98 ¦ Ceiling=100 ¦¦ Implementation Data: Output field='Complete (Scale: Complete/Partial/Not Complete)'; Standard/Reference='Confirm the source-of-truth document is the latest approved version and every referenced field/rule is traceable back to it before proceeding.' | 0 | No Dependency |  | The first component that consumes the motion tokens: an AtomicButton under 20 lines with active/focus/hover state feedback and passive touch listeners. Every interactive element built after this inherits from it, so it has to land before the input primitives. | 14,15,16,17,18,19,20
14 | 14 - Touch Standards | 2028 | TTMAC-014 | TTMAC-014-A01 | TTMAC-014 - Interactive Touch Target Standardization Engine Setup | Open the base UI asset repository at /components/atomic/buttons. | Wrap all interactive components in protective padding zones matching minimum target dimensions. ¦ Set default dimensions for icon actions to maintain structural usability. ¦ Configure clearance spaces around closely positioned items to avoid accidental double taps. ¦ Test alignment grids against different device screen scale definitions. | Interaction Architecture Group. | Establish if expanding hit boxes beyond visible component outlines is acceptable for small icons. | Interaction | Eliminates input friction caused by missed taps, enhancing precision for field workers. | Maximizes operation speed on mobile, ensuring field inputs match physical interaction realities. | Small shortcut icons preserve wide invisible click paddings to avoid input errors. | Atomic-level data fields: Repository URL; Repository Branch; Access Rights; Commit History; Repository Version; Clone Status ¦¦ Mobile UX/UI design config required: Enforce a strict minimum size ($48 \times 48\text{ dp}$) for every interactive screen asset. ¦ Ensure row items maintain distinct spacing separations to avoid tracking confusion. ¦ Include clear visual feedback states immediately upon registering a tap action. ¦ Apply clean background expansion effects to indicate successful button activations. ¦¦ Domain expertise/sign-off required: Mobile Human-Computer Interaction (HCI) Engineering & Frontend Library Standardization. | Users can tap controls confidently on the go without zooming into screens. | Selection rows allow quick operation without triggering accidental row jumps. | Standardize hit sizes using approved dimensions ($48 \times 48\text{ dp}$). | Touch target configurations wrap all fundamental clickable elements. | Base UI asset collection under /components/atomic/buttons. | Tap error events route through streaming trackers to target refinement pools. | Level 9 ¦ Phase: SETUP-09 ¦ Atomic Step: 1.0 ¦ Row: 2028.0 | 90 Minutes. | Modular input elements optimized for high tap accuracy on mobile layouts. | Average frequency of double tap corrections on closely packed selections ($<1\%$). | HC-FE-0039, HC-FE-0055. | Enforce a strict minimum size ($48 \times 48\text{ dp}$) for every interactive screen asset. | Ensure row items maintain distinct spacing separations to avoid tracking confusion. | Include clear visual feedback states immediately upon registering a tap action. | Apply clean background expansion effects to indicate successful button activations. | Mobile Human-Computer Interaction (HCI) Engineering & Frontend Library Standardization. | The component compiler throws layout warnings if an asset's interactive region drops below required touch target dimensions. | Telemetry tracking logs touch patterns; if click retry metrics spike on a component, it gets automatically flagged for design review. Vitality & Prosperity (VAP): | Reduces UI bug tracking tasks by delivering highly predictable button assets across features. | Minimizes accidental click errors, allowing teams to complete tasks faster. |  |  | TTMAC-014 - Interactive Touch Target Standardization Engine Setup | Open the base UI asset repository at /components/atomic/buttons. | Asset/Resource Location & Access Confirmation | 0.9 | 0.98 | 1.0 | Complete/Partial/Not Complete | The target resource should be reachable from one authoritative, documented location; ad-hoc or memorised paths are a floor-level practice that should be upgraded to a referenced source of truth. | Fredrick | Repository URL; Repository Branch; Access Rights; Commit History; Repository Version; Clone Status; Completion Status ('Complete/Partial/Not Complete'); Action/Event Timestamp; User/Session ID | Data Required: Asset/Resource Location & Access Confirmation ¦¦ Configuration Data: Floor=0.9 ¦ Optimal=0.98 ¦ Ceiling=1 ¦¦ Implementation Data: Output field='Complete/Partial/Not Complete'; Standard/Reference='The target resource should be reachable from one authoritative, documented location; ad-hoc or memorised paths are a floor-level practice that should…' | 0 | No Dependency |  | Wraps the AtomicButton from Step 13 in protective padding zones and clearance spacing. Extends the 48dp framework you already shipped as Step 10 (TTMAC-011) rather than duplicating it, so it must follow the component it is protecting. | 18,19,20
15 | 15 - Input Primitive | 3062 | CSIVW-001 | CSIVW-001-A01 | Implement strict client-side Input Masking on all template text area entry portals. | Audit all template text area entry portals across the application to create a complete inventory. | 1. Embed an alphanumeric keystroke filter inside the core text area component. ¦ 2. Configure strict regular expression rules to block unauthorized character sets. ¦ 3. Physically reject text pasted from clipboard arrays that exceeds defined field memory caps. |  |  | Interaction | Blocks long unstructured stories from injecting layout breakages down the pipeline. | Reduces processing and text layout calculation loops on low-tier mobile processors, preventing UI lag. | Render form fields using clear error states and visible counter boundaries beneath text lines. | Atomic-level data fields: Template Name; Template Version; Template Type; Template Configuration; Creation Date; Created By; Creation Method; Initial Configuration; Object ID ¦¦ Mobile UX/UI design config required: Match baseline Material Design Form Field text validation protocols. ¦ Display standard clear helper text blocks directly beneath form rows. ¦ Execute fluid width styling parameters across parent grid wrappers. ¦ Apply clear border colors to easily distinguish focus states from validation errors. ¦¦ Domain expertise/sign-off required: Mobile Frontend Application Architecture. | The interface physically locks keyboard input once max character parameters are reached. | Displays field-level formatting error indicators directly inside the admin view container. | Consume verified text field components directly from the platform core library. | StandardTextInputMask element. | Shared NPM frontend engineering module package. | Validation failures stream to Cloud Logging to monitor layout exception trends. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: 1.0 ¦ Row: 3062.0 | 5 Minutes. | Reusable, responsive text entry block featuring automatic validation rules. | Zero recorded layout overflows or broken text strings across standard testing devices. | HC-INF-0003. | Match baseline Material Design Form Field text validation protocols. | Display standard clear helper text blocks directly beneath form rows. | Execute fluid width styling parameters across parent grid wrappers. | Apply clear border colors to easily distinguish focus states from validation errors. | Mobile Frontend Application Architecture. | The text area physically drops any pasted input that contains non-ASCII formatting profiles. | Form entry fields will completely grey out and lock screen transitions until string parameters pass, forcing the creator to adjust the copy. ¦ | Eliminates operational confusion between structural regulatory tracks and marketing promos. | Protects parent safety by isolating core protection terms from ad clutter. | Match baseline Material Design Form Field text validation protocols. ¦ Display standard clear helper text blocks directly beneath form rows. ¦ Execute fluid width styling parameters across parent grid wrappers. ¦ Apply clear border colors to easily distinguish focus states from validation errors. |  | Implement strict client-side Input Masking on all template text area entry portals. | Audit all template text area entry portals across the application to create a complete inventory. | Scope Coverage / Audit Completeness | 80% of relevant items identified | 100% of relevant items identified and logged | 100% identified, logged, and cross-checked against spec | Complete (Scale: Complete/Partial/Not Complete) | World-class teams complete a full inventory before design work begins. Partial audits carry forward gaps that compound in later steps. | Fredrick | Template Name; Template Version; Template Type; Template Configuration; Creation Date; Created By; Creation Method; Initial Configuration; Object ID; Completion Status ('Complete (Scale: Complete/Partial/Not Complete)'); Action/Event Timestamp; User/Session ID | Data Required: Scope Coverage / Audit Completeness ¦¦ Configuration Data: Floor=80% of relevant items identified ¦ Optimal=100% of relevant items identified and logged ¦ Ceiling=100% identified, logged, and cross-checked against spec ¦¦ Implementation Data: Output field='Complete (Scale: Complete/Partial/Not Complete)'; Standard/Reference='World-class teams complete a full inventory before design work begins. Partial audits carry forward gaps that compound in later steps.' | 0 | No Dependency |  | First form primitive: client-side input masking - alphanumeric keystroke filter, regex block on unauthorised character sets, clipboard paste rejection past the field cap. Sits inside the core text area component that Steps 16-19 all decorate. | 16,17,18,19,20
16 | 16 - Input Primitive | 3205 | IS12-CSIVW-011-AS01 | IS12-CSIVW-011-AS01-A01 | Setup character formatting filters across text entry boxes. | Locate text entry box wrapper component in shared components directory. | Apply real-time input formatting layers to asset data form boxes. ¦ Restrict non-numeric keystrokes from mounting inside cost or dimension inputs. ¦ Display helpful validation message text lines right below active input cards. ¦ Unlock or freeze form confirmation keys based on field validation status. | ACTS | Step 28. | Interaction | Catches and fixes typing errors instantly at the source before incorrect data hits central servers. | Links text boxes directly to matching on-screen layouts (like numeric keys) to make entry comfortable. | Input boxes display clean green checks or clear red warning text directly beneath the typing box. | Atomic-level data fields: Step Execution ID; Execution Status; Execution Timestamp; Step Outcome; User ID ¦¦ No matched reference row in Setup Implementation master list — required data fields limited to atomic-level Data Collection Requirements only; standardized Mobile UX/UI & domain-expertise fields unavailable, verify manually. | Guides teams through detailed technical entries smoothly, preventing submission errors. | Form entries scale spaces dynamically to show inline description lines without crowding layout tools. | Display all text field validation messages using accessible text strings, never relying on color changes alone. | Self-formatting smart data entry text input (<ValidatedInputField>). | mobile-atomic-core-ui | Drastically cuts down server error logs by validating entries completely before sending data to APIs. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: 1.0 ¦ Row: 3205.0 | 5 Hours | Text field character formatting filters and validation rules. | Entering wrong data types triggers validation warnings instantly and blocks form submissions. | HC-IAM-0091. ¦ "Mobile-First & Responsive UX Google Material Design Decision: Position error text boxes directly below typing blocks to stay clear on narrow screens. | Position error text boxes directly below typing blocks to stay clear on narrow screens. | Add quick-clear "X" icons inside mobile text boxes to wipe out inputs in one tap. | Open helpful, detailed formatting guides inside floating boxes next to desktop text rows. | Organize complex input entries into structured multi-column forms across wide screens. | Front-end Component Engineer & Data Integrity Specialist. | Strip out trailing white spaces and weird symbols automatically from clipboard text when values are pasted. | Fields recheck validation criteria the second an error is edited, clearing warnings quickly once values pass rules. | Improves core database cleanliness significantly, lowering future engineering data cleaning bills. | Cuts out the frustration of filling out long forms only to have them rejected upon save clicks. | Add quick-clear "X" icons inside mobile text boxes to wipe out inputs in one tap. ¦ Open helpful, detailed formatting guides inside floating boxes next to desktop text rows. ¦ Organize complex input entries into structured multi-column forms across wide screens. |  | Setup character formatting filters across text entry boxes. | Locate text entry box wrapper component in shared components directory. | Asset & Component Discovery Completeness - Text entry box wrapper component shared | 90% of target assets confirmed present | 100% of target assets confirmed present | 100% (full inventory - no further discovery value beyond complete coverage) | Complete/Partial/Not Complete | Confirm the full inventory of the referenced files, components, or directories is located before any downstream configuration begins; partial discovery is the leading cause of rework later in the build. | Fredrick | Step Execution ID; Execution Status; Execution Timestamp; Step Outcome; User ID; Completion Status ('Complete/Partial/Not Complete'); Action/Event Timestamp; User/Session ID | Data Required: Asset & Component Discovery Completeness - Text entry box wrapper component shared ¦¦ Configuration Data: Floor=90% of target assets confirmed present ¦ Optimal=100% of target assets confirmed present ¦ Ceiling=100% (full inventory - no further discovery value beyond complete coverage) ¦¦ Implementation Data: Output field='Complete/Partial/Not Complete'; Standard/Reference='Confirm the full inventory of the referenced files, components, or directories is located before any downstream configuration begins; partial…' | 0 | No Dependency |  | Character formatting filters build directly on the mask from Step 15: real-time formatting, non-numeric keystroke restriction on cost and dimension fields, helper text under the input, and submit-key gating driven by field validation status. | 17,18,19,20
17 | 17 - Validation UX | 2490 | IS02-CSIVW-005-AS01 | IS02-CSIVW-005-AS01-A01 | Program dynamic inline error layouts to activate when input fields fail validation checks. | Locate the input field form validation component directory. | Bind custom inline error components to the blur events of core entry inputs. ¦ Lock message text strings to display in high-contrast red parameters directly below affected input containers. ¦ Program form frameworks to freeze submission actions if active errors are present. ¦ Run automated user boundary input tests to confirm clear error block display. | Real-Time Field Verification | Select the precise text size parameters required for inline descriptive error messages. | UX Flow | Eliminates confusing multi-step submission failures by correcting errors immediately at the individual field level. | Corrects data entries instantly on small mobile layouts, removing the need for heavy page reloads over weak connections. | Input elements display dynamic red warning text immediately when field conditions are violated. | Atomic-level data fields: Step Execution ID; Execution Status; Execution Timestamp; Step Outcome; User ID ¦¦ No matched reference row in Setup Implementation master list — required data fields limited to atomic-level Data Collection Requirements only; standardized Mobile UX/UI & domain-expertise fields unavailable, verify manually. | Users resolve entry mistakes instantly before moving deeper into form flows. | Management dashboard interfaces track submission error volumes clearly using active log metrics. | All error text placement rules must adhere strictly to central UI rules. | Inline error message logic scales uniformly across all data input fields. | Platform system universal form management package directory. | Field validation blocks corrupt data entries locally, keeping backend transaction metrics pristine. | Level 12 ¦ Phase: SETUP-12 ¦ Atomic Step: 1.0 ¦ Row: 2490.0 | 3 Hours | Active form layouts with real-time inline validation error displays. | Interface validation tests confirm that faulty inputs trigger immediate under-field red messages. | HC-SCH-0114. | Inline error layouts match Material 3 specifications to maximize structural visibility. | Typography configurations enforce crisp line height metrics to prevent readability clipping. | Layout components use relative parameters to scale across viewports fluidly. | Spatial gaps follow standard metric increments precisely. | Core Frontend Engineer / User Interaction Analyst. | Form submission actions remain physically locked until all active field errors are resolved. | High form field error volumes generate metrics updates on monitoring dashboards, prompting UX optimizations. | Maximizes user data accuracy across the entire pipeline, eliminating back-office manual cleanup costs. | Provides immediate guidance, ensuring a secure and transparent registration experience. | Inline error layouts match Material 3 specifications to maximize structural visibility. ¦ Typography configurations enforce crisp line height metrics to prevent readability clipping. ¦ Layout components use relative parameters to scale across viewports fluidly. ¦ Spatial gaps follow standard metric increments precisely. |  | Program dynamic inline error layouts to activate when input fields fail validation checks. | Locate the input field form validation component directory. | Asset & Component Discovery Completeness - Input field form validation component directory | 90% of target assets confirmed present | 100% of target assets confirmed present | 100% (full inventory - no further discovery value beyond complete coverage) | Complete/Partial/Not Complete | Confirm the full inventory of the referenced files, components, or directories is located before any downstream configuration begins; partial discovery is the leading cause of rework later in the build. | Fredrick | Step Execution ID; Execution Status; Execution Timestamp; Step Outcome; User ID; Completion Status ('Complete/Partial/Not Complete'); Action/Event Timestamp; User/Session ID | Data Required: Asset & Component Discovery Completeness - Input field form validation component directory ¦¦ Configuration Data: Floor=90% of target assets confirmed present ¦ Optimal=100% of target assets confirmed present ¦ Ceiling=100% (full inventory - no further discovery value beyond complete coverage) ¦¦ Implementation Data: Output field='Complete/Partial/Not Complete'; Standard/Reference='Confirm the full inventory of the referenced files, components, or directories is located before any downstream configuration begins; partial…' | 0 | No Dependency |  | Inline error layouts consume the validation status produced in Step 16. Binds error components to blur events, locks message text to high-contrast red under the affected input, and freezes form submission while errors are active. | 18,19,20
18 | 18 - Composition | 3073 | BPTR-0160 | BPTR-0160-A01 | Code and isolate mobile compound fields into distinct, standalone UI components featuring strict 48x48dp touch targets. | Identify all compound entry fields (e.g., split address blocks, combined date-time fields) in mobile views. |  | Technical Architecture Implementation | What specific data types have been assigned to the CDEs? | UX Flow | Physically eliminates data entry errors before they consume battery life to hit the network, ensuring the database only receives structured strings. | Context-aware mobile keyboards popping up automatically (e.g., dialpad for zip codes) saves thumb keystrokes and drastically speeds up form completion. | Form inputs physically block alphabetic characters when numeric is required. | Atomic-level data fields: Mobile Platform; OS Version; Device Type; Screen Dimensions; Mobile Configuration ¦¦ No matched reference row in Setup Implementation master list — required data fields limited to atomic-level Data Collection Requirements only; standardized Mobile UX/UI & domain-expertise fields unavailable, verify manually. | The system physically cannot accept a letter into a number field, eliminating post-submission frustration. | Clean data feeds into analytics dashboards without manual intervention. | Global Regex mapping per CDE applied to mobile text fields. | Regex Validation Module. | DCDF Lexicon / UDD. | N/A (Handled entirely at the edge). | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: 1.0 ¦ Row: 3073.0 | 2H | Coded Input Mask Components. | Invalid_Data_Type_Errors == 0. | HC-SCH-0008 | Contextual keyboard triggering for faster thumb typing. | Visual input masks (e.g., MM/DD/YYYY placeholders) inside the text field. | inputmode="numeric"; autocomplete="off"; | pattern="*"; min-width: 48px; | Mobile UI Development. | Mobile OS physically restricts keystrokes based on the inputmode attribute. | User cannot tap the submit button while the field is invalid, forcing them to fix their own typo instantly to proceed. |  |  |  | For Us: Zero time and compute power wasted on manual data cleansing pipelines. For Customer: Faster, error-free, thumb-optimized typing experiences. | Code and isolate mobile compound fields into distinct, standalone UI components featuring strict 48x48dp touch targets. | Identify all compound entry fields (e.g., split address blocks, combined date-time fields) in mobile views. | Field/Element Identification Accuracy | 95.0 | 99.0 | 100.0 | Pass (Scale: Pass/Fail) | Cross-check the identified list against the governing schema or UX inventory so no in-scope element is missed or wrongly included. | Fredrick | Mobile Platform; OS Version; Device Type; Screen Dimensions; Mobile Configuration; Completion Status ('Pass (Scale: Pass/Fail)'); Action/Event Timestamp; User/Session ID | Data Required: Field/Element Identification Accuracy ¦¦ Configuration Data: Floor=95 ¦ Optimal=99 ¦ Ceiling=100 ¦¦ Implementation Data: Output field='Pass (Scale: Pass/Fail)'; Standard/Reference='Cross-check the identified list against the governing schema or UX inventory so no in-scope element is missed or wrongly included.' | 0 | No Dependency |  | Compound fields (split address blocks, combined date-time) become standalone components. Needs all four preceding pieces at once: masking (15), filters (16), inline errors (17) and the 48x48dp touch bounds (14). Building it earlier means retrofitting each one. | 19,20
19 | 19 - Resilience | 3238 | REF-197 | REF-197-A01 | Developing the Safe Error-Handling UI Rollback Handler | Define standardized user-facing error text templates for common system validation rejections. | Build an error boundary wrapper around transactional forms to intercept system processing exceptions. ¦ Configure error log scrubbers to remove sensitive backend code path variables from user-facing logs. ¦ Wire up UI state controllers to fall back to generic, helpful confirmation notes when processing anomalies occur. ¦ Set up form storage managers to reset input sections back to verified local baseline states upon transaction failure. | Error management and secure application rollback frameworks. | Define standardized user-facing error text templates for common system validation rejections. | UX Flow | Hiding technical system logs prevents exposing database structure details, improving application security while keeping the interface clear for users. | Presenting simple, text-based error alerts fits mobile screens well and prevents breaking complex UI layouts when errors happen. | The application handles backend rejections gracefully, steering users away from broken states and showing clear recovery options. | Atomic-level data fields: Template Name; Template Version; Template Type; Template Configuration; Definition Name; Definition Parameters; Definition Type; Validation Status; Definition ID ¦¦ No matched reference row in Setup Implementation master list — required data fields limited to atomic-level Data Collection Requirements only; standardized Mobile UX/UI & domain-expertise fields unavailable, verify manually. | Keeps users from getting stuck on frozen screens when errors happen by offering clear ways to retry actions. | Error messages display in standard dialog view panels that stay neatly within mobile screen margins. | Use consistent error feedback models across all transactional interfaces. | Ensure the error handling boundary can wrap any data-aware component layout. | System Error Framework (@habot/error-rollback-boundary). | Streams detailed engineering error logs to centralized monitoring tools like Sentry for quick developer analysis. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: 1.0 ¦ Row: 3238.0 | 130 Minutes | A resilient error boundary module that manages transaction exceptions cleanly. | Confirm through testing that simulated server crashes result in clean, friendly alerts rather than system code traces. | HC-FE-0003, HC-DE-0033. | Ensure error text displays do not use technical code terms, keeping descriptions simple and clear. | Include an explicit, easy-to-tap retry button within error notification areas. | Use standard bottom sheet or dialog layout layers to present error feedback panels. | Assign prominent styling treatments to action controls inside error notice blocks. | Client-Side Exception Management, Application State Correction, and Informational Boundary Security Architecture. | Catch-all code structures strip out server-specific error language automatically before messages reach the UI layer. | Code reviews will flag any try-catch block that passes raw server error text directly to user interface components. | Protects system infrastructure details from accidental exposure while keeping frontend states stable during backend failures. | Replaces confusing technical error codes with simple, actionable steps to fix entries, reducing frustration. |  |  | Developing the Safe Error-Handling UI Rollback Handler | Define standardized user-facing error text templates for common system validation rejections. | Template Definition | Complete | Complete | Complete | Complete/Not Complete | Consistent error messaging. | Fredrick | Template Name; Template Version; Template Type; Template Configuration; Definition Name; Definition Parameters; Definition Type; Validation Status; Definition ID; Completion Status ('Complete/Not Complete'); Action/Event Timestamp; User/Session ID | Data Required: Template Definition ¦¦ Configuration Data: Floor=Complete ¦ Optimal=Complete ¦ Ceiling=Complete ¦¦ Implementation Data: Output field='Complete/Not Complete'; Standard/Reference='Consistent error messaging.' | 0 | No Dependency |  | The error boundary wraps the transactional forms built in Steps 15-18, scrubs sensitive backend paths from user-facing logs, and falls back to friendly copy when processing fails. Placed before the stepper so the stepper is wrapped as it is built, not retrofitted. | 20
20 | 20 - Composition | 3128 | FIEVR-033 | FIEVR-033-A01 | FIEVR-033 - Build Multi-Step Guided Carousel Layout Stepper | Review the complex data-entry process requiring stepwise decomposition. | Define step configuration paths inside localized form state machines ¦ Build an atomic horizontal stepper container under 20 lines of total functional code ¦ Program smooth transition animations to glide form steps left or right cleanly during navigation ¦ Code an integrated bottom layout progress dot row to show users their step counts instantly. | Core UI Components. | Group data entry fields logically across distinct layout steps. | Interaction. | Flooding a single mobile page with dozens of form inputs crowds views and causes form drop-offs. | Arranges long creation processes into bite-sized, single-screen segments built for mobile ergonomics. | Input fields sit inside clean, focused view cards, using progress bars and navigation buttons to guide users through steps. | Atomic-level data fields: Step Execution ID; Execution Status; Execution Timestamp; Step Outcome; User ID ¦¦ Mobile UX/UI design config required: Keep navigation actions easy to access with distinct next and back buttons. ¦ Highlight active step states with clear visual accents to show progress intuitively. ¦ Validate all inputs inside the current card before letting users slide to subsequent steps. ¦ Automatically close system keyboards during slide transitions to keep interfaces clean. ¦¦ Domain expertise/sign-off required: Frontend Component Workflow Architect. | Users fill out complex reports easily, focusing on clear input sets without getting overwhelmed by long pages. | Fits within dashboard modules, providing a clean framework for data entry fields. | Adhere strictly to Material Design 3 Stepper and Carousel guidelines. | Highly adaptable form container applied across onboarding guides and complex report submissions. | @habot-core/carousel-form-stepper. | Pipes completed form payloads directly to backend data endpoints upon step finalization. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: 1.0 ¦ Row: 3128.0 | 10 Hours. | Focused horizontal carousel form stepper with active validation integration. | Forms glide across steps cleanly in under 200ms, with progress indicator bars updating accurately. | HC-FE-0002, HC-FE-0004, HC-FE-0011, HC-FE-0024, HC-FE-0028. | Keep navigation actions easy to access with distinct next and back buttons. | Highlight active step states with clear visual accents to show progress intuitively. | Validate all inputs inside the current card before letting users slide to subsequent steps. | Automatically close system keyboards during slide transitions to keep interfaces clean. | Frontend Component Workflow Architect. | Saves entered inputs locally if an accidental view closure occurs, allowing users to resume entries instantly. | Testing routines check that validation errors block forward progress tracking loops across all form steps. | Systematic grouping of input fields preventing severe validation loop overlaps. DOCX+ 1 | Bite-sized progressive setup flows eliminating data entry fatigue. DOCX+ 1 |  |  | FIEVR-033 - Build Multi-Step Guided Carousel Layout Stepper | Review the complex data-entry process requiring stepwise decomposition. | Scope Coverage / Audit Completeness | 80% of relevant items identified | 100% of relevant items identified and logged in an inventory register | 100% identified, logged, and cross-checked against the design/architecture spec | Complete | World-class teams complete a full inventory before design work begins; partial audits (below 80%) risk missed edge cases downstream. | Fredrick | Step Execution ID; Execution Status; Execution Timestamp; Step Outcome; User ID; Completion Status ('Complete'); Action/Event Timestamp; User/Session ID | Data Required: Scope Coverage / Audit Completeness ¦¦ Configuration Data: Floor=80% of relevant items identified ¦ Optimal=100% of relevant items identified and logged in an inventory register ¦ Ceiling=100% identified, logged, and cross-checked against the design/architecture spec ¦¦ Implementation Data: Output field='Complete'; Standard/Reference='World-class teams complete a full inventory before design work begins; partial audits (below 80%) risk missed edge cases downstream.' | 0 | No Dependency |  | The highest-level composition in this batch: a multi-step guided carousel stepper. Consumes the motion tokens (11-12), the validated inputs (15-18) and the error boundary (19). Deliberately last - it is the only step that needs everything else to exist first. | -