## Read Me
How this sheet was built
Source | My stepsFN06082026.xlsx -> "Fredrick" tab (1,314 steps assigned to you)
Selection rule | Only steps where Dependency Count = 0 and Dependency (Atomic Step Serial No) = "No Dependency".
682 of your 1,314 steps qualify. All 10 chosen below are from that pool.
Why this matters | Of your 1,314 steps, 632 carry a dependency, and only 53 of those dependencies resolve to another step in
your own sheet. The rest point at rows owned by other team members. Starting on a dependent step would
block you on someone else. Every step here can be started today, in any order, without waiting on anyone.
Ordering rule | Foundation-first build logic: framework install -> design tokens -> theme modes -> grid decision ->
grid build -> layout engine -> layout shell -> navigation -> interaction standards.
The steps have no hard dependency on each other, but building in this order means no rework:
each step consumes the artefact the previous one produced.
Columns | All 49 original columns are preserved, in their original order and with their original values.
Four columns were ADDED (shaded pale yellow): Implementation Order, Build Layer,
Why This Position In The Sequence, and Blocks (Steps That Need This).
Total effort | Approximately 6.5 working days of engineering time across the 10 steps.

## Build Sequence Summary
# | Build Layer | Global Ref ID | Atomic Step Ref ID | Setup Step (Action) | Est. Time | Dependency Count | Original S. No | Why This Position In The Sequence
1 | 1 - Framework Install | TTMCS-001 | TTMCS-001-A01 | Install and configure the verified Material 3 layout component framework within frontend client packages. | 5 Hours | 0 | 1797 | Nothing else can be built until the approved Material 3 component library is installed and the global theme adapter is instantiated. This is the only step that has no software prerequisite of any kind.
2 | 2 - Design Tokens | RCGLA-001 | RCGLA-001-A01 | Build global corporate style token variables inside the mobile client framework. | 5 Hours | 0 | 3227 | Tokens (colour, typography, spacing, elevation, iconography) must exist before any component is styled. Placed straight after the framework install because the token map is written INTO the theme adapter created in Step 1.
3 | 3 - Theme Modes | TTMCS-004 | TTMCS-004-A01 | TTMCS-004 — Configure Atomic Light/Dark Adaptation Tokens | 5 Hours. | 0 | 1654 | Light/dark adaptation tokens extend the base token set from Step 2. Doing this now avoids a second pass over every component later to retrofit dark mode.
4 | 4 - Theme Modes | TTMCS-005 | TTMCS-005-A01 | TTMCS-005 — Mobile Dark Mode Contrast Enforcement | 5 Hrs | 0 | 3139 | Dark-mode surface elevation and contrast enforcement completes the theming layer started in Step 3. Both TTMCS steps ship together so WCAG AA contrast is verified once, not twice.
5 | 5 - Grid Decision | SSTLA-004 | SSTLA-004-A01 | Define the exact base breakpoint, column count, fluid margin, and gutter widths for the core mobile experience before scaling upward to tablet or desktop views. | 4 Hours | 0 | 169 | A pure decision/specification step: fixes breakpoints, column count, margins and gutters. It produces the JSON token file that Steps 6 and 7 consume, so it must precede any grid code.
6 | 6 - Grid Build | RCGLA-012 | RCGLA-012-A01 | RCGLA-012 - Initialize Atomic Grid System & Mobile Viewport Constraints | 4 Hours. | 0 | 345 | First grid code. Implements the breakpoints agreed in Step 5 as the MobileGridContainer plus viewport meta tags and build-time linting against hardcoded pixels.
7 | 7 - Layout Engine | RCGLA-032 | RCGLA-032-A01 | RCGLA-032 - Configure the Material Design 3 (MD3) adaptive 4-column fluid layout token engine for mobile screens. | 6 Hours | 0 | 3051 | Configures the MD3 adaptive 4-column fluid layout token engine on top of the grid container from Step 6. Reuses the 16px margin/gutter profile fixed in Step 5.
8 | 8 - Layout Shell | RCGLA-018 | RCGLA-018-A01 | RCGLA-018 - Universal Master Layout Architecture for React Components | 3 Hours. | 0 | 356 | The universal master layout wrapper that every page uses. It can only lock dimensions once the grid (Step 6) and layout token engine (Step 7) exist to lock them against.
9 | 9 - Navigation | ANSA-012 | ANSA-012-A01 | Establish Contextual Navigation Header Framework. | 1 Day. | 0 | 4 | The contextual navigation header is the first real UI surface. It sits inside the master layout wrapper from Step 8 and consumes the tokens from Steps 2-4.
10 | 10 - Interaction Std | TTMAC-011 | TTMAC-011-A01 | Touch-Target Optimization Framework Setup (48×48 dp Minimum Interaction Nodes). | 6 Hours. | 0 | 3095 | Touch-target framework (48x48dp minimum) is applied to the interactive elements that now exist - the header actions from Step 9 being the first. Setting it last means the rule is enforced against real components rather than in the abstract.

## First 10 - Build Order
Implementation Order | Build Layer | S. No | Global Reference ID | Atomic Steps Reference ID | Setup Step (Action) | Setup Step Description | 4 Substeps | Decision Group | Decision to be Made Before Setup Step | Decision Category | Why This Matters | Mobile App First Implication | UX Translation | Data Requirement | User Interaction / Flow Impact | Dashboard / Interface Implication | What Standardized Must Be Done | Atomic Reusability | Common Library to Store | GCP / BigQuery Alignment | Sequence Order | Estimated Time Required | Expected Output | Completion Measures | Dependencies | Mobile-First & Responsive UX Google Material Design Decision | Mobile-First & Responsive UI Google Material Design Decision | Mobile-First & Responsive UX Google Material Design Implementation | Mobile-First & Responsive UI Google Material Design Implementation | Domain Expertise Needed | Mistake-Proofing (Poka-Yoke) | Self-Chasing | What Creates Vitality & Prosperity For Us | What Creates Vitality & Prosperity For the Customer | Responsive UX/UI Design | Vitality & Prosperity (VAP) | Setup Step (Action).1 | Atomic Step | Metric Name | Floor Boundary | Optimal Target | Ceiling Boundary | Best Qualitative Output | Best Qualitative/Quantitative Output Type | Assigned Team Member | Data Collected by System | Required Data / Configuration / Implementation Fields (from AL-AQ Analysis) | Dependency Count | Dependency (Atomic Step Serial No) | Output format | Why This Position In The Sequence | Blocks (Steps That Need This)
1 | 1 - Framework Install | 1797 | TTMCS-001 | TTMCS-001-A01 | Install and configure the verified Material 3 layout component framework within frontend client packages. | Verify the version of the Material 3 component library to be installed — confirm it is the approved version. | Add the modern design library package framework to the project development dependencies. ¦ Instantiate the global theme configuration adapter at the web layout layer. ¦ Configure global fluid containers that reflow components dynamically based on screen widths. ¦ Run automated interface rendering tests to confirm uniform component appearance across target device emulators. | Frontend Styling Foundation | Select the baseline component elevation variables required for interactive layer containers. | UX Flow | Standardizes user interaction components, completely removing inconsistent local layout style configurations across development teams. | Ensures that the core layout engine prioritizes compact layout spaces natively before scaling up to larger viewports. | Renders clean adaptive navigation containers that transition smoothly between mobile view classes. | Atomic-level data fields: Library Name; Library Version; Component Count; Installation Status; Dependency List; Library Location Path ¦¦ Mobile UX/UI design config required: Sidebar navigation components auto-collapse smoothly on screen layout sizes under 768px. ¦ UI page frames apply subtle dynamic linear gradients (#F2F6F9 to #EEF2F6) to minimize user reading strain. ¦ Component container borders match rigid brand theme rules precisely. ¦ Layout structures enforce strict vertical component stacks on phone profiles. ¦¦ Domain expertise/sign-off required: Lead Frontend Engineer / Mobile UI Specialist. | App navigation feels predictable and easy to learn across different sections of the digital portal. | Administrative interfaces maintain clean card blocks aligned to structured information hierarchies. | All custom user interfaces must use pre-verified design tokens explicitly. | The styling foundation acts as the universal blueprint for all forthcoming page assets. | Shared frontend platform system design package module. | Dynamic styling elements load locally to minimize structural API query delays during interface initial render tracks. | Level 3 ¦ Phase: SETUP-03 ¦ Atomic Step: 1.0 ¦ Row: 1797.0 | 5 Hours | An enforced global Material 3 design system framework styling interface view layers natively. | Frontend component rendering checks confirm 100% compliance with corporate token definitions. | HC-SCH-0079. | Sidebar navigation components auto-collapse smoothly on screen layout sizes under 768px. | UI page frames apply subtle dynamic linear gradients (#F2F6F9 to #EEF2F6) to minimize user reading strain. | Component container borders match rigid brand theme rules precisely. | Layout structures enforce strict vertical component stacks on phone profiles. | Lead Frontend Engineer / Mobile UI Specialist. | Frontend style check sweeps block project compilation steps if local code scripts introduce standalone CSS layout code. | Layout alignment discrepancies trigger formatting tool rejections, prompting developers to match system tokens immediately. | Speeds up frontend design delivery times by leveraging a predictable, highly reusable component ecosystem. | Delivers a crisp, modern user experience that behaves smoothly across all portable platforms. | Sidebar navigation components auto-collapse smoothly on screen layout sizes under 768px. ¦ UI page frames apply subtle dynamic linear gradients (#F2F6F9 to #EEF2F6) to minimize user reading strain. ¦ Component container borders match rigid brand theme rules precisely. ¦ Layout structures enforce strict vertical component stacks on phone profiles. |  | Install and configure the verified Material 3 layout component framework within frontend client packages. | Verify the version of the Material 3 component library to be installed — confirm it is the approved version. | Business Rule / Threshold Definition Coverage | 90% of rules formally defined | 100% of rules formally defined and peer-reviewed | 100% of rules defined, reviewed, and versioned in approved spec | Complete (Scale: Complete/Partial/Not Complete) | Threshold values must be sourced from an approved policy document, not hardcoded assumptions. Peer review is required before the definition is locked. | Fredrick | Library Name; Library Version; Component Count; Installation Status; Dependency List; Library Location Path; Completion Status ('Complete (Scale: Complete/Partial/Not Complete)'); Action/Event Timestamp; User/Session ID | Data Required: Business Rule / Threshold Definition Coverage ¦¦ Configuration Data: Floor=90% of rules formally defined ¦ Optimal=100% of rules formally defined and peer-reviewed ¦ Ceiling=100% of rules defined, reviewed, and versioned in approved spec ¦¦ Implementation Data: Output field='Complete (Scale: Complete/Partial/Not Complete)'; Standard/Reference='Threshold values must be sourced from an approved policy document, not hardcoded assumptions. Peer review is required before the definition is locked.' | 0 | No Dependency |  | Nothing else can be built until the approved Material 3 component library is installed and the global theme adapter is instantiated. This is the only step that has no software prerequisite of any kind. | 2,3,4,7,8,9,10
2 | 2 - Design Tokens | 3227 | RCGLA-001 | RCGLA-001-A01 | Build global corporate style token variables inside the mobile client framework. | Gather all brand identity assets — color palette, typography, spacing, iconography, elevation. | * Map semantic spacing constants (e.g., margins, paddings, column gaps) inside theme configurations. * Implement an adaptive 4-column layout matrix optimized for compact smartphone screens. * Code standardized element elevation levels and background shadow weight variables. * Test design asset consistency behaviors across distinct local device viewport resolutions. | Material Design Component Systems | The exact primary corporate theme colors matching accessibility contrast rules. | UX Flow & Component Layout | Prevents design fragmentation and chaotic, custom interface variations that smash user muscle memory patterns. | Central token classes ensure styling metrics remain tiny, reducing terminal application compilation payload sizes. | Layout grids reflow dynamically, displaying crisp, proportional interfaces across diverse smartphone screen form factors. | Atomic-level data fields: Font Name; Font Size; Line Height; Font Weight; Font File Path ¦¦ Domain expertise/sign-off required: Mobile UI Engineering & Google Material Design 3 Implementation. | Explicit touch target areas guarantee tap action precision, preventing frustrating layout mis-clicks. | Monitoring screens show design verification consistency metrics across deployment tracks safely. | Layout structures must utilize standard tokens imported from the core UI framework package exclusively. | Every token class functions as an abstract styling brick reusable across all form elements. | Private package module folder location named universal_library/ui/theme/tokens.json. | Matches client-side layout rules with automated interface delivery pipelines smoothly. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: 1.0 ¦ Row: 3227.0 | 5 Hours | An audited, production-ready mobile layout design token matrix. | Continuous integration code verification pipelines report zero instances of hardcoded hex colors or spacing values. | HC-PAD-0001 must be complete to ensure validation elements incorporate token spacing rules. * Mobile-First & Responsive UX Decision: Enforce rigid layout column rules to establish consistent structural information hierarchy paths. * Mobile-First & Responsive UI Decision: Apply forced 8dp baseline grid steps across structural spacing metrics. * Mobile-First & Responsive UX Implementation: Build screen elements utilizing adaptive, flexible container blocks. * Mobile-First & Responsive UI Implementation: Disable manual style choices on individual views to protect layout integrity standards. |  |  |  |  | Mobile UI Engineering & Google Material Design 3 Implementation. | Style repository checks automatically fail if layout padding variables use non-standard grid intervals. | Bad styling definitions trigger layout checker alerts, forcing front-end teams to align variables to pass deployments. |  |  |  | For Us: Rapid frontend feature iteration loops driven by highly uniform visual styling patterns. For Customer: Visually restful, clean interfaces that eliminate data entry confusion completely. | Build global corporate style token variables inside the mobile client framework. | Gather all brand identity assets — color palette, typography, spacing, iconography, elevation. | Scope Coverage / Audit Completeness | 80% of relevant items identified | 100% of relevant items identified and logged | 100% identified, logged, and cross-checked against spec | Complete (Scale: Complete/Partial/Not Complete) | World-class teams complete a full inventory before design work begins. Partial audits carry forward gaps that compound in later steps. | Fredrick | Font Name; Font Size; Line Height; Font Weight; Font File Path; Completion Status ('Complete (Scale: Complete/Partial/Not Complete)'); Action/Event Timestamp; User/Session ID | Data Required: Scope Coverage / Audit Completeness ¦¦ Configuration Data: Floor=80% of relevant items identified ¦ Optimal=100% of relevant items identified and logged ¦ Ceiling=100% identified, logged, and cross-checked against spec ¦¦ Implementation Data: Output field='Complete (Scale: Complete/Partial/Not Complete)'; Standard/Reference='World-class teams complete a full inventory before design work begins. Partial audits carry forward gaps that compound in later steps.' | 0 | No Dependency |  | Tokens (colour, typography, spacing, elevation, iconography) must exist before any component is styled. Placed straight after the framework install because the token map is written INTO the theme adapter created in Step 1. | 3,4,8,9,10
3 | 3 - Theme Modes | 1654 | TTMCS-004 | TTMCS-004-A01 | TTMCS-004 — Configure Atomic Light/Dark Adaptation Tokens | Set up standard Material Design 3 dynamic color tokens. | Set up standard Material Design 3 dynamic color tokens using unified root CSS custom properties ¦ Write an atomic preference hook listening directly to browser system dark preferences ¦ Build a performance-optimized theme container that switches modes cleanly without triggering full component reflows ¦ Implement explicit accessibility contrast-checking workflows mapping directly to WCAG AA mobile layout rules. | UI Layout Foundation. | Determine precise brand-approved color hex codes across both light and dark operational profiles. | Interaction. | High ambient sunlight demands high-contrast light layouts, whereas low-light night conditions require deep dark interfaces to protect user vision and maximize mobile battery cycles. | Directly reduces mobile display energy footprints, extending phone uptime for long-duration field users. | Dynamic color shifts preserve visual component hierarchies perfectly across all screen brightness variations. | Atomic-level data fields: Color Code (HEX/RGB); Color Name; Color Scheme; Contrast Ratio; Color Application Map ¦¦ Mobile UX/UI design config required: Utilize structural elevation overlays instead of deep drop shadows to indicate component layering in dark configurations. ¦ Enforce primary text contrast levels checking out above WCAG AA standard mobile parameters. ¦ Map semantic tokens clearly to avoid mixing up distinct component background definitions. ¦ Apply transition timing configurations smoothly over layout styling adjustments. ¦¦ Domain expertise/sign-off required: UI Designer / CSS Specialist. | Users experience an instantaneous, cohesive theme shift that requires zero manually triggered application configurations. | Charts and data tables dynamically invert backgrounds while maintaining clean label contrast boundaries. | strict adoption of Material Design 3 color system distribution matrices. | Every visible surface component references these fundamental color tokens. | @habot-core/theme-tokens. | Log user color format metrics across individual sessions to drive localized presentation optimization strategies. | Level 2 ¦ Phase: SETUP-02 ¦ Atomic Step: 1.0 ¦ Row: 1654.0 | 5 Hours. | Extensively documented Material token map matching English Code specifications perfectly. | Automated verification confirming a minimum 4.5:1 contrast ratio across all dynamic layout color pairs. | HC-FE-0002. | Utilize structural elevation overlays instead of deep drop shadows to indicate component layering in dark configurations. | Enforce primary text contrast levels checking out above WCAG AA standard mobile parameters. | Map semantic tokens clearly to avoid mixing up distinct component background definitions. | Apply transition timing configurations smoothly over layout styling adjustments. | UI Designer / CSS Specialist. | Style builders throw compilation errors if raw, untokenized hex codes find their way into layout sheets. | Visual regression suites automatically compare light and dark snapshots on every single pull request pipeline run. | Brand consistency across all lighting conditions with unified token management. | Eye comfort in low light and extended battery life on OLED mobile screens. |  |  | TTMCS-004 — Configure Atomic Light/Dark Adaptation Tokens | Set up standard Material Design 3 dynamic color tokens. | Material Design Density Compliance (dp) | 4dp minimum spacing (Material Design accessibility floor) | 6–8dp padding / 32–48dp row height (Material Design dense-table optimum) | 12dp (maximum density before readability/touch-target risk) | Good / Average / Poor | Google Material Design guidelines set minimum spacing/touch-target thresholds for dense data tables; density above the ceiling risks accessibility and tap-accuracy failures. | Fredrick | Color Code (HEX/RGB); Color Name; Color Scheme; Contrast Ratio; Color Application Map; Completion Status ('Good / Average / Poor'); Action/Event Timestamp; User/Session ID | Data Required: Material Design Density Compliance (dp) ¦¦ Configuration Data: Floor=4dp minimum spacing (Material Design accessibility floor) ¦ Optimal=6–8dp padding / 32–48dp row height (Material Design dense-table optimum) ¦ Ceiling=12dp (maximum density before readability/touch-target risk) ¦¦ Implementation Data: Output field='Good / Average / Poor'; Standard/Reference='Google Material Design guidelines set minimum spacing/touch-target thresholds for dense data tables; density above the ceiling risks accessibility…' | 0 | No Dependency |  | Light/dark adaptation tokens extend the base token set from Step 2. Doing this now avoids a second pass over every component later to retrofit dark mode. | 4,9
4 | 4 - Theme Modes | 3139 | TTMCS-005 | TTMCS-005-A01 | TTMCS-005 — Mobile Dark Mode Contrast Enforcement | Define surface elevation tokens for dark mode. | Surface elevation tokens ¦ Text contrast thresholds ¦ Brand color adjustments ¦ System theme listeners. | Mobile UI | Theming Engine | Data Visualization | Adapts dynamically to real-world ambient conditions while unlocking massive power optimization vectors for OLED mobile hardware. |  | Adaptive layout inversions that map to client environment choices. Preference tracking variables pass to BigQuery to audit active dark mode adaptation rates. | Atomic-level data fields: Definition Name; Definition Parameters; Definition Type; Validation Status; Definition ID ¦¦ Mobile UX/UI design config required: Layered surface elevations , baseline dark configurations , semantic theme coloring , Material Dark Theme compliance rules. ¦¦ Domain expertise/sign-off required: UI Design. |  |  |  | Centralized design token parameters managed by a Theme Provider Component stored in the UI Core Lib. |  | N/A (Native edge environment states). | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: 1.0 ¦ Row: 3139.0 | 5 Hrs | CSS Token Variables |  | 6.0 |  |  | Layered surface elevations , baseline dark configurations , semantic theme coloring , Material Dark Theme compliance rules. |  | UI Design. | Build validation blocks compilation if color ratios test below a hard 4.5:1 ratio threshold. Automated validation dashboards chase design leads to remediate non-compliant values. |  | Seamless compliance with global accessibility regulations | Clear, painless app usability in intense sunlight or pitch-black spaces. |  |  | TTMCS-005 — Mobile Dark Mode Contrast Enforcement | Define surface elevation tokens for dark mode. | WCAG Colour Contrast Ratio | 4.5:1 (WCAG 2.1 Level AA minimum for normal text) | 7:1 (WCAG 2.1 Level AAA target) | No upper bound required — avoid glare/over-contrast beyond 21:1 | Pass / Fail | WCAG 2.1 accessibility standard sets 4.5:1 as the legal-minimum floor and 7:1 as the AAA optimum for readability in both light and dark modes. | Fredrick | Definition Name; Definition Parameters; Definition Type; Validation Status; Definition ID; Completion Status ('Pass / Fail'); Action/Event Timestamp; User/Session ID | Data Required: WCAG Colour Contrast Ratio ¦¦ Configuration Data: Floor=4.5:1 (WCAG 2.1 Level AA minimum for normal text) ¦ Optimal=7:1 (WCAG 2.1 Level AAA target) ¦ Ceiling=No upper bound required — avoid glare/over-contrast beyond 21:1 ¦¦ Implementation Data: Output field='Pass / Fail'; Standard/Reference='WCAG 2.1 accessibility standard sets 4.5:1 as the legal-minimum floor and 7:1 as the AAA optimum for readability in both light and dark modes.' | 0 | No Dependency |  | Dark-mode surface elevation and contrast enforcement completes the theming layer started in Step 3. Both TTMCS steps ship together so WCAG AA contrast is verified once, not twice. | 9
5 | 5 - Grid Decision | 169 | SSTLA-004 | SSTLA-004-A01 | Define the exact base breakpoint, column count, fluid margin, and gutter widths for the core mobile experience before scaling upward to tablet or desktop views. | Collate cross-device screen resolution metrics for target mobile, tablet, and desktop viewports. |  | UI/UX Baseline Configuration (Google Material Design System Alignment) |  | Interaction | Eliminates arbitrary layout configurations across team members, preventing viewport overflow bugs and ensuring absolute layout consistency across varying mobile viewports. | Forces developers to build layouts optimized natively for one-handed thumb interaction ranges before scaling out to expansive screen resolutions. |  | Atomic-level data fields: Mobile Platform; OS Version; Device Type; Screen Dimensions; Mobile Configuration ¦¦ No matched reference row in Setup Implementation master list — required data fields limited to atomic-level Data Collection Requirements only; standardized Mobile UX/UI & domain-expertise fields unavailable, verify manually. | Prevents accidental visual clipping of primary Call-to-Actions (CTAs) on tight displays, reducing interaction friction. |  |  |  |  | Event-driven streaming of real-time window resizing occurrences to monitor responsive layout health dynamically. | Level 10 ¦ Phase: SETUP-10 ¦ Atomic Step: 1.0 ¦ Row: 169.0 | 4 Hours | Approved JSON Token File and an interactive structural layout wireframe for compact mobile devices. |  | None. | [5 empty] | Auto-rejection of any pull request containing hardcoded pixel layout values via rigid Stylelint/ESLint AST parsing checks. | An autonomous pre-commit script screens layout properties, compiling an alert log to the UI team Slack channel if arbitrary media queries are declared. |  |  |  |  | Define the exact base breakpoint, column count, fluid margin, and gutter widths for the core mobile experience before scaling upward to tablet or desktop views. | Collate cross-device screen resolution metrics for target mobile, tablet, and desktop viewports. | Task Execution Quality Score (1-5 scale) — Collate cross-device screen resolution metrics for target | 3.5 | 4.5 | 5.0 | Good/Average/Poor | General benchmark drawn from PMI/Agile execution-quality norms where output quality is scored by a reviewer against a defined rubric. | Fredrick | Mobile Platform; OS Version; Device Type; Screen Dimensions; Mobile Configuration; Completion Status ('Good/Average/Poor'); Action/Event Timestamp; User/Session ID | Data Required: Task Execution Quality Score (1-5 scale) — Collate cross-device screen resolution metrics for target ¦¦ Configuration Data: Floor=3.5 ¦ Optimal=4.5 ¦ Ceiling=5 ¦¦ Implementation Data: Output field='Good/Average/Poor'; Standard/Reference='General benchmark drawn from PMI/Agile execution-quality norms where output quality is scored by a reviewer against a defined rubric.' | 0 | No Dependency |  | A pure decision/specification step: fixes breakpoints, column count, margins and gutters. It produces the JSON token file that Steps 6 and 7 consume, so it must precede any grid code. | 6,7
6 | 6 - Grid Build | 345 | RCGLA-012 | RCGLA-012-A01 | RCGLA-012 - Initialize Atomic Grid System & Mobile Viewport Constraints | Open the @habot-core/mobile-layout-system library package. | Define layout breakpoints in the common library configuration (xs: 0px, sm: 600px) ¦ Configure HTML Meta viewport tags to disallow user-scalable zooming ¦ Build a pure MobileGridContainer React component restricted to 20 lines ¦ Implement automated build-time linting to flag hardcoded pixel values. | UI Layout Foundation. | Absolute baseline breakout metrics for viewport constraints and target base font scaling. | UX Flow. | Setting up the grid dynamically controls how structural components snap into position. Getting this wrong results in unpredictable horizontal scrolling. | Forces a lightweight 4-column layout layout strategy, dropping performance payloads by avoiding heavy multi-breakpoint responsive calculation evaluations on lower-end mobile CPUs. | Formulates predictable screen layouts using standard 16px fluid outer margins and a continuous 8px vertical rhythm rhythm alignment. | Atomic-level data fields: Layout Type; Layout Grid Dimensions; Spacing Rules; Alignment Settings; Layout Validation Status ¦¦ Mobile UX/UI design config required: Define mobile margin standardations explicitly at 16px with an 8px gutter grid system. ¦ Adopt component scale metrics mapping directly to touch-safe Material UI tokens. ¦ Restrict layout viewport structural compositions strictly to the 4-column layout layer. ¦ Implement CSS Flexbox systems that wrap dynamically when screen space becomes highly constrained. ¦¦ Domain expertise/sign-off required: Senior Frontend / Mobile UI Architect. | Eradicates unpredictable layout shifting (CLS) during heavy API hydration sequences. | Automatically renders clean stacked dashboards designed exclusively for thumb navigation patterns. | Strict adoption of Material Design 3 adaptive design paradigms. | High. Every single visual UI view component inherits from this core container layout wrapper. | @habot-core/mobile-layout-system. | Event-driven telemetry captures viewport resolution variations instantly via real-time stream processing. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: 1.0 ¦ Row: 345.0 | 4 Hours. | Pure MobileGridContainer component codebase along with its semantic English Code specification sheet. | Zero instances of horizontal scrollbars across simulated iPhone SE, 14 Pro, and Pixel devices. Cumulative Layout Shift (CLS) scores tracking strictly under 0.05. | None. This serves as the system foundational layout block. | Define mobile margin standardations explicitly at 16px with an 8px gutter grid system. | Adopt component scale metrics mapping directly to touch-safe Material UI tokens. | Restrict layout viewport structural compositions strictly to the 4-column layout layer. | Implement CSS Flexbox systems that wrap dynamically when screen space becomes highly constrained. | Senior Frontend / Mobile UI Architect. | Build validation rules directly into the Webpack/Vite pipeline that immediately break compilation tasks if outer layout wrappers contain hardcoded fixed pixel widths over 360px. | Automated integration testing scripts spin up headless Chromium mobile browsers on every Git commit, scanning programmatic layouts for unexpected out-of-bounds component overflow elements. | Standardization reduces technical debt and maintenance ease by enforcing a unified, mobile-first grid. | Guaranteed responsive layouts and eliminated horizontal scrolling build long-term trust in UI stability. |  |  | RCGLA-012 - Initialize Atomic Grid System & Mobile Viewport Constraints | Open the @habot-core/mobile-layout-system library package. | Asset/Resource Location & Access Confirmation | 0.8 | 0.95 | 1.0 | Pass/Fail | The target resource should be reachable from one authoritative, documented location; ad-hoc or memorised paths are a floor-level practice that should be upgraded to a referenced source of truth. | Fredrick | Layout Type; Layout Grid Dimensions; Spacing Rules; Alignment Settings; Layout Validation Status; Completion Status ('Pass/Fail'); Action/Event Timestamp; User/Session ID | Data Required: Asset/Resource Location & Access Confirmation ¦¦ Configuration Data: Floor=0.8 ¦ Optimal=0.95 ¦ Ceiling=1 ¦¦ Implementation Data: Output field='Pass/Fail'; Standard/Reference='The target resource should be reachable from one authoritative, documented location; ad-hoc or memorised paths are a floor-level practice that should…' | 0 | No Dependency |  | First grid code. Implements the breakpoints agreed in Step 5 as the MobileGridContainer plus viewport meta tags and build-time linting against hardcoded pixels. | 7,8
7 | 7 - Layout Engine | 3051 | RCGLA-032 | RCGLA-032-A01 | RCGLA-032 - Configure the Material Design 3 (MD3) adaptive 4-column fluid layout token engine for mobile screens. | Open the private core layout shell package @habot-connect/layout-shell. | Define global system layout properties with a 16px outer margin and a 16px column gutter spacing profile Operationalizing System Architecture Design]. Implement an automated viewport listener that flags any element trying to split into more than 4 vertical segments on mobile viewports. Wrap all application view components inside a global layout boundary container component Operationalizing System Architecture Design]. Write automatic viewport-testing checks to evaluate layout rendering across common compact resolutions (360px, 375px, and 412px). | Frontend System Baseline. | Determine whether columns should stretch symmetrically or use asymmetrical layouts for specific data entry features. | UX Flow / Dashboard. | It guarantees that multi-column desktop layouts cleanly scale down into a single functional column on mobile, preventing broken text strings and horizontal scrolling. | Forces developers to build interfaces optimized for single-axis thumb-scrolling up front instead of treating small screens as an afterthought. | Elements scale smoothly across diverse mobile viewports without drifting out of visual bounds or clipping interactive buttons. | Atomic-level data fields: Layout Type; Layout Grid Dimensions; Spacing Rules; Alignment Settings; Layout Validation Status ¦¦ Mobile UX/UI design config required: Follow MD3 compact window-size class guidelines explicitly. ¦ Utilize the standardized layout margin system token parameters (16px gutter spacing alignment). ¦ Set container dimensions using relative CSS percentages to ensure fluid elasticity across diverse aspect ratios. ¦ Bind structural grid items with automatic wrapping styling parameters (flex-wrap: wrap). ¦¦ Domain expertise/sign-off required: Senior UI/UX Front-End Layout Engineer. | Users scroll through interface forms in a predictable top-to-bottom pattern, speeding up data input loops. | Analytical charts stack into a clean, single-column dashboard layout on mobile screens instead of multi-column side-by-side grids Operationalizing System Architecture Design]. | All sub-feature layouts must wrap within the unified responsive grid component layout. | High; this foundational layout grid structure handles 100% of visible interface layouts. | Private core layout shell package (@habot-connect/layout-shell). | Viewport configuration data is appended to telemetry traces to track layout render health across diverse mobile devices Operationalizing System Architecture Design]. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: 1.0 ¦ Row: 3051.0 | 6 Hours | Responsive grid system asset deployed and verified across target device simulations. | Zero instances of horizontal scrollbars or overflowing design tokens on screens down to 320px width. | HC-DE-0274 Universal Mobile Component Registry Initialization. Mobile-First & Responsive UX Google Material Design Decision: Follow MD3 compact window-size class guidelines explicitly. Mobile-First & Responsive UI Google Material Design Decision: Utilize the standardized layout margin system token parameters (16px gutter spacing alignment). Mobile-First & Responsive UX Google Material Design Implementation: Set container dimensions using relative CSS percentages to ensure fluid elasticity across diverse aspect ratios. Mobile-First & Responsive UI Google Material Design Implementation: Bind structural grid items with automatic wrapping styling parameters (flex-wrap: wrap). Domain expertise needed to implement this step: Senior UI/UX Front-End Layout Engineer. Mistake-Proofing (Poka-Yoke): The core CSS compilation step automatically inserts max-width: 100vw and hides horizontal overflow to make accidental side-scrolling physically impossible. Self-Chasing: Automated styling check scripts scan pull requests; if a file specifies absolute layout widths in pixels instead of relative percentages, the deployment pipeline blocks the build. Vitality & Prosperity (VAP): What creates VAP for us: Reduces layout-related bug tickets across teams, speeding up feature delivery times. What creates VAP for the customer: Offers a responsive mobile experience that works flawlessly on budget smartphones and premium devices alike. | Follow MD3 compact window-size class guidelines explicitly. | Utilize the standardized layout margin system token parameters (16px gutter spacing alignment). | Set container dimensions using relative CSS percentages to ensure fluid elasticity across diverse aspect ratios. | Bind structural grid items with automatic wrapping styling parameters (flex-wrap: wrap). | Senior UI/UX Front-End Layout Engineer. |  |  | Reduces layout-related bug tickets across teams, speeding up feature delivery times. | Offers a responsive mobile experience that works flawlessly on budget smartphones and premium devices alike. |  |  | RCGLA-032 - Configure the Material Design 3 (MD3) adaptive 4-column fluid layout token engine for mobile screens. | Open the private core layout shell package @habot-connect/layout-shell. | Asset/Resource Location & Access Confirmation | 4dp | 8dp | 16dp | Pass/Fail | The target resource should be reachable from one authoritative, documented location; ad-hoc or memorised paths are a floor-level practice that should be upgraded to a referenced source of truth. | Fredrick | Layout Type; Layout Grid Dimensions; Spacing Rules; Alignment Settings; Layout Validation Status; Completion Status ('Pass/Fail'); Action/Event Timestamp; User/Session ID | Data Required: Asset/Resource Location & Access Confirmation ¦¦ Configuration Data: Floor=4dp ¦ Optimal=8dp ¦ Ceiling=16dp ¦¦ Implementation Data: Output field='Pass/Fail'; Standard/Reference='The target resource should be reachable from one authoritative, documented location; ad-hoc or memorised paths are a floor-level practice that should…' | 0 | No Dependency |  | Configures the MD3 adaptive 4-column fluid layout token engine on top of the grid container from Step 6. Reuses the 16px margin/gutter profile fixed in Step 5. | 8
8 | 8 - Layout Shell | 356 | RCGLA-018 | RCGLA-018-A01 | RCGLA-018 - Universal Master Layout Architecture for React Components | Audit existing pages for custom, one-off dimension definitions. | Build primary scaffold locking metrics. ¦ Implement configurable child prop targets. ¦ Block flexible padding assignments. ¦ Force tracks to implement central layouts. | Architecture Standardization. | Global responsive breakpoint thresholds. | Interaction. | Guarantees total frontend design layout consistency. | Mandates mobile-first styling dimensions dynamically adjusting prior to larger viewports. | Connected micro-apps share pixel-perfect dimensions. | Atomic-level data fields: Audit Type; Audit Date; Audit Result; Audit Trail; Auditor Information ¦¦ Mobile UX/UI design config required: Adaptive fluid alignment parameters optimizing density seamlessly. ¦ Precise spacing margins. ¦ Dynamic breakpoint configurations adjusting safely on mobile. ¦ Adaptive elevation styling variables. ¦¦ Domain expertise/sign-off required: React Native / React Frontend Architecture, Mobile-First Web Design, & CSS Grid Layouts. | Minimizes operational adaptation friction. | Internal reporting renders perfectly inside standard containers. | Rigid template usage globally enforced via continuous testing. | Layout systems operate as multi-tenant structural shells. | core.ui.master_scaffold. | Interfacing logic maps to central analytic tools securely. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: 1.0 ¦ Row: 356.0 | 3 Hours. | Production global template forcing visual structure metrics. | Code scanning proves 100% of app instances use wrappers. | None. | Adaptive fluid alignment parameters optimizing density seamlessly. | Precise spacing margins. | Dynamic breakpoint configurations adjusting safely on mobile. | Adaptive elevation styling variables. | React Native / React Frontend Architecture, Mobile-First Web Design, & CSS Grid Layouts. | Custom local padding declarations are programmatically stripped by central package rules. | Non-standard layouts cause automated branch check rejections, forcing alignment. | Strips redundant duplicate design work. | Delivers a predictable app journey, eliminating fatigue. |  |  | RCGLA-018 - Universal Master Layout Architecture for React Components | Audit existing pages for custom, one-off dimension definitions. | Scope Coverage / Audit Completeness | 80% of relevant items identified | 100% of relevant items identified and logged in an inventory register | 100% identified, logged, and cross-checked against the design/architecture spec | Complete | World-class teams complete a full inventory before design work begins; partial audits (below 80%) risk missed edge cases downstream. | Fredrick | Audit Type; Audit Date; Audit Result; Audit Trail; Auditor Information; Completion Status ('Complete'); Action/Event Timestamp; User/Session ID | Data Required: Scope Coverage / Audit Completeness ¦¦ Configuration Data: Floor=80% of relevant items identified ¦ Optimal=100% of relevant items identified and logged in an inventory register ¦ Ceiling=100% identified, logged, and cross-checked against the design/architecture spec ¦¦ Implementation Data: Output field='Complete'; Standard/Reference='World-class teams complete a full inventory before design work begins; partial audits (below 80%) risk missed edge cases downstream.' | 0 | No Dependency |  | The universal master layout wrapper that every page uses. It can only lock dimensions once the grid (Step 6) and layout token engine (Step 7) exist to lock them against. | 9,10
9 | 9 - Navigation | 4 | ANSA-012 | ANSA-012-A01 | Establish Contextual Navigation Header Framework. | Open the Core Design System Library repository. | Cap maximum string titles to protect horizontal grid boundaries. ¦ Embed standard high-contrast action vector icons for core paths. ¦ Inject scroll-listening hooks to adjust header elevations dynamically. ¦ Link the master back arrow component to secure state management targets. | Marketing UI Component Architecture. | Finalize application navigation pathways and directory hierarchies. | UX Flow. | Secures immediate operational context, stopping users from becoming stranded deep inside app pipelines. | Imposes a strict, lightweight layout container pinned at the top viewport rim, standardizing view handovers under network flux. | Top navigation bars transition from flat fills to high-elevation shadows as lower contents scroll. | Atomic-level data fields: System Name; System Version; Component List; Token Values; Documentation Links; System Configuration Details ¦¦ Mobile UX/UI design config required: Hide excessive, low-priority shortcut items inside unified trailing overflow menus on tight displays. ¦ Align textual header targets strictly to standard left grid baselines. ¦ Compress header spacing scales smoothly as parent view boundaries contract. ¦ Secure the top app container height to an unyielding 64dp profile line. ¦¦ Domain expertise/sign-off required: Mobile UI Navigation Architecture / Front-End Routing Engineering | Users return to clean ancestral views seamlessly using predictable, single-tap backtracking buttons. | Structural section headers remain cleanly readable, preserving lower screen spaces for metric summaries. | Top App Bar construction blueprint enforcement. | ContextualHeaderModule. | Core Design System Library. | Emits navigation telemetry events instantly into real-time Pub/Sub message queues. | Level 1 ¦ Phase: SETUP-01 ¦ Atomic Step: 1.0 ¦ Row: 4.0 | 1 Day. | Standardized header layout template integration code. What measures we should look at to confirm completion of this task: 100% of application pages render matching navigation rules with zero history stack leaks. |  | None. | Hide excessive, low-priority shortcut items inside unified trailing overflow menus on tight displays. | Align textual header targets strictly to standard left grid baselines. | Compress header spacing scales smoothly as parent view boundaries contract. | Secure the top app container height to an unyielding 64dp profile line. | Mobile UI Navigation Architecture / Front-End Routing Engineering | Intercept routes block rapid double-tapping on back controls, saving history queues from array corruption. | Missing back-navigation hooks block repository compilation checks via automated layout review scans. Vitality & Prosperity (VAP): | Standardized headers remove unique view layout logic errors during sprint timelines. | High contextual clarity structures clean choices, decreasing application navigation fatigue. |  |  | Establish Contextual Navigation Header Framework. | Open the Core Design System Library repository. | Environment / Asset Access Readiness | Located on first attempt | Path version-controlled & documented | N/A (one-time setup) | Complete / Partial / Not Complete | Source files and directories referenced should be under version control and discoverable without tribal knowledge. | Fredrick | System Name; System Version; Component List; Token Values; Documentation Links; System Configuration Details; Completion Status ('Complete / Partial / Not Complete'); Action/Event Timestamp; User/Session ID | Data Required: Environment / Asset Access Readiness ¦¦ Configuration Data: Floor=Located on first attempt ¦ Optimal=Path version-controlled & documented ¦ Ceiling=N/A (one-time setup) ¦¦ Implementation Data: Output field='Complete / Partial / Not Complete'; Standard/Reference='Source files and directories referenced should be under version control and discoverable without tribal knowledge.' | 0 | No Dependency |  | The contextual navigation header is the first real UI surface. It sits inside the master layout wrapper from Step 8 and consumes the tokens from Steps 2-4. | 10
10 | 10 - Interaction Std | 3095 | TTMAC-011 | TTMAC-011-A01 | Touch-Target Optimization Framework Setup (48×48 dp Minimum Interaction Nodes). | Open the core layout utility module /ui/core/touch_container.py. | Define absolute minimum touch-target boundaries ($\ge 48 \times 48\text{ dp}$) for compact layout elements ¦ Inject transparent target expansion boxes around micro-icons or selector ticks ¦ Configure button element grid bounds to preserve an 8 dp safety spacing margin ¦ Map long-press interaction paths to reveal detailed tooltips instead of dense text boxes. | Mobile-First Core UX/UI Layout Foundations. | Step 09 global responsive layout grid configuration completion. | Interaction. | Sub-standard touch target dimensions cause accidental clicks on adjacent button elements, breaking transaction actions. | Forces device layout physics to dictate structural interface boundaries before any desktop layouts are constructed. | Action selectors and option checkboxes feature high-visibility border padding. | Atomic-level data fields: Layout Type; Layout Grid Dimensions; Spacing Rules; Alignment Settings; Layout Validation Status ¦¦ Mobile UX/UI design config required: Cluster floating action items inside lower viewport quadrants to optimize single-hand actions. ¦ Apply high-contrast outline borders around main interactive containers. ¦ Transition selection button states instantly using clear visual highlights on touch. ¦ Ensure checkmark fields maintain clear, readable spacing from peripheral labels. ¦¦ Domain expertise/sign-off required: Accessibility Framework Systems Engineer / Mobile UI UX Designer | Tapping interactive menu items triggers instant, accurate system responses with zero accidental neighbor selection triggers. | Summary charts place interactive buttons inside distinct horizontal layout bands. | Adherence to TKI 9 core web property interactive component parameters. | Unified touch container bounding box utility module. | /ui/core/touch_container.py. | Ingests touch performance variables into BigQuery telemetry systems via event-driven Pub/Sub loops. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: 1.0 ¦ Row: 3095.0 | 6 Hours. | Native touch target component configuration library files. | 100% of deployed interactive elements maintain physical tap boundaries $\ge 48 \times 48\text{ dp}$. | HC-FE-0027. | Cluster floating action items inside lower viewport quadrants to optimize single-hand actions. | Apply high-contrast outline borders around main interactive containers. | Transition selection button states instantly using clear visual highlights on touch. | Ensure checkmark fields maintain clear, readable spacing from peripheral labels. | Accessibility Framework Systems Engineer / Mobile UI UX Designer | The compile engine throws an validation error if any touch target layout bounds map below $48\text{ dp}$ constraints. | Accidental double-tap interaction runs automatically filter down into single events, tracking duplicate event noise metrics. | Drives down user drop-off risks across high-value operational loops, lowering client support ticket processing costs. | Eliminates fat-finger clicking errors and selection friction during critical transaction workflows under erratic field environments. |  |  | Touch-Target Optimization Framework Setup (48×48 dp Minimum Interaction Nodes). | Open the core layout utility module /ui/core/touch_container.py. | Environment / Asset Access Readiness | Located on first attempt | Path version-controlled & documented | N/A (one-time setup) | Complete / Partial / Not Complete | Source files and directories referenced should be under version control and discoverable without tribal knowledge. | Fredrick | Layout Type; Layout Grid Dimensions; Spacing Rules; Alignment Settings; Layout Validation Status; Completion Status ('Complete / Partial / Not Complete'); Action/Event Timestamp; User/Session ID | Data Required: Environment / Asset Access Readiness ¦¦ Configuration Data: Floor=Located on first attempt ¦ Optimal=Path version-controlled & documented ¦ Ceiling=N/A (one-time setup) ¦¦ Implementation Data: Output field='Complete / Partial / Not Complete'; Standard/Reference='Source files and directories referenced should be under version control and discoverable without tribal knowledge.' | 0 | No Dependency |  | Touch-target framework (48x48dp minimum) is applied to the interactive elements that now exist - the header actions from Step 9 being the first. Setting it last means the rule is enforced against real components rather than in the abstract. | -