## Read Me
Steps 36-50 - Dependency-Free Build Order
Source | My stepsFN06082026.xlsx -> "Fredrick" tab (1,314 steps assigned to you)
Selection rule | Only steps where Dependency Count = 0 and Dependency (Atomic Step Serial No) = "No Dependency",
AND not already implemented in Steps 1-35. Verified row by row - all 15 confirmed zero-dependency.
Pool | 682 of your 1,314 steps have zero dependencies. 35 are done, leaving 647. Of those, 415 are
front-end steps whose output columns are not contaminated by backend content. These 15 come from there.
Track chosen | Navigation & adaptive shell - the structural layer the first 35 steps are waiting for.
Steps 1-10 gave you the frame, 11-20 the input layer, 21-35 the response layer. Every one of
those is a within-screen concern: there is still no way to move BETWEEN screens, no tablet
layout, no routing, and nothing reachable except a probe page.
Ordering rule | Foundation-first. shell blueprint -> shell containers -> distribution -> dashboard grid spec ->
navigation surfaces -> routing core -> routing budget -> content layout -> content guard ->
shell state -> destinations.
No step here depends on any other, so you can start any of them today. The order means no rework:
each one consumes the artefact the previous one produced.
Why the shell first | Steps 36-39 are four layout steps before a single navigation control. That is deliberate: a
navigation rail is an edge of a layout, and deciding where the rail goes before deciding how
the screen divides means moving it twice. SSTLA-012 (Step 36) names the constraint itself -
its poka-yoke blocks any view that does not extend the master layout wrapper you shipped as
Step 8, so this batch extends that scaffold rather than starting a second layout system.
ROW QUALITY | Four of the 15 are richly specified in the way Steps 1-20 were: Steps 36 (SSTLA-012),
38 (SSTLA-010), 39 (SSTLA-018) and 49 (IS22-RCGLA-022). The eleven GEN-* rows share a
boilerplate Expected Output ("Fully configured and validated implementation of...") and
Completion Measure ("100% CI/CD pass rate"), so their gates will be derived from the Setup
Step, the Description and the Metric Name, which are specific. Same ratio as Steps 21-35.
DATA QUALITY FLAGS | No selected row has a contaminated Expected Output this time - an improvement on the last two
batches. Four rows do carry a Metric Name that does not describe their step, and three rich
rows have an empty Completion Measure. Gate the action, not the metric:
S.No 10311 deep link routing engine -> Metric = "Push Notification Click-Through Rate (%)"
S.No 9706 tab-switch latency -> Metric = "Information Architecture Task Success Rate"
(the 200ms budget is in the Setup Step itself)
S.No 9233 deep link context manager -> Metric = "Syntax Validity" (thin, but gateable)
S.No 10289 320dp text fitting -> Metric = "Step Completion Rate (%)" (generic)
S.No 13776 / 3161 / 2105 -> Completion Measures column is EMPTY on all three,
despite rich Setup Step and poka-yoke columns.
S.No 2039 preference manager panel -> Estimated Time reads "5 Minutes" for a responsive
settings panel with database writes. Treat as an
estimation error, not a scope signal.
All are worth correcting at source in the master sheet.
Still open from earlier | Step 6 (RCGLA-012) is Partial pending your zoom-lock decision. Step 31 (IS38-SGTIM-018) is
batches | Partial pending physical-device confirmation of the overscroll stretch. Step 5 (SSTLA-004)
awaits a reviewer quality score. None of these blocks this batch.
Next candidates | Rich or coherent rows that fit a later batch: S.No 389 (swipeable ENUM chip arrays),
3172 (expiry timeline tracker), 3084 (binary checklist steppers), 10839 (WCAG 2.2 AA +
screen reader audit), 12786 (accessibility hints), 9222 (first-load / Core Web Vitals),
10124 (segmented buttons), 11092 (autocomplete menu), 11037 (offline fallback queue).
Columns | All 49 original columns preserved, in original order, with original values (verified cell-for-cell).
Four columns ADDED (shaded pale yellow): Implementation Order, Build Layer,
Why This Position In The Sequence, and Blocks (Steps That Need This).
Total effort | Approximately 73 hours - 9 to 10 working days across the 15 steps.

## Build Sequence Summary
# | Build Layer | Global Ref ID | Atomic Step Ref ID | Setup Step (Action) | Est. Time | Dependency Count | Original S. No | Why This Position In The Sequence
36 | 36 - Shell Blueprint | SSTLA-012 | SSTLA-012-A01 | Defining the structural assembly blueprint for the mobile split-screen (Contextual Mirror) layout to present evidence and action panels on small screens. | 5 Hours. | 0 | 13776 | The structural blueprint for the split-screen shell, and the first thing to build because everything else in this batch renders inside it. Its own poka-yoke -- "code linters block views that do not extend the master layout wrapper" -- points straight at HabotMasterScaffold from Step 8, so this extends what you already have rather than starting a second layout system.
37 | 37 - Shell Containers | GEN-03270 | GEN-03270 | Create responsive split-screen and master-detail layout containers for mobile/tablet screens. | 4 Hours | 0 | 11488 | Turns the blueprint into real containers: split-screen and master-detail, switching on the window class the grid tokens already define. Second because a container without a blueprint is a guess, and because Steps 38-39 distribute content inside these containers rather than beside them.
38 | 38 - Shell Distribution | SSTLA-010 | SSTLA-010-A01 | Formulate the responsive split-screen grid distributions and layout rules for Micro Task Outsourcing (MTO) panels to maximize readability on small devices. | 8 Hours | 0 | 3161 | The column distribution inside the split view, plus the pinned-metrics rule its poka-yoke names ("key source metrics are pinned immovably at the top of the viewport"). Needs the containers from Step 37 to exist; needs to be settled before the navigation surfaces claim their own edges of the screen.
39 | 39 - Dashboard Grid Spec | SSTLA-018 | SSTLA-018-A01 | Formulating the responsive layout rules to organize parent command sections on 5.5-inch mobile viewports. | 16 Hours. | 0 | 2105 | The layout rules for command sections on a 5.5-inch viewport -- the Mobile Dashboard Grid Spec. The largest step in the batch at 16 hours. It comes after the split rules because a command section is one pane of that split, and before the nav surfaces because it decides how much room they may take.
40 | 40 - Navigation Surface | GEN-02334 | GEN-02334 | Integrate M3 Navigation Rails for tablet views and Bottom App Bars for mobile views. | 4 Hours | 0 | 10553 | M3 navigation rails on tablet, bottom app bars on mobile -- the first thing in this codebase that lets a user move between screens rather than within one. Sits on the window-class breakpoints from Step 5 and the shell from Steps 36-39, which is why it is not first despite being the headline.
41 | 41 - Navigation Surface | GEN-02676 | GEN-02676 | Add a badge counter to the bottom navigation icon that displays the current unread notification count. | 4 Hours | 0 | 10894 | The unread badge on the bottom navigation icon. Directly after the bar it attaches to, and it reuses the status vocabulary and badge component from Step 28 rather than inventing a second kind of badge.
42 | 42 - Routing Core | GEN-00999 | GEN-00999 | Deploy Automated Mobile Deep Link Routing & Context Restoration Engine | 4 Hours | 0 | 9233 | The deep-link context manager -- the step names the file. Restores where a user was, not just which screen. Placed after the navigation surfaces because a restored context has to land on a real destination, and before the routing engine because the engine is what calls it.
43 | 43 - Routing Core | GEN-02082 | GEN-02082 | Build a deep link routing engine leveraging Navigation component routing. | 4 Hours | 0 | 10311 | The route table and link parser on top of Step 42. Split from it deliberately: parsing a URL and restoring a context are different failures with different fixes, and the sheet lists them as two steps.
44 | 44 - Routing Budget | GEN-01474 | GEN-01474 | Benchmark tab switching latency to ensure view rendering completes under 200ms. | 4 Hours | 0 | 9706 | The 200ms tab-switch budget, measured. Last of the navigation work because it is the check on all of it -- a benchmark written before the tabs exist measures nothing. Consumes the motion ceiling already set in Step 11.
45 | 45 - Content Layout | GEN-00022 | GEN-00022 | Configure dashboard widgets and audit forms to stack vertically in a single-column or 2x2 grid on mobile. | 4 Hours | 0 | 8265 | Dashboard widgets and audit forms stacking to a single column or a 2x2 grid on mobile. The first consumer of the grid spec from Step 39, and the step that proves the shell can actually hold content rather than just divide space.
46 | 46 - Content Guard | GEN-02060 | GEN-02060 | Ensure text breathes and fits its container without truncating unreadably on 320dp screens. | 4 Hours | 0 | 10289 | Text fits its container without unreadable truncation at 320dp -- the narrowest device in your matrix. Deliberately after the layout steps rather than before: this is the guard that catches what they broke, and it has nothing to check until they exist.
47 | 47 - Shell State | GEN-02720 | GEN-02720 | Write the offline UI state management logic that activates when the polling function fails to receive a response within the timeout threshold. | 4 Hours | 0 | 10938 | The offline state machine, triggered when polling passes its timeout. Before the banner because the banner is a view of this state; building the view first means inventing a second source of truth for whether the app is offline.
48 | 48 - Shell State | GEN-03437 | GEN-03437 | Display an "Offline Mode" status banner and pending queue counters on UI screens. | 4 Hours | 0 | 11653 | The Offline Mode banner and pending-queue counters, rendering the state from Step 47. Its metric is a contrast ratio (4.5:1 floor, 7:1 optimal), which the WCAG engine from Step 4 measures directly -- one of the few GEN-* rows in this batch with a metric that genuinely fits its step.
49 | 49 - Destination | IS22-RCGLA-022-AS01 | IS22-RCGLA-022-AS01-A01 | Build and deploy a responsive preference manager panel inside client settings. | 5 Minutes. | 0 | 2039 | The preference manager panel: the first real destination the shell hosts, rather than a probe screen. Richly specified -- mapped preference columns, responsive containers, a spacing decision and a poka-yoke that freezes transitions until a change is written. Needs the shell (36-40) to have somewhere to put it.
50 | 50 - Destination | GEN-03404 | GEN-03404 | Build the mobile notification preference screen using M3 Switch components. | 4 Hours | 0 | 11620 | The notification preference screen, built from M3 switches inside the panel Step 49 delivers. Last because it is the narrowest and most dependent thing in the batch: a screen, inside a panel, inside a shell, reached through a route -- every layer below it built first.

## Steps 1-35 (already done)
# | Global Ref ID | Atomic Step Ref ID | Setup Step (Action) | Original S. No | Status
1 | TTMCS-001 | TTMCS-001-A01 | Install and configure the verified Material 3 layout component framework within frontend client packages. | 1797 | Implemented - Complete (all gates active and passing)
2 | RCGLA-001 | RCGLA-001-A01 | Build global corporate style token variables inside the mobile client framework. | 3227 | Implemented - Complete (all gates active and passing)
3 | TTMCS-004 | TTMCS-004-A01 | TTMCS-004 — Configure Atomic Light/Dark Adaptation Tokens | 1654 | Implemented - Complete (all gates active and passing)
4 | TTMCS-005 | TTMCS-005-A01 | TTMCS-005 — Mobile Dark Mode Contrast Enforcement | 3139 | Implemented - Complete (all gates active and passing)
5 | SSTLA-004 | SSTLA-004-A01 | Define the exact base breakpoint, column count, fluid margin, and gutter widths for the core mobile experience before scaling upward to tablet or desktop views. | 169 | Implemented - Complete, awaiting a human reviewer quality score
6 | RCGLA-012 | RCGLA-012-A01 | RCGLA-012 - Initialize Atomic Grid System & Mobile Viewport Constraints | 345 | Implemented - PARTIAL (2 gates deferred: zoom lock, CLS)
7 | RCGLA-032 | RCGLA-032-A01 | RCGLA-032 - Configure the Material Design 3 (MD3) adaptive 4-column fluid layout token engine for mobile screens. | 3051 | Implemented - Complete (all gates active and passing)
8 | RCGLA-018 | RCGLA-018-A01 | RCGLA-018 - Universal Master Layout Architecture for React Components | 356 | Implemented - Complete (all gates active and passing)
9 | ANSA-012 | ANSA-012-A01 | Establish Contextual Navigation Header Framework. | 4 | Implemented - Complete (all gates active and passing)
10 | TTMAC-011 | TTMAC-011-A01 | Touch-Target Optimization Framework Setup (48×48 dp Minimum Interaction Nodes). | 3095 | Implemented - Complete (all gates active and passing)
11 | BPTR-0422 | BPTR-0422-A01 | Define Passive Failure Motion Curves. | 257 | Implemented - Complete (all gates active and passing)
12 | REF-377 | REF-377-A01 | Set Progressive Stepper Transitions. | 400 | Implemented - Complete (all gates active and passing)
13 | BPTR-0128 | BPTR-0128-A01 | Establish Global Atomic Byt Micro-Interaction Boundaries | 1566 | Implemented - Complete (all gates active and passing)
14 | TTMAC-014 | TTMAC-014-A01 | TTMAC-014 - Interactive Touch Target Standardization Engine Setup | 2028 | Implemented - Complete (its deferred gate was closed by Steps 34-35)
15 | CSIVW-001 | CSIVW-001-A01 | Implement strict client-side Input Masking on all template text area entry portals. | 3062 | Implemented - Complete (all gates active and passing)
16 | IS12-CSIVW-011-AS01 | IS12-CSIVW-011-AS01-A01 | Setup character formatting filters across text entry boxes. | 3205 | Implemented - Complete (all gates active and passing)
17 | IS02-CSIVW-005-AS01 | IS02-CSIVW-005-AS01-A01 | Program dynamic inline error layouts to activate when input fields fail validation checks. | 2490 | Implemented - Complete (all gates active and passing)
18 | BPTR-0160 | BPTR-0160-A01 | Code and isolate mobile compound fields into distinct, standalone UI components featuring strict 48x48dp touch targets. | 3073 | Implemented - Complete (all gates active and passing)
19 | REF-197 | REF-197-A01 | Developing the Safe Error-Handling UI Rollback Handler | 3238 | Implemented - Complete (all gates active and passing)
20 | FIEVR-033 | FIEVR-033-A01 | FIEVR-033 - Build Multi-Step Guided Carousel Layout Stepper | 3128 | Implemented - Complete (all gates active and passing)
21 | GEN-00055 | GEN-00055 | Build the BottomSheet atomic component using MD3 design tokens. | 8298 | Implemented - Complete (all gates active and passing)
22 | GEN-00954 | GEN-00954 | Standardize Material Design 3 (MD3) Bottom-Sheet UI for Mobile Complex Action Flows | 9189 | Implemented - Complete (all gates active and passing)
23 | GEN-00235 | GEN-00235 | Set the default snapping point to 60% viewport height for optimal thumb interaction. | 8474 | Implemented - Complete (all gates active and passing)
24 | MUFCE-028 | MUFCE-028-A01 | Mandatory removal of all mouse hover tooltips and replacement with touch long-press modal sheets. | 1786 | Implemented - Complete (all gates active and passing)
25 | GEN-01363 | GEN-01363 | Bind the client UI error boundaries to trigger M3 error Snackbars upon caught exceptions. | 9596 | Implemented - Complete (all gates active and passing)
26 | GEN-01848 | GEN-01848 | Implement visual progress indicators to show user advancement. | 10080 | Implemented - Complete (all gates active and passing)
27 | GEN-01297 | GEN-01297 | Implement an empty state container with custom illustrations to display when search queries return zero logs. | 9530 | Implemented - Complete (all gates active and passing)
28 | GEN-01275 | GEN-01275 | Embed M3 status Badges to mark completed and active milestone nodes. | 9508 | Implemented - Complete (all gates active and passing)
29 | GEN-01452 | GEN-01452 | Construct the card UI chassis using M3 Outlined or Elevated Card specifications. | 9684 | Implemented - Complete (all gates active and passing)
30 | GEN-00201 | GEN-00201 | Use Material Design 3 shared axis transitions for mobile view state changes. | 8441 | Implemented - Complete (all gates active and passing)
31 | IS38-SGTIM-018-AS01 | IS38-SGTIM-018-AS01-A01 | Apply M3 Overscroll Stretch on MTOI Lists | 1555 | Implemented - PARTIAL (1 gate deferred: physical-device confirmation of the stretch)
32 | CPNCA-006 | CPNCA-006-A01 | Build a standardized list virtualization and dynamic data chunking component for data tables Operationalizing System Architecture Design]. | 2468 | Implemented - Complete (all gates active and passing)
33 | ANSA-006 | ANSA-006-A01 | Implementation Step 15: Build an expandable search text line inside primary system headers. (ANSA-006) | 3194 | Implemented - Complete (all gates active and passing)
34 | UFHT-032 | UFHT-032 | UI Hesitation Tracker Engine Setup | 4723 | Implemented - Complete (all gates active and passing)
35 | GEN-00632 | GEN-00632 | Deploy Mobile UX Friction Logs (Hesitation Tracking) | 8870 | Implemented - Complete (all gates active and passing)

## Steps 36-50 - Build Order
Implementation Order | Build Layer | S. No | Global Reference ID | Atomic Steps Reference ID | Setup Step (Action) | Setup Step Description | 4 Substeps | Decision Group | Decision to be Made Before Setup Step | Decision Category | Why This Matters | Mobile App First Implication | UX Translation | Data Requirement | User Interaction / Flow Impact | Dashboard / Interface Implication | What Standardized Must Be Done | Atomic Reusability | Common Library to Store | GCP / BigQuery Alignment | Sequence Order | Estimated Time Required | Expected Output | Completion Measures | Dependencies | Mobile-First & Responsive UX Google Material Design Decision | Mobile-First & Responsive UI Google Material Design Decision | Mobile-First & Responsive UX Google Material Design Implementation | Mobile-First & Responsive UI Google Material Design Implementation | Domain Expertise Needed | Mistake-Proofing (Poka-Yoke) | Self-Chasing | What Creates Vitality & Prosperity For Us | What Creates Vitality & Prosperity For the Customer | Responsive UX/UI Design | Vitality & Prosperity (VAP) | Setup Step (Action).1 | Atomic Step | Metric Name | Floor Boundary | Optimal Target | Ceiling Boundary | Best Qualitative Output | Best Qualitative/Quantitative Output Type | Assigned Team Member | Data Collected by System | Required Data / Configuration / Implementation Fields (from AL-AQ Analysis) | Dependency Count | Dependency (Atomic Step Serial No) | Output format | Why This Position In The Sequence | Blocks (Steps That Need This)
36 | 36 - Shell Blueprint | 13776 | SSTLA-012 | SSTLA-012-A01 | Defining the structural assembly blueprint for the mobile split-screen (Contextual Mirror) layout to present evidence and action panels on small screens. | Gather detailed functional requirements for the mobile Contextual Mirror layout experience. |  | Logical Verification Setup. |  | UX Flow / Interaction. | Clunky split-screen layouts cause constant scrolling, increasing processing errors. | Maximizes the available layout space by adapting container boxes to compact touch displays. |  | Atomic-level data fields: Layout Type; Layout Grid Dimensions; Spacing Rules; Alignment Settings; Layout Validation Status ¦¦ No matched reference row in Setup Implementation master list — required data fields limited to atomic-level Data Collection Requirements only; standardized Mobile UX/UI & domain-expertise fields unavailable, verify manually. | Double-tapping panel bars snaps views between split ratios instantly. |  |  |  |  | Sync panel view metrics to track layout usage patterns on mobile displays. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: 1.0 ¦ Row: 13776.0 | 5 Hours. | Unified layout container component files. Measures of Completion: Mobile views adjust cleanly when rotated, maintaining target sizes across panels. |  | Decisions 5, 11. Mobile-First UX GMRD Decision: Anchor validation buttons safely along lower viewport limits. Mobile-First UI GMRD Decision: Use clear boundary borders to highlight active panels. Mobile-First UX GMRD Implementation: Add clean touch physics to screen splitter controls. Mobile-First UI GMRD Implementation: Position action alerts clearly within the active panel view. | [5 empty] | Code linters block views that do not extend the master layout wrapper. | Missing layout hooks stop compilation, keeping bad code out of testing builds. |  |  |  |  | Defining the structural assembly blueprint for the mobile split-screen (Contextual Mirror) layout to present evidence and action panels on small screens. | Gather detailed functional requirements for the mobile Contextual Mirror layout experience. | Requirement & Asset Discovery Coverage (%) — detailed functional requirements for the mobile | 0.9 | 1.0 | 1.0 | Complete/Partial/Not Complete | Aligned to BABOK v3 elicitation-completeness practice: benchmark teams close out discovery only once all in-scope items are catalogued, with no material gaps carried into design. | Fredrick | Layout Type; Layout Grid Dimensions; Spacing Rules; Alignment Settings; Layout Validation Status; Completion Status ('Complete/Partial/Not Complete'); Action/Event Timestamp; User/Session ID | Data Required: Requirement & Asset Discovery Coverage (%) — detailed functional requirements for the mobile ¦¦ Configuration Data: Floor=0.9 ¦ Optimal=1 ¦ Ceiling=1 ¦¦ Implementation Data: Output field='Complete/Partial/Not Complete'; Standard/Reference='Aligned to BABOK v3 elicitation-completeness practice: benchmark teams close out discovery only once all in-scope items are catalogued, with no…' | 0 | No Dependency |  | The structural blueprint for the split-screen shell, and the first thing to build because everything else in this batch renders inside it. Its own poka-yoke -- "code linters block views that do not extend the master layout wrapper" -- points straight at HabotMasterScaffold from Step 8, so this extends what you already have rather than starting a second layout system. | 37,38,39,40,45,49
37 | 37 - Shell Containers | 11488 | GEN-03270 | GEN-03270 | Create responsive split-screen and master-detail layout containers for mobile/tablet screens. | Create responsive split-screen and master-detail layout containers for mobile/tablet screens. | 1. Plan and scope this step. 2. Implement the core configuration. 3. Test and validate in staging. 4. Document and commit to runbook. | Architecture & Implementation Governance | What exact configuration and validation approach should be applied for: Create responsive split-screen and master-detail layout containers for mobile/ta? | UX Flow / BigQuery | Create responsive split-screen and master-detail layout containers for mobile/tablet screens. is a critical implementation step. Without it, downstream steps lack the required baseline configuration. | Ensures sub-100ms API response latencies on mobile clients via optimized backend configuration. | Single-column mobile layout with M3 status cards displaying step completion state. | Data/artifacts to prepare: mobile/tablet. Metric config: 'Layout Responsiveness Pass Rate' (floor threshold: 1.0). Reference standard/spec to configure against: Material Design 3 Layouts. Output field to capture: Complete. | Users interact with this step exclusively through the mobile engineering console. Read-only M3 KPI cards with deep-link drill-down. | Engineering console dashboard displays step health via M3 Elevated Card with inline status chip. | English Code (EC) blueprint required before any code is written. All functions must have single-verb EC headers. | Core pattern for this step stored as a reusable module in the shared library. | @habot/shared-library | All step execution events stream to BigQuery partitioned by event_date, clustered by trace_id. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: N/A ¦ Row: 11488.0 | 4 Hours | Fully configured and validated implementation of: Create responsive split-screen and master-detail layout containers for mobile/ta. | 100% CI/CD pass rate. All validation checks passing. Documentation committed to runbook. | Dependent on prior foundational steps. | M3 responsive layout: single-column on mobile (<600dp), multi-column on desktop (≥840dp). | M3 Elevated Cards Level 2 (3dp). M3 Status Chips for health indicators. 48x48dp touch targets. | Background polling refreshes data every 30 seconds. Pull-to-refresh triggers manual sync. | M3 Bottom Sheet for configuration inputs. M3 Snackbar for confirmations. Material You dynamic color. | Mobile Engineering, GCP Architecture, UX/UI Design (MD3), DCDF Engine Architecture. | CI/CD pipeline physically blocks deployment if any gate for this step fails. | Automated Liveness Handshake monitors this step every 30 seconds and triggers rollback on failure. | Eliminates manual overhead, reduces operational cost, and protects revenue pipelines. | Engineers and end-users experience reliable, uninterrupted platform performance. | M3 responsive single-column on mobile, multi-panel on tablet/desktop. 48x48dp touch targets. | Us: Eliminates manual overhead and reduces operational cost. ¦ Customer: Reliable, uninterrupted platform performance. | Create responsive split-screen and master-detail layout containers for mobile/tablet screens. | Create responsive split-screen and master-detail layout containers for mobile/tablet screens. | Layout Responsiveness Pass Rate | 1.0 | 1.0 | 1.0 | Complete | Material Design 3 Layouts | Fredrick | mobile/tablet; Completion Status ('Complete'); Action/Event Timestamp; User/Session ID | Data Required: Layout Responsiveness Pass Rate ¦¦ Configuration Data: Floor=1 ¦ Optimal=1 ¦ Ceiling=1 ¦¦ Implementation Data: Output field='Complete'; Standard/Reference='Material Design 3 Layouts' | 0 | No Dependency |  | Turns the blueprint into real containers: split-screen and master-detail, switching on the window class the grid tokens already define. Second because a container without a blueprint is a guess, and because Steps 38-39 distribute content inside these containers rather than beside them. | 38,39,40,45,49
38 | 38 - Shell Distribution | 3161 | SSTLA-010 | SSTLA-010-A01 | Formulate the responsive split-screen grid distributions and layout rules for Micro Task Outsourcing (MTO) panels to maximize readability on small devices. | Identify core visual content requirements for Micro Task Outsourcing (MTO) mobile interface panels. |  | MTO Workflow Interface Architecture |  | UX Flow | Poorly scaled split viewports on mobile devices lead to constant pinching and zooming, causing fast operator fatigue and input mistakes. | Replaces wide side-by-side desktop grids with clean, thumb-friendly vertical stacks tailored for mobile interaction. |  | Atomic-level data fields: Mobile Platform; OS Version; Device Type; Screen Dimensions; Mobile Configuration ¦¦ No matched reference row in Setup Implementation master list — required data fields limited to atomic-level Data Collection Requirements only; standardized Mobile UX/UI & domain-expertise fields unavailable, verify manually. | Keeps operators perfectly focused on a single verification task, eliminating distracting page turns or multi-step navigation. |  |  |  |  | Speeds up human verification loops, ensuring fast queue resolution inside Cloud Pub/Sub networks. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: 1.0 ¦ Row: 3161.0 | 8 Hours | High-fidelity layout templates built for phone and tablet screens. |  | Serial Number 5. | [5 empty] | Key source metrics are pinned immovably at the top of the viewport, keeping important details visible while filling out long fields. | Hardcoding layout values across screens creates broken, overlapping UI elements on smaller devices, instantly stalling qa cycles. |  |  |  |  | Formulate the responsive split-screen grid distributions and layout rules for Micro Task Outsourcing (MTO) panels to maximize readability on small devices. | Identify core visual content requirements for Micro Task Outsourcing (MTO) mobile interface panels. | Requirement & Asset Discovery Coverage (%) — core visual content requirements for Micro Task | 0.9 | 1.0 | 1.0 | Complete/Partial/Not Complete | Aligned to BABOK v3 elicitation-completeness practice: benchmark teams close out discovery only once all in-scope items are catalogued, with no material gaps carried into design. | Fredrick | Mobile Platform; OS Version; Device Type; Screen Dimensions; Mobile Configuration; Completion Status ('Complete/Partial/Not Complete'); Action/Event Timestamp; User/Session ID | Data Required: Requirement & Asset Discovery Coverage (%) — core visual content requirements for Micro Task ¦¦ Configuration Data: Floor=0.9 ¦ Optimal=1 ¦ Ceiling=1 ¦¦ Implementation Data: Output field='Complete/Partial/Not Complete'; Standard/Reference='Aligned to BABOK v3 elicitation-completeness practice: benchmark teams close out discovery only once all in-scope items are catalogued, with no…' | 0 | No Dependency |  | The column distribution inside the split view, plus the pinned-metrics rule its poka-yoke names ("key source metrics are pinned immovably at the top of the viewport"). Needs the containers from Step 37 to exist; needs to be settled before the navigation surfaces claim their own edges of the screen. | 39,40,45
39 | 39 - Dashboard Grid Spec | 2105 | SSTLA-018 | SSTLA-018-A01 | Formulating the responsive layout rules to organize parent command sections on 5.5-inch mobile viewports. | Identify target 5.5-inch mobile viewport dimensions and resolution constraints (e.g., 1080x1920 pixels at 16:9). |  | UI/UX Design & Content Strategy. |  | UX Flow. | Cluttered or rigid mobile screen interfaces frustrate parents, driving application abandonment spikes. | Screen elements must collapse into vertical layout stacks to eliminate horizontal scroll glitches. |  | Atomic-level data fields: Mobile Platform; OS Version; Device Type; Screen Dimensions; Mobile Configuration ¦¦ No matched reference row in Setup Implementation master list — required data fields limited to atomic-level Data Collection Requirements only; standardized Mobile UX/UI & domain-expertise fields unavailable, verify manually. | Navigation bars sit comfortably within standard thumb interaction spaces. |  |  |  |  | Application view layouts adjust dynamically based on user parameter fields. | Level 10 ¦ Phase: SETUP-10 ¦ Atomic Step: 1.0 ¦ Row: 2105.0 | 16 Hours. | Mobile Dashboard Grid Spec. |  | Decision 3. | [5 empty] | Selection items lock automatically if required preceding details stay empty. | Screen load delays trigger background event logs to track down latency bottlenecks. |  |  |  |  | Formulating the responsive layout rules to organize parent command sections on 5.5-inch mobile viewports. | Identify target 5.5-inch mobile viewport dimensions and resolution constraints (e.g., 1080x1920 pixels at 16:9). | Requirement & Asset Discovery Coverage (%) — target 5.5-inch mobile viewport dimensions and resolution | 0.9 | 1.0 | 1.0 | Complete/Partial/Not Complete | Aligned to BABOK v3 elicitation-completeness practice: benchmark teams close out discovery only once all in-scope items are catalogued, with no material gaps carried into design. | Fredrick | Mobile Platform; OS Version; Device Type; Screen Dimensions; Mobile Configuration; Completion Status ('Complete/Partial/Not Complete'); Action/Event Timestamp; User/Session ID | Data Required: Requirement & Asset Discovery Coverage (%) — target 5.5-inch mobile viewport dimensions and resolution ¦¦ Configuration Data: Floor=0.9 ¦ Optimal=1 ¦ Ceiling=1 ¦¦ Implementation Data: Output field='Complete/Partial/Not Complete'; Standard/Reference='Aligned to BABOK v3 elicitation-completeness practice: benchmark teams close out discovery only once all in-scope items are catalogued, with no…' | 0 | No Dependency |  | The layout rules for command sections on a 5.5-inch viewport -- the Mobile Dashboard Grid Spec. The largest step in the batch at 16 hours. It comes after the split rules because a command section is one pane of that split, and before the nav surfaces because it decides how much room they may take. | 40,45,46
40 | 40 - Navigation Surface | 10553 | GEN-02334 | GEN-02334 | Integrate M3 Navigation Rails for tablet views and Bottom App Bars for mobile views. | Integrate M3 Navigation Rails for tablet views and Bottom App Bars for mobile views. | 1. Plan and scope this step. 2. Implement the core configuration. 3. Test and validate in staging. 4. Document and commit to runbook. | Architecture & Implementation Governance | What exact configuration and validation approach should be applied for: Integrate M3 Navigation Rails for tablet views and Bottom App Bars for mobile vi? | UX Flow / BigQuery | Integrate M3 Navigation Rails for tablet views and Bottom App Bars for mobile views. is a critical implementation step. Without it, downstream steps lack the required baseline configuration. | Ensures sub-100ms API response latencies on mobile clients via optimized backend configuration. | Single-column mobile layout with M3 status cards displaying step completion state. | Data/artifacts to prepare: Integrate M3 Navigation Rails for tablet views and Bottom App…. Metric config: 'UI Compliance Rate (%)' (floor threshold: 95%). Reference standard/spec to configure against: Material Design 3, WCAG 2.2 AA, W3C Web Standards. Output field to capture: Pass/Fail. | Users interact with this step exclusively through the mobile engineering console. Read-only M3 KPI cards with deep-link drill-down. | Engineering console dashboard displays step health via M3 Elevated Card with inline status chip. | English Code (EC) blueprint required before any code is written. All functions must have single-verb EC headers. | Core pattern for this step stored as a reusable module in the shared library. | @habot/shared-library | All step execution events stream to BigQuery partitioned by event_date, clustered by trace_id. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: N/A ¦ Row: 10553.0 | 4 Hours | Fully configured and validated implementation of: Integrate M3 Navigation Rails for tablet views and Bottom App Bars for mobile vi. | 100% CI/CD pass rate. All validation checks passing. Documentation committed to runbook. | Dependent on prior foundational steps. | M3 responsive layout: single-column on mobile (<600dp), multi-column on desktop (≥840dp). | M3 Elevated Cards Level 2 (3dp). M3 Status Chips for health indicators. 48x48dp touch targets. | Background polling refreshes data every 30 seconds. Pull-to-refresh triggers manual sync. | M3 Bottom Sheet for configuration inputs. M3 Snackbar for confirmations. Material You dynamic color. | Mobile Engineering, GCP Architecture, UX/UI Design (MD3), DCDF Engine Architecture. | CI/CD pipeline physically blocks deployment if any gate for this step fails. | Automated Liveness Handshake monitors this step every 30 seconds and triggers rollback on failure. | Eliminates manual overhead, reduces operational cost, and protects revenue pipelines. | Engineers and end-users experience reliable, uninterrupted platform performance. | M3 responsive single-column on mobile, multi-panel on tablet/desktop. 48x48dp touch targets. | Us: Eliminates manual overhead and reduces operational cost. ¦ Customer: Reliable, uninterrupted platform performance. | Integrate M3 Navigation Rails for tablet views and Bottom App Bars for mobile views. | Integrate M3 Navigation Rails for tablet views and Bottom App Bars for mobile views. | UI Compliance Rate (%) | 0.95 | 1.0 | 1.0 | Pass/Fail | Material Design 3, WCAG 2.2 AA, W3C Web Standards | Fredrick | Integrate M3 Navigation Rails for tablet views and Bottom App…; Completion Status ('Pass/Fail'); Action/Event Timestamp; User/Session ID | Data Required: UI Compliance Rate (%) ¦¦ Configuration Data: Floor=0.95 ¦ Optimal=1 ¦ Ceiling=1 ¦¦ Implementation Data: Output field='Pass/Fail'; Standard/Reference='Material Design 3, WCAG 2.2 AA, W3C Web Standards' | 0 | No Dependency |  | M3 navigation rails on tablet, bottom app bars on mobile -- the first thing in this codebase that lets a user move between screens rather than within one. Sits on the window-class breakpoints from Step 5 and the shell from Steps 36-39, which is why it is not first despite being the headline. | 41,42,43,44,49
41 | 41 - Navigation Surface | 10894 | GEN-02676 | GEN-02676 | Add a badge counter to the bottom navigation icon that displays the current unread notification count. | Add a badge counter to the bottom navigation icon that displays the current unread notification count. | 1. Plan and scope this step. 2. Implement the core configuration. 3. Test and validate in staging. 4. Document and commit to runbook. | Architecture & Implementation Governance | What exact configuration and validation approach should be applied for: Add a badge counter to the bottom navigation icon that displays the current unre? | UX Flow / BigQuery | Add a badge counter to the bottom navigation icon that displays the current unread notification coun is a critical implementation step. Without it, downstream steps lack the required baseline configuration. | Ensures sub-100ms API response latencies on mobile clients via optimized backend configuration. | Single-column mobile layout with M3 status cards displaying step completion state. | Data/artifacts to prepare: Add a badge counter to the bottom navigation icon that…. Metric config: 'Implementation Completeness Rate' (floor threshold: 90% of defined scope completed). Reference standard/spec to configure against: ISO/IEC 25010:2011 — Systems and Software Quality Requirements. Output field to capture: Complete / Partial / Not Complete. | Users interact with this step exclusively through the mobile engineering console. Read-only M3 KPI cards with deep-link drill-down. | Engineering console dashboard displays step health via M3 Elevated Card with inline status chip. | English Code (EC) blueprint required before any code is written. All functions must have single-verb EC headers. | Core pattern for this step stored as a reusable module in the shared library. | @habot/shared-library | All step execution events stream to BigQuery partitioned by event_date, clustered by trace_id. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: N/A ¦ Row: 10894.0 | 4 Hours | Fully configured and validated implementation of: Add a badge counter to the bottom navigation icon that displays the current unre. | 100% CI/CD pass rate. All validation checks passing. Documentation committed to runbook. | Dependent on prior foundational steps. | M3 responsive layout: single-column on mobile (<600dp), multi-column on desktop (≥840dp). | M3 Elevated Cards Level 2 (3dp). M3 Status Chips for health indicators. 48x48dp touch targets. | Background polling refreshes data every 30 seconds. Pull-to-refresh triggers manual sync. | M3 Bottom Sheet for configuration inputs. M3 Snackbar for confirmations. Material You dynamic color. | Mobile Engineering, GCP Architecture, UX/UI Design (MD3), DCDF Engine Architecture. | CI/CD pipeline physically blocks deployment if any gate for this step fails. | Automated Liveness Handshake monitors this step every 30 seconds and triggers rollback on failure. | Eliminates manual overhead, reduces operational cost, and protects revenue pipelines. | Engineers and end-users experience reliable, uninterrupted platform performance. | M3 responsive single-column on mobile, multi-panel on tablet/desktop. 48x48dp touch targets. | Us: Eliminates manual overhead and reduces operational cost. ¦ Customer: Reliable, uninterrupted platform performance. | Add a badge counter to the bottom navigation icon that displays the current unread notification coun | Add a badge counter to the bottom navigation icon that displays the current unread notification count. | Implementation Completeness Rate | 90% of defined scope completed | 100% of scope complete with peer validation | 1.0 | Complete / Partial / Not Complete | ISO/IEC 25010:2011 — Systems and Software Quality Requirements | Fredrick | Add a badge counter to the bottom navigation icon that…; Completion Status ('Complete / Partial / Not Complete'); Action/Event Timestamp; User/Session ID | Data Required: Implementation Completeness Rate ¦¦ Configuration Data: Floor=90% of defined scope completed ¦ Optimal=100% of scope complete with peer validation ¦¦ Implementation Data: Output field='Complete / Partial / Not Complete'; Standard/Reference='ISO/IEC 25010:2011 — Systems and Software Quality Requirements' | 0 | No Dependency |  | The unread badge on the bottom navigation icon. Directly after the bar it attaches to, and it reuses the status vocabulary and badge component from Step 28 rather than inventing a second kind of badge. | -
42 | 42 - Routing Core | 9233 | GEN-00999 | GEN-00999 | Deploy Automated Mobile Deep Link Routing & Context Restoration Engine | Create deep_link_context_manager.dart / .kt. | 1. Plan and scope this step. 2. Implement the core configuration. 3. Test and validate in staging. 4. Document and commit to runbook. | Architecture & Implementation Governance | What exact configuration and validation approach should be applied for: Create deep_link_context_manager.dart / .kt.? | UX Flow / BigQuery | Create deep_link_context_manager.dart / .kt. is a critical implementation step. Without it, downstream steps lack the required baseline configuration. | Ensures sub-100ms API response latencies on mobile clients via optimized backend configuration. | Single-column mobile layout with M3 status cards displaying step completion state. | Data/artifacts to prepare: deep_link_context_manager. Metric config: 'Syntax Validity' (floor threshold: $100\%$). Reference standard/spec to configure against: Dart/Kotlin Conventions. Output field to capture: Complete / Not Complete. | Users interact with this step exclusively through the mobile engineering console. Read-only M3 KPI cards with deep-link drill-down. | Engineering console dashboard displays step health via M3 Elevated Card with inline status chip. | English Code (EC) blueprint required before any code is written. All functions must have single-verb EC headers. | Core pattern for this step stored as a reusable module in the shared library. | @habot/shared-library | All step execution events stream to BigQuery partitioned by event_date, clustered by trace_id. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: N/A ¦ Row: 9233.0 | 4 Hours | Fully configured and validated implementation of: Create deep_link_context_manager.dart / .kt.. | 100% CI/CD pass rate. All validation checks passing. Documentation committed to runbook. | Dependent on prior foundational steps. | M3 responsive layout: single-column on mobile (<600dp), multi-column on desktop (≥840dp). | M3 Elevated Cards Level 2 (3dp). M3 Status Chips for health indicators. 48x48dp touch targets. | Background polling refreshes data every 30 seconds. Pull-to-refresh triggers manual sync. | M3 Bottom Sheet for configuration inputs. M3 Snackbar for confirmations. Material You dynamic color. | Mobile Engineering, GCP Architecture, UX/UI Design (MD3), DCDF Engine Architecture. | CI/CD pipeline physically blocks deployment if any gate for this step fails. | Automated Liveness Handshake monitors this step every 30 seconds and triggers rollback on failure. | Eliminates manual overhead, reduces operational cost, and protects revenue pipelines. | Engineers and end-users experience reliable, uninterrupted platform performance. | M3 responsive single-column on mobile, multi-panel on tablet/desktop. 48x48dp touch targets. | Us: Eliminates manual overhead and reduces operational cost. ¦ Customer: Reliable, uninterrupted platform performance. | Deploy Automated Mobile Deep Link Routing & Context Restoration Engine | Create deep_link_context_manager.dart / .kt. | Syntax Validity | $100\%$ | $100\%$ | N/A (100% target) | Complete / Not Complete | Dart/Kotlin Conventions | Fredrick | deep_link_context_manager; Completion Status ('Complete / Not Complete'); Action/Event Timestamp; User/Session ID | Data Required: Syntax Validity ¦¦ Configuration Data: Floor=$100\%$ ¦ Optimal=$100\%$ ¦ Ceiling=N/A (100% target) ¦¦ Implementation Data: Output field='Complete / Not Complete'; Standard/Reference='Dart/Kotlin Conventions' | 0 | No Dependency |  | The deep-link context manager -- the step names the file. Restores where a user was, not just which screen. Placed after the navigation surfaces because a restored context has to land on a real destination, and before the routing engine because the engine is what calls it. | 43,44
43 | 43 - Routing Core | 10311 | GEN-02082 | GEN-02082 | Build a deep link routing engine leveraging Navigation component routing. | Build a deep link routing engine leveraging Navigation component routing. | 1. Plan and scope this step. 2. Implement the core configuration. 3. Test and validate in staging. 4. Document and commit to runbook. | Architecture & Implementation Governance | What exact configuration and validation approach should be applied for: Build a deep link routing engine leveraging Navigation component routing.? | UX Flow / BigQuery | Build a deep link routing engine leveraging Navigation component routing. is a critical implementation step. Without it, downstream steps lack the required baseline configuration. | Ensures sub-100ms API response latencies on mobile clients via optimized backend configuration. | Single-column mobile layout with M3 status cards displaying step completion state. | Data/artifacts to prepare: Build a deep link routing engine leveraging Navigation component routing.. Metric config: 'Push Notification Click-Through Rate (%)' (floor threshold: 10). Reference standard/spec to configure against: Mobile Marketing Analytics & APNS/FCM Standards. Output field to capture: High/Medium/Low. | Users interact with this step exclusively through the mobile engineering console. Read-only M3 KPI cards with deep-link drill-down. | Engineering console dashboard displays step health via M3 Elevated Card with inline status chip. | English Code (EC) blueprint required before any code is written. All functions must have single-verb EC headers. | Core pattern for this step stored as a reusable module in the shared library. | @habot/shared-library | All step execution events stream to BigQuery partitioned by event_date, clustered by trace_id. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: N/A ¦ Row: 10311.0 | 4 Hours | Fully configured and validated implementation of: Build a deep link routing engine leveraging Navigation component routing.. | 100% CI/CD pass rate. All validation checks passing. Documentation committed to runbook. | Dependent on prior foundational steps. | M3 responsive layout: single-column on mobile (<600dp), multi-column on desktop (≥840dp). | M3 Elevated Cards Level 2 (3dp). M3 Status Chips for health indicators. 48x48dp touch targets. | Background polling refreshes data every 30 seconds. Pull-to-refresh triggers manual sync. | M3 Bottom Sheet for configuration inputs. M3 Snackbar for confirmations. Material You dynamic color. | Mobile Engineering, GCP Architecture, UX/UI Design (MD3), DCDF Engine Architecture. | CI/CD pipeline physically blocks deployment if any gate for this step fails. | Automated Liveness Handshake monitors this step every 30 seconds and triggers rollback on failure. | Eliminates manual overhead, reduces operational cost, and protects revenue pipelines. | Engineers and end-users experience reliable, uninterrupted platform performance. | M3 responsive single-column on mobile, multi-panel on tablet/desktop. 48x48dp touch targets. | Us: Eliminates manual overhead and reduces operational cost. ¦ Customer: Reliable, uninterrupted platform performance. | Build a deep link routing engine leveraging Navigation component routing. | Build a deep link routing engine leveraging Navigation component routing. | Push Notification Click-Through Rate (%) | 10.0 | 25.0 | 50.0 | High/Medium/Low | Mobile Marketing Analytics & APNS/FCM Standards | Fredrick | Build a deep link routing engine leveraging Navigation component routing.; Completion Status ('High/Medium/Low'); Action/Event Timestamp; User/Session ID | Data Required: Push Notification Click-Through Rate (%) ¦¦ Configuration Data: Floor=10 ¦ Optimal=25 ¦ Ceiling=50 ¦¦ Implementation Data: Output field='High/Medium/Low'; Standard/Reference='Mobile Marketing Analytics & APNS/FCM Standards' | 0 | No Dependency |  | The route table and link parser on top of Step 42. Split from it deliberately: parsing a URL and restoring a context are different failures with different fixes, and the sheet lists them as two steps. | 44
44 | 44 - Routing Budget | 9706 | GEN-01474 | GEN-01474 | Benchmark tab switching latency to ensure view rendering completes under 200ms. | Benchmark tab switching latency to ensure view rendering completes under 200ms. | 1. Plan and scope this step. 2. Implement the core configuration. 3. Test and validate in staging. 4. Document and commit to runbook. | Architecture & Implementation Governance | What exact configuration and validation approach should be applied for: Benchmark tab switching latency to ensure view rendering completes under 200ms.? | UX Flow / BigQuery | Benchmark tab switching latency to ensure view rendering completes under 200ms. is a critical implementation step. Without it, downstream steps lack the required baseline configuration. | Ensures sub-100ms API response latencies on mobile clients via optimized backend configuration. | Single-column mobile layout with M3 status cards displaying step completion state. | Data/artifacts to prepare: Benchmark tab switching latency to ensure view rendering completes under…. Metric config: 'Information Architecture Task Success Rate' (floor threshold: 0.8). Reference standard/spec to configure against: Nielsen Norman Group Usability Heuristics. Output field to capture: Good/Average/Poor. | Users interact with this step exclusively through the mobile engineering console. Read-only M3 KPI cards with deep-link drill-down. | Engineering console dashboard displays step health via M3 Elevated Card with inline status chip. | English Code (EC) blueprint required before any code is written. All functions must have single-verb EC headers. | Core pattern for this step stored as a reusable module in the shared library. | @habot/shared-library | All step execution events stream to BigQuery partitioned by event_date, clustered by trace_id. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: N/A ¦ Row: 9706.0 | 4 Hours | Fully configured and validated implementation of: Benchmark tab switching latency to ensure view rendering completes under 200ms.. | 100% CI/CD pass rate. All validation checks passing. Documentation committed to runbook. | Dependent on prior foundational steps. | M3 responsive layout: single-column on mobile (<600dp), multi-column on desktop (≥840dp). | M3 Elevated Cards Level 2 (3dp). M3 Status Chips for health indicators. 48x48dp touch targets. | Background polling refreshes data every 30 seconds. Pull-to-refresh triggers manual sync. | M3 Bottom Sheet for configuration inputs. M3 Snackbar for confirmations. Material You dynamic color. | Mobile Engineering, GCP Architecture, UX/UI Design (MD3), DCDF Engine Architecture. | CI/CD pipeline physically blocks deployment if any gate for this step fails. | Automated Liveness Handshake monitors this step every 30 seconds and triggers rollback on failure. | Eliminates manual overhead, reduces operational cost, and protects revenue pipelines. | Engineers and end-users experience reliable, uninterrupted platform performance. | M3 responsive single-column on mobile, multi-panel on tablet/desktop. 48x48dp touch targets. | Us: Eliminates manual overhead and reduces operational cost. ¦ Customer: Reliable, uninterrupted platform performance. | Benchmark tab switching latency to ensure view rendering completes under 200ms. | Benchmark tab switching latency to ensure view rendering completes under 200ms. | Information Architecture Task Success Rate | 0.8 | 0.95 | 1.0 | Good/Average/Poor | Nielsen Norman Group Usability Heuristics | Fredrick | Benchmark tab switching latency to ensure view rendering completes under…; Completion Status ('Good/Average/Poor'); Action/Event Timestamp; User/Session ID | Data Required: Information Architecture Task Success Rate ¦¦ Configuration Data: Floor=0.8 ¦ Optimal=0.95 ¦ Ceiling=1 ¦¦ Implementation Data: Output field='Good/Average/Poor'; Standard/Reference='Nielsen Norman Group Usability Heuristics' | 0 | No Dependency |  | The 200ms tab-switch budget, measured. Last of the navigation work because it is the check on all of it -- a benchmark written before the tabs exist measures nothing. Consumes the motion ceiling already set in Step 11. | -
45 | 45 - Content Layout | 8265 | GEN-00022 | GEN-00022 | Configure dashboard widgets and audit forms to stack vertically in a single-column or 2x2 grid on mobile. | Configure dashboard widgets and audit forms to stack vertically in a single-column or 2x2 grid on mobile. | 1. Plan and scope this step. 2. Implement the core configuration. 3. Test and validate in staging. 4. Document and commit to runbook. | Architecture & Implementation Governance | What exact configuration and validation approach should be applied for: Configure dashboard widgets and audit forms to stack vertically in a single-colu? | UX Flow / BigQuery | Configure dashboard widgets and audit forms to stack vertically in a single-column or 2x2 grid on mo is a critical implementation step. Without it, downstream steps lack the required baseline configuration. | Ensures sub-100ms API response latencies on mobile clients via optimized backend configuration. | Single-column mobile layout with M3 status cards displaying step completion state. | Data/artifacts to prepare: Configure dashboard widgets and audit forms to stack vertically in…. Metric config: 'Cross-Viewport Rendering Consistency' (floor threshold: Zero regressions on primary breakpoints (360/390/412px)). Reference standard/spec to configure against: W3C Responsive Images/Web Design guidelines; BrowserStack device-matrix best practice. Output field to capture: Pass/Fail. | Users interact with this step exclusively through the mobile engineering console. Read-only M3 KPI cards with deep-link drill-down. | Engineering console dashboard displays step health via M3 Elevated Card with inline status chip. | English Code (EC) blueprint required before any code is written. All functions must have single-verb EC headers. | Core pattern for this step stored as a reusable module in the shared library. | @habot/shared-library | All step execution events stream to BigQuery partitioned by event_date, clustered by trace_id. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: N/A ¦ Row: 8265.0 | 4 Hours | Fully configured and validated implementation of: Configure dashboard widgets and audit forms to stack vertically in a single-colu. | 100% CI/CD pass rate. All validation checks passing. Documentation committed to runbook. | Dependent on prior foundational steps. | M3 responsive layout: single-column on mobile (<600dp), multi-column on desktop (≥840dp). | M3 Elevated Cards Level 2 (3dp). M3 Status Chips for health indicators. 48x48dp touch targets. | Background polling refreshes data every 30 seconds. Pull-to-refresh triggers manual sync. | M3 Bottom Sheet for configuration inputs. M3 Snackbar for confirmations. Material You dynamic color. | Mobile Engineering, GCP Architecture, UX/UI Design (MD3), DCDF Engine Architecture. | CI/CD pipeline physically blocks deployment if any gate for this step fails. | Automated Liveness Handshake monitors this step every 30 seconds and triggers rollback on failure. | Eliminates manual overhead, reduces operational cost, and protects revenue pipelines. | Engineers and end-users experience reliable, uninterrupted platform performance. | M3 responsive single-column on mobile, multi-panel on tablet/desktop. 48x48dp touch targets. | Us: Eliminates manual overhead and reduces operational cost. ¦ Customer: Reliable, uninterrupted platform performance. | Configure dashboard widgets and audit forms to stack vertically in a single-column or 2x2 grid on mo | Configure dashboard widgets and audit forms to stack vertically in a single-column or 2x2 grid on mobile. | Cross-Viewport Rendering Consistency | Zero regressions on primary breakpoints (360/390/412px) | Zero regressions across full tested device matrix | N/A (zero-tolerance metric, no upper bound) | Pass/Fail | W3C Responsive Images/Web Design guidelines; BrowserStack device-matrix best practice | Fredrick | Configure dashboard widgets and audit forms to stack vertically in…; Completion Status ('Pass/Fail'); Action/Event Timestamp; User/Session ID | Data Required: Cross-Viewport Rendering Consistency ¦¦ Configuration Data: Floor=Zero regressions on primary breakpoints (360/390/412px) ¦ Optimal=Zero regressions across full tested device matrix ¦ Ceiling=N/A (zero-tolerance metric, no upper bound) ¦¦ Implementation Data: Output field='Pass/Fail'; Standard/Reference='W3C Responsive Images/Web Design guidelines; BrowserStack device-matrix best practice' | 0 | No Dependency |  | Dashboard widgets and audit forms stacking to a single column or a 2x2 grid on mobile. The first consumer of the grid spec from Step 39, and the step that proves the shell can actually hold content rather than just divide space. | 46
46 | 46 - Content Guard | 10289 | GEN-02060 | GEN-02060 | Ensure text breathes and fits its container without truncating unreadably on 320dp screens. | Ensure text breathes and fits its container without truncating unreadably on 320dp screens. | 1. Plan and scope this step. 2. Implement the core configuration. 3. Test and validate in staging. 4. Document and commit to runbook. | Architecture & Implementation Governance | What exact configuration and validation approach should be applied for: Ensure text breathes and fits its container without truncating unreadably on 320? | UX Flow / BigQuery | Ensure text breathes and fits its container without truncating unreadably on 320dp screens. is a critical implementation step. Without it, downstream steps lack the required baseline configuration. | Ensures sub-100ms API response latencies on mobile clients via optimized backend configuration. | Single-column mobile layout with M3 status cards displaying step completion state. | Data/artifacts to prepare: Ensure text breathes and fits its container without truncating unreadably…. Metric config: 'Step Completion Rate (%)' (floor threshold: 90). Reference standard/spec to configure against: ISO/IEC 27001:2022 General Standards. Output field to capture: Complete/Partial/Not Complete. | Users interact with this step exclusively through the mobile engineering console. Read-only M3 KPI cards with deep-link drill-down. | Engineering console dashboard displays step health via M3 Elevated Card with inline status chip. | English Code (EC) blueprint required before any code is written. All functions must have single-verb EC headers. | Core pattern for this step stored as a reusable module in the shared library. | @habot/shared-library | All step execution events stream to BigQuery partitioned by event_date, clustered by trace_id. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: N/A ¦ Row: 10289.0 | 4 Hours | Fully configured and validated implementation of: Ensure text breathes and fits its container without truncating unreadably on 320. | 100% CI/CD pass rate. All validation checks passing. Documentation committed to runbook. | Dependent on prior foundational steps. | M3 responsive layout: single-column on mobile (<600dp), multi-column on desktop (≥840dp). | M3 Elevated Cards Level 2 (3dp). M3 Status Chips for health indicators. 48x48dp touch targets. | Background polling refreshes data every 30 seconds. Pull-to-refresh triggers manual sync. | M3 Bottom Sheet for configuration inputs. M3 Snackbar for confirmations. Material You dynamic color. | Mobile Engineering, GCP Architecture, UX/UI Design (MD3), DCDF Engine Architecture. | CI/CD pipeline physically blocks deployment if any gate for this step fails. | Automated Liveness Handshake monitors this step every 30 seconds and triggers rollback on failure. | Eliminates manual overhead, reduces operational cost, and protects revenue pipelines. | Engineers and end-users experience reliable, uninterrupted platform performance. | M3 responsive single-column on mobile, multi-panel on tablet/desktop. 48x48dp touch targets. | Us: Eliminates manual overhead and reduces operational cost. ¦ Customer: Reliable, uninterrupted platform performance. | Ensure text breathes and fits its container without truncating unreadably on 320dp screens. | Ensure text breathes and fits its container without truncating unreadably on 320dp screens. | Step Completion Rate (%) | 90.0 | 99.0 | 100.0 | Complete/Partial/Not Complete | ISO/IEC 27001:2022 General Standards | Fredrick | Ensure text breathes and fits its container without truncating unreadably…; Completion Status ('Complete/Partial/Not Complete'); Action/Event Timestamp; User/Session ID | Data Required: Step Completion Rate (%) ¦¦ Configuration Data: Floor=90 ¦ Optimal=99 ¦ Ceiling=100 ¦¦ Implementation Data: Output field='Complete/Partial/Not Complete'; Standard/Reference='ISO/IEC 27001:2022 General Standards' | 0 | No Dependency |  | Text fits its container without unreadable truncation at 320dp -- the narrowest device in your matrix. Deliberately after the layout steps rather than before: this is the guard that catches what they broke, and it has nothing to check until they exist. | -
47 | 47 - Shell State | 10938 | GEN-02720 | GEN-02720 | Write the offline UI state management logic that activates when the polling function fails to receive a response within the timeout threshold. | Write the offline UI state management logic that activates when the polling function fails to receive a response within the timeout threshold. | 1. Plan and scope this step. 2. Implement the core configuration. 3. Test and validate in staging. 4. Document and commit to runbook. | Architecture & Implementation Governance | What exact configuration and validation approach should be applied for: Write the offline UI state management logic that activates when the polling func? | UX Flow / BigQuery | Write the offline UI state management logic that activates when the polling function fails to receiv is a critical implementation step. Without it, downstream steps lack the required baseline configuration. | Ensures sub-100ms API response latencies on mobile clients via optimized backend configuration. | Single-column mobile layout with M3 status cards displaying step completion state. | Data/artifacts to prepare: Write the offline UI state management logic that activates when…. Metric config: 'Implementation Completeness Rate' (floor threshold: 90% of defined build scope completed). Reference standard/spec to configure against: DORA — DevOps Research — Implementation Quality Standards. Output field to capture: Complete / Partial / Not Complete. | Users interact with this step exclusively through the mobile engineering console. Read-only M3 KPI cards with deep-link drill-down. | Engineering console dashboard displays step health via M3 Elevated Card with inline status chip. | English Code (EC) blueprint required before any code is written. All functions must have single-verb EC headers. | Core pattern for this step stored as a reusable module in the shared library. | @habot/shared-library | All step execution events stream to BigQuery partitioned by event_date, clustered by trace_id. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: N/A ¦ Row: 10938.0 | 4 Hours | Fully configured and validated implementation of: Write the offline UI state management logic that activates when the polling func. | 100% CI/CD pass rate. All validation checks passing. Documentation committed to runbook. | Dependent on prior foundational steps. | M3 responsive layout: single-column on mobile (<600dp), multi-column on desktop (≥840dp). | M3 Elevated Cards Level 2 (3dp). M3 Status Chips for health indicators. 48x48dp touch targets. | Background polling refreshes data every 30 seconds. Pull-to-refresh triggers manual sync. | M3 Bottom Sheet for configuration inputs. M3 Snackbar for confirmations. Material You dynamic color. | Mobile Engineering, GCP Architecture, UX/UI Design (MD3), DCDF Engine Architecture. | CI/CD pipeline physically blocks deployment if any gate for this step fails. | Automated Liveness Handshake monitors this step every 30 seconds and triggers rollback on failure. | Eliminates manual overhead, reduces operational cost, and protects revenue pipelines. | Engineers and end-users experience reliable, uninterrupted platform performance. | M3 responsive single-column on mobile, multi-panel on tablet/desktop. 48x48dp touch targets. | Us: Eliminates manual overhead and reduces operational cost. ¦ Customer: Reliable, uninterrupted platform performance. | Write the offline UI state management logic that activates when the polling function fails to receiv | Write the offline UI state management logic that activates when the polling function fails to receive a response within the timeout threshold. | Implementation Completeness Rate | 90% of defined build scope completed | 100% of scope complete with peer validation | 1.0 | Complete / Partial / Not Complete | DORA — DevOps Research — Implementation Quality Standards | Fredrick | Write the offline UI state management logic that activates when…; Completion Status ('Complete / Partial / Not Complete'); Action/Event Timestamp; User/Session ID | Data Required: Implementation Completeness Rate ¦¦ Configuration Data: Floor=90% of defined build scope completed ¦ Optimal=100% of scope complete with peer validation ¦¦ Implementation Data: Output field='Complete / Partial / Not Complete'; Standard/Reference='DORA — DevOps Research — Implementation Quality Standards' | 0 | No Dependency |  | The offline state machine, triggered when polling passes its timeout. Before the banner because the banner is a view of this state; building the view first means inventing a second source of truth for whether the app is offline. | 48
48 | 48 - Shell State | 11653 | GEN-03437 | GEN-03437 | Display an "Offline Mode" status banner and pending queue counters on UI screens. | Display an "Offline Mode" status banner and pending queue counters on UI screens. | 1. Plan and scope this step. 2. Implement the core configuration. 3. Test and validate in staging. 4. Document and commit to runbook. | Architecture & Implementation Governance | What exact configuration and validation approach should be applied for: Display an "Offline Mode" status banner and pending queue counters on UI screens? | UX Flow / BigQuery | Display an "Offline Mode" status banner and pending queue counters on UI screens. is a critical implementation step. Without it, downstream steps lack the required baseline configuration. | Ensures sub-100ms API response latencies on mobile clients via optimized backend configuration. | Single-column mobile layout with M3 status cards displaying step completion state. | Data/artifacts to prepare: Offline Mode. Metric config: 'Banner Contrast Ratio' (floor threshold: 4.5:1). Reference standard/spec to configure against: WCAG 2.2 AA Contrast Standards. Output field to capture: Pass. | Users interact with this step exclusively through the mobile engineering console. Read-only M3 KPI cards with deep-link drill-down. | Engineering console dashboard displays step health via M3 Elevated Card with inline status chip. | English Code (EC) blueprint required before any code is written. All functions must have single-verb EC headers. | Core pattern for this step stored as a reusable module in the shared library. | @habot/shared-library | All step execution events stream to BigQuery partitioned by event_date, clustered by trace_id. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: N/A ¦ Row: 11653.0 | 4 Hours | Fully configured and validated implementation of: Display an "Offline Mode" status banner and pending queue counters on UI screens. | 100% CI/CD pass rate. All validation checks passing. Documentation committed to runbook. | Dependent on prior foundational steps. | M3 responsive layout: single-column on mobile (<600dp), multi-column on desktop (≥840dp). | M3 Elevated Cards Level 2 (3dp). M3 Status Chips for health indicators. 48x48dp touch targets. | Background polling refreshes data every 30 seconds. Pull-to-refresh triggers manual sync. | M3 Bottom Sheet for configuration inputs. M3 Snackbar for confirmations. Material You dynamic color. | Mobile Engineering, GCP Architecture, UX/UI Design (MD3), DCDF Engine Architecture. | CI/CD pipeline physically blocks deployment if any gate for this step fails. | Automated Liveness Handshake monitors this step every 30 seconds and triggers rollback on failure. | Eliminates manual overhead, reduces operational cost, and protects revenue pipelines. | Engineers and end-users experience reliable, uninterrupted platform performance. | M3 responsive single-column on mobile, multi-panel on tablet/desktop. 48x48dp touch targets. | Us: Eliminates manual overhead and reduces operational cost. ¦ Customer: Reliable, uninterrupted platform performance. | Display an "Offline Mode" status banner and pending queue counters on UI screens. | Display an "Offline Mode" status banner and pending queue counters on UI screens. | Banner Contrast Ratio | 4.5:1 | 7:1 | 21:1 | Pass | WCAG 2.2 AA Contrast Standards | Fredrick | Offline Mode; Completion Status ('Pass'); Action/Event Timestamp; User/Session ID | Data Required: Banner Contrast Ratio ¦¦ Configuration Data: Floor=4.5:1 ¦ Optimal=7:1 ¦ Ceiling=21:1 ¦¦ Implementation Data: Output field='Pass'; Standard/Reference='WCAG 2.2 AA Contrast Standards' | 0 | No Dependency |  | The Offline Mode banner and pending-queue counters, rendering the state from Step 47. Its metric is a contrast ratio (4.5:1 floor, 7:1 optimal), which the WCAG engine from Step 4 measures directly -- one of the few GEN-* rows in this batch with a metric that genuinely fits its step. | -
49 | 49 - Destination | 2039 | IS22-RCGLA-022-AS01 | IS22-RCGLA-022-AS01-A01 | Build and deploy a responsive preference manager panel inside client settings. | Open the client settings directory within the main UI portal repository. | 1. Map explicit preference columns (allow_promo, allow_transaction) inside user state tables. ¦ 2. Render responsive configuration controls linked directly to these column models. ¦ 3. Update user database preferences instantly when sliders change on screen. ¦ 4. Connect configuration choices directly to core outbound message workflows. | Interface Product Design | Select acceptable visual spacing boundaries for preference layout lists. | Interaction / UX Flow | Replaces messy layout structures with an automated, highly clean user configuration pane. | Highly optimized local client preference mapping slashes backend query delays during data checks. | Render simple selection rows using modern Material Design styling treatments. | Atomic-level data fields: Repository URL; Repository Branch; Access Rights; Commit History; Repository Version; Clone Status ¦¦ No matched reference row in Setup Implementation master list — required data fields limited to atomic-level Data Collection Requirements only; standardized Mobile UX/UI & domain-expertise fields unavailable, verify manually. | Users control platform alert frequencies smoothly without encountering extra hurdles. | Displays true user configuration choices on administration overview logs. | Process all preference adjustment metrics through a standard configuration toolkit. | NotificationPreferenceSheet UI wrapper block. | Shared corporate layout configuration module directory. | Preference updates map to streaming system metrics tables for real-time engagement insights. | Level 9 ¦ Phase: SETUP-09 ¦ Atomic Step: 1.0 ¦ Row: 2039.0 | 5 Minutes. | Operational settings component bundle running inside client applications. | Preference changes write to the database accurately during interface evaluation loops. | HC-INF-0003, HC-FE-0100. | Match modern Material Design settings layout guidelines. | Render highly explicit status summaries next to toggle controls. | Use generous touch area guidelines for all interactive items. | Apply sharp text contrast to ensure absolute readability on mobile screens. | Mobile Frontend Application Architecture / UI Experience Optimization. | Selection inputs freeze screen transitions until changes write to database rows. | Broken logic layers trigger an immediate system block alert to data management controllers | Slashes human data processing errors by removing visual clutter from outsourced task screens. | Assures parents that private family details are deeply hidden from worker views. | Match modern Material Design settings layout guidelines. ¦ Render highly explicit status summaries next to toggle controls. ¦ Use generous touch area guidelines for all interactive items. ¦ Apply sharp text contrast to ensure absolute readability on mobile screens. |  | Build and deploy a responsive preference manager panel inside client settings. | Open the client settings directory within the main UI portal repository. | Asset & Component Discovery Completeness - Client settings directory main ui portal | 90% of target assets confirmed present | 100% of target assets confirmed present | 100% (full inventory - no further discovery value beyond complete coverage) | Complete/Partial/Not Complete | Confirm the full inventory of the referenced files, components, or directories is located before any downstream configuration begins; partial discovery is the leading cause of rework later in the build. | Fredrick | Repository URL; Repository Branch; Access Rights; Commit History; Repository Version; Clone Status; Completion Status ('Complete/Partial/Not Complete'); Action/Event Timestamp; User/Session ID | Data Required: Asset & Component Discovery Completeness - Client settings directory main ui portal ¦¦ Configuration Data: Floor=90% of target assets confirmed present ¦ Optimal=100% of target assets confirmed present ¦ Ceiling=100% (full inventory - no further discovery value beyond complete coverage) ¦¦ Implementation Data: Output field='Complete/Partial/Not Complete'; Standard/Reference='Confirm the full inventory of the referenced files, components, or directories is located before any downstream configuration begins; partial…' | 0 | No Dependency |  | The preference manager panel: the first real destination the shell hosts, rather than a probe screen. Richly specified -- mapped preference columns, responsive containers, a spacing decision and a poka-yoke that freezes transitions until a change is written. Needs the shell (36-40) to have somewhere to put it. | 50
50 | 50 - Destination | 11620 | GEN-03404 | GEN-03404 | Build the mobile notification preference screen using M3 Switch components. | Build the mobile notification preference screen using M3 Switch components. | 1. Plan and scope this step. 2. Implement the core configuration. 3. Test and validate in staging. 4. Document and commit to runbook. | Architecture & Implementation Governance | What exact configuration and validation approach should be applied for: Build the mobile notification preference screen using M3 Switch components.? | UX Flow / BigQuery | Build the mobile notification preference screen using M3 Switch components. is a critical implementation step. Without it, downstream steps lack the required baseline configuration. | Ensures sub-100ms API response latencies on mobile clients via optimized backend configuration. | Single-column mobile layout with M3 status cards displaying step completion state. | Data/artifacts to prepare: Build the mobile notification preference screen using M3 Switch components.. Metric config: 'Preference Screen Render Time' (floor threshold: < 100ms). Reference standard/spec to configure against: Material Design 3 Screens. Output field to capture: Complete. | Users interact with this step exclusively through the mobile engineering console. Read-only M3 KPI cards with deep-link drill-down. | Engineering console dashboard displays step health via M3 Elevated Card with inline status chip. | English Code (EC) blueprint required before any code is written. All functions must have single-verb EC headers. | Core pattern for this step stored as a reusable module in the shared library. | @habot/shared-library | All step execution events stream to BigQuery partitioned by event_date, clustered by trace_id. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: N/A ¦ Row: 11620.0 | 4 Hours | Fully configured and validated implementation of: Build the mobile notification preference screen using M3 Switch components.. | 100% CI/CD pass rate. All validation checks passing. Documentation committed to runbook. | Dependent on prior foundational steps. | M3 responsive layout: single-column on mobile (<600dp), multi-column on desktop (≥840dp). | M3 Elevated Cards Level 2 (3dp). M3 Status Chips for health indicators. 48x48dp touch targets. | Background polling refreshes data every 30 seconds. Pull-to-refresh triggers manual sync. | M3 Bottom Sheet for configuration inputs. M3 Snackbar for confirmations. Material You dynamic color. | Mobile Engineering, GCP Architecture, UX/UI Design (MD3), DCDF Engine Architecture. | CI/CD pipeline physically blocks deployment if any gate for this step fails. | Automated Liveness Handshake monitors this step every 30 seconds and triggers rollback on failure. | Eliminates manual overhead, reduces operational cost, and protects revenue pipelines. | Engineers and end-users experience reliable, uninterrupted platform performance. | M3 responsive single-column on mobile, multi-panel on tablet/desktop. 48x48dp touch targets. | Us: Eliminates manual overhead and reduces operational cost. ¦ Customer: Reliable, uninterrupted platform performance. | Build the mobile notification preference screen using M3 Switch components. | Build the mobile notification preference screen using M3 Switch components. | Preference Screen Render Time | < 100ms | < 30ms | 200ms | Complete | Material Design 3 Screens | Fredrick | Build the mobile notification preference screen using M3 Switch components.; Completion Status ('Complete'); Action/Event Timestamp; User/Session ID | Data Required: Preference Screen Render Time ¦¦ Configuration Data: Floor=< 100ms ¦ Optimal=< 30ms ¦ Ceiling=200ms ¦¦ Implementation Data: Output field='Complete'; Standard/Reference='Material Design 3 Screens' | 0 | No Dependency |  | The notification preference screen, built from M3 switches inside the panel Step 49 delivers. Last because it is the narrowest and most dependent thing in the batch: a screen, inside a panel, inside a shell, reached through a route -- every layer below it built first. | -